## Slide 1
SUMMARY's SCHEDULE |  |  |  |  |  | 
 | BLM's | Dismounting (days) | Re-Installation (days) | RSM(nights) | Total days | Weeks
R1: Q1-Q11 | 84 | 1.5 | 2.5 | 1 | 5 | 1
ARC12: Q12-Q12 | 272 | 3 | 6 | 1.5 | 10.5 | 2,3
L2:Q1-Q11 | 98 | 1.5 | 2.5 | 1 | 5 | 4
R2:Q1-Q11 | 96 | 1.5 | 2.5 | 1 | 5 | 5
ARC23: Q12-Q12 | 280 | 3 | 6 | 1.5 | 10.5 | 6,7
L3:Q6-Q11 | 74 | 1.5 | 2.5 | 1 | 5 | 8
R3:Q6-Q11 | 74 | 1.5 | 2.5 | 1 | 5 | 9
ARC34: Q12-Q12 | 278 | 3 | 6 | 1.5 | 10.5 | 10,11
L4: Q5-Q11 | 47 | 1 | 1.5 | 1 | 3.5 | 12
R4: Q5-Q11 | 47 | 1 | 1.5 | 1 | 3.5 | 12, 13(1/2)
ARC45: Q12-Q12 | 272 | 3 | 6 | 1.5 | 10.5 | 13,14, 15(1/2)
L5:Q1-Q11 | 81 | 1.5 | 2.5 | 1 | 5 | 15, 16(1/2)
R5:Q1-Q11 | 82 | 1.5 | 2.5 | 1 | 5 | 16, 17(1/2)
ARC56: Q12-Q12 | 272 | 3 | 6 | 1.5 | 10.5 | 17,18, 19(1/2)
L6:Q4-Q5,Q8-Q11 | 36 | 0.5 | 1 | 0.5 | 2 | 19
R6:Q4-Q5,Q8-Q11 | 36 | 0.5 | 1 | 0.5 | 2 | 20(1/2)
ARC67: Q12-Q12 | 276 | 3 | 6 | 1.5 | 10.5 | 20,21, 22(1/2)
L7:Q6-Q11 | 61 | 1.5 | 2 | 1 | 4.5 | 22, 23(1/2)
R7:Q4-Q5,Q8-Q11 | 64 | 1.5 | 2 | 1 | 4.5 | 23, 24(1/2)
ARC78: Q12-Q12 | 270 | 3 | 6 | 1.5 | 10.5 | 24,25, 26(1/2)
L8:Q1-Q11 | 90 | 1.5 | 2.5 | 1 | 5 | 26, 27(1/2)
R8:Q1-Q11 | 90 | 1.5 | 2.5 | 1 | 5 | 27, 28(1/2)
ARC81: Q12-Q12 | 270 | 3 | 6 | 1.5 | 10.5 | 28,29, 30(1/2)
L1:Q1-Q11 | 83 | 1.5 | 2.5 | 1 | 5 | 30,31
Total days |  | 45 | 82 | 27 | 154 | 
 |  | consequent works for 4 person's team +1 superviser(especially for RSM)- > |  |  |  | 31 weeks
2010 Planning

## Slide 2
 |  |  |  |  | 16 Quads/day
 |  |  |  |  | all 6 monitors
 |  | Quads (12L-12R) | BLM | Additional BLM | Dismounting (days)
1 | ARC12 | 45 | 270 | 2 | 3
2 | ARC23 | 45 | 270 | 10 | 3
3 | ARC34 | 45 | 270 | 8 | 3
4 | ARC45 | 45 | 270 | 2 | 3
5 | ARC56 | 45 | 270 | 2 | 3
6 | ARC67 | 45 | 270 | 6 | 3
7 | ARC78 | 45 | 270 | 0 | 3
8 | ARC81 | 45 | 270 | 0 | 3
 | Total(days) |  |  | 2 | 23
 |  |  |  |  |  | 6 Quads/day
 |  |  |  |  |  | all 8 monitors
 |  |  |  |  |  | 48 BLM/day
 |  |  | Quads (12L-12R) | BLM | Additional BLM | Installation (days)
 | 1 | ARC12 | 45 | 270 | 92 | 8
 | 2 | ARC23 | 45 | 270 | 100 | 8
 | 3 | ARC34 | 45 | 270 | 98 | 8
 | 4 | ARC45 | 45 | 270 | 92 | 8
 | 5 | ARC56 | 45 | 270 | 92 | 8
 | 6 | ARC67 | 45 | 270 | 96 | 8
 | 7 | ARC78 | 45 | 270 | 90 | 8
 | 8 | ARC81 | 45 | 270 | 90 | 8
ARC: Dismounting of current installed BLMs
ARC: Installation of existing and 2 more BLMs
ARC: RSM
1 sourse, 2->-> teams,18:00-6:00;12 (6+6) hours
or 2 sourse, ¦¦ 2 teams, 6 hours
30 quads/night
 | Quads (12L-12R) | BLM | Nights(18:00-6:00)
1 | ARC12 | 362 | 3
2 | ARC23 | 370 | 3
3 | ARC34 | 368 | 3
4 | ARC45 | 362 | 3
5 | ARC56 | 362 | 3
6 | ARC67 | 366 | 3
7 | ARC78 | 360 | 3
8 | ARC81 | 360 | 3

## Slide 3: Splices
PT
PT
PT
PT
PT
PT
PT
PT
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Splices
Warm-up
Preparation for cool-down
Cool-down
Splices
Splices
Splices
Splices
Splices
Splices
Splices
Splices
Jean-Philippe : “LHC consolidation of the superconducting circuits ”
-> 10K
CSCM
CSCM preparation
Warm-up
Warm-up
Warm-up
Warm-up
Warm-up
Warm-up
Warm-up
Warm-up
Cool-down
Cool-down
Cool-down
Cool-down
Cool-down
Cool-down
Cool-down
Cool-down

## Slide 4: Splices
PT
PT
PT
PT
PT
PT
PT
PT
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Powering Tests
Splices
Warm-up
Preparation for cool-down
Cool-down
Splices
Splices
Splices
Splices
Splices
Splices
Splices
Splices
Jean-Philippe : “LHC consolidation of the superconducting circuits ”
-> 10K
CSCM
CSCM preparation
Warm-up
Warm-up
Warm-up
Warm-up
Warm-up
Warm-up
Warm-up
Warm-up
Cool-down
Cool-down
Cool-down
Cool-down
Cool-down
Cool-down
Cool-down
Cool-down
3/12 - 21/12 |  | 
1 week |  | 
 | 1 week | 
 |  | 1 week
7/01-13/01
14/01 – 03/02 |  | 
1 week |  | 
 | 1 week | 
 |  | 1 week
4/02-11/02
Dismounting BLM: Dec,Jan,Feb
1 week
12/08-08/09
4 weeks
09/09-06/10
4 weeks
7/10-3/11
4 weeks
4/11-1/12
4 weeks
RMS
Installation BLM: Aug,Sep,Oct,Nov
8 weeks during the night for RSM : Dec,Jan2014