## Slide 1: IHEP (visit of V. Seleznev and A. Larionov)
Bernd Dehning
CERN BE/BI

## Slide 2: IHEP – CERN BE-BI-BL II
Contract for regular test of the vacuum, filling and production stand (standby contract)
  Skrinsky II contracts are not any more possible
  New contract type (cooperation agreement: KN contract) has to be agreed by CERN management
    Max amount 200 kCHF, if more contracts need to be split)
  New contract proposal will be provided by T. Kurtyka by mid of March
  Highest priority for contract to be signed
Preparation of contract for de-installation, installation and test of BLM system at CERN during the LS1
  BL will make new estimate of needed volume taking into account Chamonix planning
  BL will estimate the option of distributing the chambers along the magnets in the LHC arc and having two more ionization chamber per half cell located
  Contract proposal will be made by BL taking previous installation contract into account
  Proposal of contract to be finished end of March

## Slide 3: IHEP – CERN BE-BI-BL II
Production of IC for SACLAY
  Request of 50 ionization chamber received
  Update of drawings
    Tightner changes, change of endplate diameter, …
    Designer need to be reserved for it, begin March
  Update of procedure
    Test to be done up 3 kV, development of soldering test
  Monitors to be delivered to Saclay in December 2012
  cooperation agreement: KN contract to be prepared for production by the end of March
  Aiming for contract to be signed by May
  in case monitors are not produced in time spare LHC ionization chambers will be shipped to Saclay
Evaluation of option: production of about 800 new IC for the LHC
  Decision for production to be made by CERN in March
  Last date for installation do be defined, CERN
  Preparation of schedule CERN-IHEP
Brain storming of design and production of a flat IC (BOOSTER)
  To be continued by CERN, BOOSTER simulation, space requirements
  In case of production decided after LHC ionization chambers