## Drawings
LIC Production - Drawing list - 17.12.2010
Drawing information | [5 empty] | Production issues
Drawing number | Remark |  | Vers. | See | Q. Ass. | Qty. | Spare | Pro. Qty. | Total | Material | Manuf. | Assembly | Remarks | Order by | Status
LHCBLM__0087 | on work | ELECTRICAL CONNECTORS - LIC ASSEMBLY | 1st | See |  | 300 | 15 | 0 | 315 |  |  | Protvino | drawing to upgrade | JMM
LHCBLM__0037 |  | ELECTRICAL CONNECTION - EXTERNAL PLATE | C | See | 1 | 300 | 15 | 0 | 315 | CERN | External | Protvino |  | JMM
LHCBLM__0038 |  | ELECTRICAL CONNECTION - EXTERNAL TUBE | B | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM
LHCBLM__0056 |  | SCREEN FOR SEM COVER - | 1st | See | 1 | 300 | 15 | 0 | 315 | External | External |  |  | JMM
LHCBLM__0084 | on work | LIC ASSEMBLY - ALUMINIUM ELECTRODES | 1st | See | 1 | 300 | 15 | 0 | 315 |  |  | Protvino |  | JMM
LHCBLM__0004 | TYPE 1 | MULTIPLE ELECTRODE BLM - ELECTRODE | B | See | 3 | 900 | 45 | 1000 | 0
LHCBLM__0007 | TYPE E | MULTIPLE ELECTRODE BLM - ELECTRODE SPACERS | D | See | 6 | 1800 | 90 | 0 | 1890 | CERN | External |  |  | JMM
LHCBLM__0007 | TYPE A | MULTIPLE ELECTRODE BLM - ELECTRODE SPACERS | D | See | 3 | 900 | 45 | 1000 | 0
LHCBLM__0081 |  | LIC ELECTRODES - BOTTOM COVER | 1st | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM
LHCBLM__0052 |  | SEM-TITANIUM ELECTRODES - ELECTRICAL CONNECTION | 1st | See | 2 | 600 | 30 | 0 | 630 | External | External |  |  | JMM
LHCBLM__0040 | TYPE D | MULTIPLE ELECTRODE BLM - EXTERNAL TUBE | B | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM
LHCBLM__0086 | on work | LIC ALUMINIUM ELECTRODES - COVER ASSEMBLY | A | See | 1 | 300 | 15 | 0 | 315 |  |  | Protvino | drawing to upgrade | JMM
LHCBLM__0082 |  | LIC ELECTRODES - COVER | 1st | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM
LHCBLM__0035 |  | WELDED SPACER - | A | See | 3 | 900 | 45 | 1220 | 0
LHCBLM__0088 |  | MANCHON ISOLANT - | 1st | See | 4 | 1200 | 60 | 0 | 1260 | External | External |  | Manufacture according to drawing LHCBLM__0055 | JMM | 4483010
LHCBLM__0083 |  | ELECTRICAL SHIELDING - FOR FEEDTHROUGH | 1st | See | 2 | 600 | 30 | 0 | 630 | External | External |  |  | JMM
LHCBLM__0085 |  | HOLDER ON COVER - | 1st | See | 1 | 300 | 15 | 0 | 315 | External | External |  |  | JMM
Note on G5: jherranz: Is the quantity requested in the assembly to which this drawing belongs
Note on I5: jherranz: Quantity of spare chambers to build
Note on J5: jherranz: Quantity availabe in Protvino
Note on K5: jherranz: Quantity of units to produce = Q. Ass. x (Qty + Spare)
Note on L5: jherranz: Where is foreseen to order the material, i.e: CERN, external supplier…
Note on M5: jherranz: Where is foreseen to manufacture the product i.e: CERN, supplier name…
Note on N5: jherranz: Where is foreseen to assembly (welding, bolted or other) the parts i.e: CERN, external supplier…

## Commercial
LIC Production - Commercial part list - 17.12.2010
Commercial part information | [8 empty] | Ordering information
Qty. | Descrition | Pos. | Material | Dimension | Norm. | Remarks | Ref. CERN | Assembly | Ass. Qty. | Pro. Qty. | T. Qty. | Remarks | Order by | Status
3 | Round tube dia. 7/4 | 4 | AW6082 | L=60.5 |  |  |  | LHBLM__0087 | 315 | 0 | 945 | need manufacturing: cutting | JMM
3 | Threaded rod M4x85 | 5 | SS A2 | M4x85 |  |  |  | LHBLM__0087 | 315 | 0 | 945 | need manufacturing: cutting | JMM
3 | Washer M4 | 6 | SS A2 | M4 |  |  |  | LHBLM__0087 | 315 | 0 | 945 |  | JMM
6 | Nut M4 | 7 | SS A2 | M4 |  |  |  | LHBLM__0087 | 315 | 1800 | 90 |  | JMM
1 | Hex. Hd point screw M3x5 | 8 | SS A2 | M3x5 |  |  |  | LHBLM__0087 | 315 | 0 | 315 |  | JMM
1 | Signal connector | 9 |  |  |  |  | 09.41.25.160.9 | LHBLM__0087 | 315 | 0 | 315 |  | JMM
2 | H.V. connector | 10 |  |  |  |  | 09.46.11.360.4 | LHBLM__0087 | 315 | 0 | 630 |  | JMM
1 | Capacitor | 11 |  |  |  | WIMA MKP 10-0.47microF/2000V |  | LHBLM__0087 | 315 | 100 | 215 |  | BE/BI/BLM
1 | Resistor | 12 |  |  |  | EBG SOX 20-10MOhm/15kV |  | LHBLM__0087 | 315 | 315 | 0
1 | TERM.CAB.S.SINGLE | ?? |  |  |  | D 4,2X23,5mm | 04.76.26.448.1 | LHBLM__0087 | 315 | 0 | 315 |  | BE/BI/BLM
1 | BRASS SOLDER.CAB.T. | ?? |  |  |  | BNC 50 OHM | 09.46.11.520.6 | LHBLM__0087 | 315 | 0 | 315 |  | BE/BI/BLM
18 | Washer dia. 8/4.2 thk 0.2 | 8 | 1.4310 | 8/4.2 thk 0.2 | BN838 | Bossard BN838 |  | LHBLM__0084 | 315 | 4300 | 1370 |  | JMM
6 | Nut M4 | 9 | SS A4 | M4 |  |  |  | LHBLM__0084 | 315 | 0 | 1890 |  | JMM
4 | Hdless screw M3x3 | 10 | SS A4 | M3x3 | BN618 | Bossard BN618 |  | LHBLM__0084 | 315 | 2000 | 0
2 | FEEDTHROUGH | 2 |  |  |  | CERAMASEAL 3887-12-W |  | LHBLM__0086 | 390 | 0 | 780 |  | BE/BI/BLM
1 | Round tube dia. 10 x 8 mm | 6 | COPPER | L=120 mm |  |  | 39.71.20.008.8 | LHBLM__0086 | 315 | 0 | 315 | need manufacturing: cutting, annealing, UHV cleaning and packing | JMM
Note on B5: jherranz: Is the quantity requested in the assembly to which this part belongs
Note on D5: jherranz: Is the possition in the assembly drawing for this part
Note on K5: jherranz: Quantity of assembies to product
Note on L5: jherranz: Quantity availabe in Protvino
Note on M5: jherranz: Total number of parts to order
Note on L9: Viatcheslav Grishin:no vaccuum part
Note on L10: Viatcheslav Grishin: we have M3x4
Note on L18: Viatcheslav Grishin: it's vaccuum part