## Drawings
LIC Production - Drawing list - 17.12.2010
Drawing information | [5 empty] | Production issues
Drawing number | Remark |  | Vers. | See | Q. Ass. | Qty. | Spare | Pro. Qty. | Total | Material | Manuf. | Assembly | Remarks | Order by | Status
LHCBLM__0087 | on work | ELECTRICAL CONNECTORS - LIC ASSEMBLY | 1st | See |  | 300 | 15 | 0 | 315 |  |  | Protvino | drawing to upgrade | JMM
LHCBLM__0037 |  | ELECTRICAL CONNECTION - EXTERNAL PLATE | C | See | 1 | 300 | 15 | 0 | 315 | CERN | External | Protvino |  | JMM
LHCBLM__0038 |  | ELECTRICAL CONNECTION - EXTERNAL TUBE | B | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM
LHCBLM__0056 |  | SCREEN FOR SEM COVER - | 1st | See | 1 | 300 | 15 | 0 | 315 | External | External |  |  | JMM
LHCBLM__0084 | on work | LIC ASSEMBLY - ALUMINIUM ELECTRODES | 1st | See | 1 | 300 | 15 | 0 | 315 |  |  | Protvino |  | JMM
LHCBLM__0004 | TYPE 1 | MULTIPLE ELECTRODE BLM - ELECTRODE | B | See | 3 | 900 | 45 | 1000 | 0
LHCBLM__0007 | TYPE E | MULTIPLE ELECTRODE BLM - ELECTRODE SPACERS | D | See | 6 | 1800 | 90 | 0 | 1890 | CERN | External |  |  | JMM
LHCBLM__0007 | TYPE A | MULTIPLE ELECTRODE BLM - ELECTRODE SPACERS | D | See | 3 | 900 | 45 | 1000 | 0
LHCBLM__0081 |  | LIC ELECTRODES - BOTTOM COVER | 1st | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM
LHCBLM__0052 |  | SEM-TITANIUM ELECTRODES - ELECTRICAL CONNECTION | 1st | See | 2 | 600 | 30 | 0 | 630 | External | External |  |  | JMM
LHCBLM__0040 | TYPE D | MULTIPLE ELECTRODE BLM - EXTERNAL TUBE | B | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM
LHCBLM__0086 | on work | LIC ALUMINIUM ELECTRODES - COVER ASSEMBLY | A | See | 1 | 300 | 15 | 0 | 315 |  |  | Protvino | drawing to upgrade | JMM
LHCBLM__0082 |  | LIC ELECTRODES - COVER | 1st | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM
LHCBLM__0035 |  | WELDED SPACER - | A | See | 3 | 900 | 45 | 1220 | 0
LHCBLM__0088 |  | MANCHON ISOLANT - | 1st | See | 4 | 1200 | 60 | 0 | 1260 | External | External |  | Manufacture according to drawing LHCBLM__0055 | JMM | 4483010
LHCBLM__0083 |  | ELECTRICAL SHIELDING - FOR FEEDTHROUGH | 1st | See | 2 | 600 | 30 | 0 | 630 | External | External |  |  | JMM
LHCBLM__0085 |  | HOLDER ON COVER - | 1st | See | 1 | 300 | 15 | 0 | 315 | External | External |  |  | JMM
order by JMM
|  | DISQUES INOX 316 L |  |  |  | 1000
|  | TUBE INOX 316L D. 6 X 4 RE |  |  |  | 24m
|  | 330 pieces 105mm+330 pieces 66mm-vu avec |  |  |  | 56m
|  | ROUND TU. 304L WELD. 88,9x2,0 |  |  |  | 12m
|  | TUBE INOX 316L D.18 X 15 RE plan LHCBLM__0083.4 |  |  |  | 26m
ELECTRODES SPACERS LIC. Fabrication de : - 1890 "Multiple electrode BLM, electrode spacers" en inox 316L suivant plan LHCBLM__0007.4.D
315 "bottom cover" -> LHCBLM__0081.4 - 315 "external plate" -> LHCBLM__0037.3 (pos. 1) - 630 "electrical shielding for feedthrough -> LHCBLM__0083.4
|  | Fabrication de 315 "LIC electrodes cover" en inox 316L suivant plan LHCBLM__0082.3 |  |  |  | 315 | 4553320
|  | feed throughs |  |  |  | 750 |  | 4553303

## Commercial
LIC Production - Commercial part list - 11.01.11
Commercial part information | [8 empty] | Ordering information
Qty. | Descrition | Pos. | Material | Dimension | Norm. | Remarks | Ref. CERN | Assembly | Ass. Qty. | Pro. Qty. | T. Qty. | Remarks | Order by | Status
3 | Round tube dia. 7/4 | 4 | AW6082 | L=60.5 |  |  |  | LHBLM__0087 | 315 | 0 | 945 | need manufacturing: cutting | JMM
3 | Threaded rod M4x85 | 5 | SS A2 | M4x85 |  |  |  | LHBLM__0087 | 315 | 0 | 945 | need manufacturing: cutting | JMM
3 | Washer M4 | 6 | SS A2 | M4 |  | Bossard BN838 Art. No: 3062667 |  | LHBLM__0087 | 315 | 0 | 945 |  | SG
6 | Nut M4 | 7 | SS A2 | M4 |  |  | 47.43.77.040.1 | LHBLM__0087 | 315 | 1800 | 90 |  | SG
1 | Hex. Hd point screw M3x5 | 8 | SS A2 | M3x5 |  |  | 47.62.96.101.1 | LHBLM__0087 | 315 | 0 | 315 |  | SG
1 | Signal connector | 9 |  |  |  |  | 09.46.11.360.4 | LHBLM__0087 | 315 | 0 | 315 |  | SG
2 | H.V. connector | 10 |  |  |  |  | 09.41.25.160.9 | LHBLM__0087 | 315 | 0 | 630 |  | SG
1 | Capacitor | 11 |  |  |  | WIMA MKP 10-0.47microF/2000V |  | LHBLM__0087 | 315 | 100 | 215 |  | SG
1 | Resistor | 12 |  |  |  | EBG SOX 20-10MOhm/15kV |  | LHBLM__0087 | 315 | 315 | 0 |  | SG
1 | TERM.CAB.S.SINGLE | 14 |  |  |  | D 4,2X23,5mm | 04.76.26.448.1 | LHBLM__0087 | 315 | 0 | 315 |  | SG
1 | BRASS SOLDER.CAB.T. | 15 |  |  |  | BNC 50 OHM | 09.46.11.520.6 | LHBLM__0087 | 315 | 0 | 315 |  | SG
18 | Washer dia. 8/4.2 thk 0.2 | 8 | 1.4310 | 8/4.2 thk 0.2 | BN838 | Bossard BN838 Art. No: 3062667 |  | LHBLM__0084 | 315 | 4300 | 1370 |  | SG
6 | Nut M4 | 9 | SS A4 | M4 |  |  | 47.43.77.040.1 | LHBLM__0084 | 315 | 0 | 1890 |  | SG
4 | Hdless screw M3x3 | 10 | SS A4 | M3x3 | BN618 | Bossard BN618 Art. No: 1748483 |  | LHBLM__0084 | 315 | 2000 | 0 |  | SG
2 | FEEDTHROUGH | 2 |  |  |  | CERAMASEAL 3887-12-W |  | LHBLM__0086 | 390 | 0 | 780 |  | SG
1 | Round tube dia. 10 x 8 mm | 6 | COPPER | L=120 mm |  |  | 39.71.20.008.8 | LHBLM__0086 | 315 | 0 | 315 | need manufacturing: cutting, annealing, UHV cleaning and packing | JMM

## Protvino
# |  | Qty. | Price(CHF) | EDH Number of request
1 | Detergent NGL 17.40SP ALU III | 40 kg (2x20) | 630 | 4550385
2 | Insert Front Olifes | 300 | 390 | 4548629
3 | Insert Rear Olifes | 300 | 360 | 4548629
4 | Kapton tape | 2 | 120 | 4550300/5
5 | W electrode (WY-20) | 20 | 132 | 4549148
6 | Filler wire(filament) | 1 | 231 | 4549148
7 | Sachet polyeth 220x310 | 5 | 60 | 4549148