## Drawings
LIC Production - Drawing list
Drawing information | [5 empty] | Production issues | [8 empty] | Orders
Drawing number | Remark |  | Vers. | See | Q. Ass. | Qty. | Spare | Pro. Qty. | Total | Material | Manuf. | Assembly | Remarks | Order by | Material | Manufact | All
LHCBLM__0087 | on work | ELECTRICAL CONNECTORS - LIC ASSEMBLY | 1st | See |  | 300 | 15 | 0 | 315 |  |  | Protvino | drawing to upgrade | JMM
LHCBLM__0037/1 |  | ELECTRICAL CONNECTION - EXTERNAL PLATE | C | See | 1 | 300 | 15 | 0 | 315 | CERN | External | Protvino |  | JMM |  |  | 4551965
LHCBLM__0037/2 |  | ELECTRICAL CONNECTION - EXTERNAL PLATE | C | See | 1 | 300 | 15 | 0 | 315 | CERN | External | Protvino |  | JMM |  |  | 4563280
LHCBLM__0038 |  | ELECTRICAL CONNECTION - EXTERNAL TUBE | B | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM | 4550566
LHCBLM__0056 |  | SCREEN FOR SEM COVER - | 1st | See | 1 | 300 | 15 | 0 | 315 | External | External |  |  | JMM |  |  | 4563280
LHCBLM__0084 | on work | LIC ASSEMBLY - ALUMINIUM ELECTRODES | 1st | See | 1 | 300 | 15 | 0 | 315 |  |  | Protvino |  | JMM
LHCBLM__0004 | TYPE 1 | MULTIPLE ELECTRODE BLM - ELECTRODE | B | See | 3 | 900 | 45 | 1000 | 0 | [5 empty] | none | none | none
LHCBLM__0007 | TYPE E | MULTIPLE ELECTRODE BLM - ELECTRODE SPACERS | D | See | 6 | 1800 | 90 | 0 | 1890 | CERN | External |  |  | JMM |  |  | 4551963
LHCBLM__0007 | TYPE A | MULTIPLE ELECTRODE BLM - ELECTRODE SPACERS | D | See | 3 | 900 | 45 | 1000 | 0 | [5 empty] | none | none | none
LHCBLM__0081 |  | LIC ELECTRODES - BOTTOM COVER | 1st | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM | 4550566 | 4551965
LHCBLM__0052 |  | SEM-TITANIUM ELECTRODES - ELECTRICAL CONNECTION | 1st | See | 2 | 600 | 30 | 0 | 630 | External | External |  |  | JMM |  |  | 4563242
LHCBLM__0040 | TYPE D | MULTIPLE ELECTRODE BLM - EXTERNAL TUBE | B | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM | 4550566
LHCBLM__0086 | on work | LIC ALUMINIUM ELECTRODES - COVER ASSEMBLY | A | See | 1 | 300 | 15 | 0 | 315 |  |  | Protvino | drawing to upgrade | JMM
LHCBLM__0082 |  | LIC ELECTRODES - COVER | 1st | See | 1 | 300 | 15 | 0 | 315 | CERN | External |  |  | JMM | 4550566 | 4553320
LHCBLM__0035 |  | WELDED SPACER - | A | See | 3 | 900 | 45 | 1220 | 0 | [5 empty] | none | none | none
LHCBLM__0088 |  | MANCHON ISOLANT - | 1st | See | 4 | 1200 | 60 | 0 | 1260 | External | External |  | Manufacture according to drawing LHCBLM__0055 | JMM |  |  | 4483010
LHCBLM__0083 |  | ELECTRICAL SHIELDING - FOR FEEDTHROUGH | 1st | See | 2 | 600 | 30 | 0 | 630 | External | External |  |  | JMM | 4551043 | 4551965
LHCBLM__0085 |  | HOLDER ON COVER - | 1st | See | 1 | 300 | 15 | 0 | 315 | External | External |  |  | JMM |  |  | 4563280
Note on G5: jherranz: Is the quantity requested in the assembly to which this drawing belongs
Note on I5: jherranz: Quantity of spare chambers to build
Note on J5: jherranz: Quantity availabe in Protvino
Note on K5: jherranz: Quantity of units to produce = Q. Ass. x (Qty + Spare)
Note on L5: jherranz: Where is foreseen to order the material, i.e: CERN, external supplier…
Note on M5: jherranz: Where is foreseen to manufacture the product i.e: CERN, supplier name…
Note on N5: jherranz: Where is foreseen to assembly (welding, bolted or other) the parts i.e: CERN, external supplier…

## Commercial
LIC Production - Commercial part list
Commercial part information | [8 empty] | Ordering information
Qty. | Descrition | Pos. | Material | Dimension | Norm. | Remarks | Ref. CERN | Assembly | Ass. Qty. | Pro. Qty. | T. Qty. | Remarks | Order by | Status
3 | Round tube dia. 7/4 | 4 | AW6082 | L=60.5 |  |  |  | LHBLM__0087 | 315 | 0 | 945 | need manufacturing: cutting | JMM
3 | Threaded rod M4x85 | 5 | SS A2 | M4x85 |  |  |  | LHBLM__0087 | 315 | 0 | 945 | need manufacturing: cutting | JMM
3 | Washer M4 | 6 | SS A2 | M4 |  |  |  | LHBLM__0087 | 315 | 0 | 945 |  | SG
6 | Nut M4 | 7 | SS A2 | M4 |  |  |  | LHBLM__0087 | 315 | 1800 | 90 |  | SG
1 | Hex. Hd point screw M3x5 | 8 | SS A2 | M3x5 |  |  |  | LHBLM__0087 | 315 | 0 | 315 |  | SG
1 | Signal connector | 9 |  |  |  |  | 09.46.11.360.4 | LHBLM__0087 | 315 | 0 | 315 |  | SG
2 | H.V. connector | 10 |  |  |  |  | 09.41.25.160.9 | LHBLM__0087 | 315 | 0 | 630 |  | SG
1 | Capacitor | 11 |  |  |  | WIMA MKP 10-0.47microF/2000V |  | LHBLM__0087 | 315 | 100 | 215 |  | SG
1 | Resistor | 12 |  |  |  | EBG SOX 20-10MOhm/15kV |  | LHBLM__0087 | 315 | 315 | 0 |  | SG
1 | TERM.CAB.S.SINGLE | 14 |  |  |  | D 4,2X23,5mm | 04.76.26.448.1 | LHBLM__0087 | 315 | 0 | 315 |  | SG
1 | BRASS SOLDER.CAB.T. | 15 |  |  |  | BNC 50 OHM | 09.46.11.520.6 | LHBLM__0087 | 315 | 0 | 315 |  | SG
18 | Washer dia. 8/4.2 thk 0.2 | 8 | 1.4310 | 8/4.2 thk 0.2 | BN838 | Bossard BN838 |  | LHBLM__0084 | 315 | 4300 | 1370 |  | SG
6 | Nut M4 | 9 | SS A4 | M4 |  |  |  | LHBLM__0084 | 315 | 0 | 1890 |  | SG
4 | Hdless screw M3x3 | 10 | SS A4 | M3x3 | BN618 | Bossard BN618 |  | LHBLM__0084 | 315 | 2000 | 0 |  | SG
2 | FEEDTHROUGH | 2 |  |  |  | CERAMASEAL 3887-12-W |  | LHBLM__0086 | 390 | 0 | 780 |  | SG | 4553303
1 | Round tube dia. 10 x 8 mm | 6 | COPPER | L=120 mm |  |  | 39.71.20.008.8 | LHBLM__0086 | 315 | 0 | 315 | need manufacturing: cutting, annealing, UHV cleaning and packing | JMM
Note on B5: jherranz: Is the quantity requested in the assembly to which this part belongs
Note on D5: jherranz: Is the possition in the assembly drawing for this part
Note on K5: jherranz: Quantity of assembies to product
Note on L5: jherranz: Quantity availabe in Protvino
Note on M5: jherranz: Total number of parts to order
Note on L9: Viatcheslav Grishin:no vaccuum part
Note on L10: Viatcheslav Grishin: we have M3x4
Note on L18: Viatcheslav Grishin: it's vaccuum part

## Orders
LIC Production - orders list
Number | Type | Short Description | Creator | Created | Total | Description
4563280 | JOB | (J3000786) LIC SHEET METAL WORKING | Laurence FOL | 27.01.2011 | 5708 | LIC SHEET METAL WORKING. Fabrication de : - 315 "Screen for SEM Cover" en inox 304L -> LHCBLM__0056.4 - 315 "External plate pos.2" en inox 304L -> LHCBLM__0037.3.C - 315 "Holder on cover" en inox 304L -> LHCBLM__0085.4
4563242 | JOB | (J3000785) ELECTRICAL CONNECTION LIC | Laurence FOL | 27.01.2011 | 1222 | ELECTRICAL CONNECTION LIC. Fabrication de 630 "Electrical connection" en inox 316L suivant plan LHC BLM__0052.3
4553320 | JOB | (J3000674) COVERS FOR LIC PROJECT | Laurence FOL | 17.01.2011 | 4278 | COVERS FOR LIC PROJECT. Fabrication de 315 "LIC electrodes cover" en inox 316L suivant plan LHCBLM__0082.3
4551965 | JOB | (J3000664) PLATES AND ITEMS LIC PROJECT | Laurence FOL | 14.01.2011 | 6012 | PLATES AND ITEMS LIC PROJECT. Manufacture of : - 315 "bottom cover" -> LHCBLM__0081.4 - 315 "external plate" -> LHCBLM__0037.3 (pos. 1) - 630 "electrical shielding for feedthrough -> LHCBLM__0083.4
4551963 | JOB | (J3000667) ELECTRODES SPACERS LIC | Laurence FOL | 14.01.2011 | 2956 | ELECTRODES SPACERS LIC. Fabrication de : - 1890 "Multiple electrode BLM, electrode spacers" en inox 316L suivant plan LHCBLM__0007.4.D
4483010 | JOB | (J1503021) MANCHONS ISOLANTS | Laurence FOL | 15.10.2010 | 56991 | MANCHONS ISOLANTS. Fabrication avec matiere de 1500 manchons isolants suivant plan 85657 QB AA
4468205 | JOB | (J3000016) LIC (little ionisation chamber) | Christiane PERQUIN | 29.09.2010 | 8160 | LIC (little ionisation chamber). Modifications des plans du SEM (beam lost monitor)pour fabrication du LIC (little ionisation chamber).
4551869 | MAG | (QUAL4551869) BLM-LIC assembly | Viatcheslav GRISHIN | 14.01.2011 | 22.39 | 200-(Flat washers, without chamfer, for screws with cylindrical head), 100-(Hexagon socket set screws, with cone point), 100-(Hexagon nuts ~0,8d)
4550356 | MAG | (QUAL4550356) BLM-LIC assembly | Viatcheslav GRISHIN | 13.01.2011 | 23.47 | 100-(Hexagon socket set screws, with cone point), 53-(Disc springs, works standard)
4551043 | MAG | (BAAN4551043) LIC ITEMS | Jean-Marc MALZACKER | 13.01.2011 | 594 | TUBE INOX 316L D.18 X 15 RE
4550566 | MAG | (BAAN4550566) LIC ITEMS | Jean-Marc MALZACKER | 13.01.2011 | 4659.8 | DISQUES INOX 316 L, TUBE INOX 316L D. 6 X 4 RE, ROUND TU. 304L WELD. 88,9x2,0, ROUND TU. 304L WELD. 88,9x2,0
4550300 | MAG | (BAAN4550300) BLM-LIC assembly | Viatcheslav GRISHIN | 13.01.2011 | 8842.5 | 315-CABLE PLUG /CENTR BNC 50 OHM, 630-CEN.CHASS.PLUG POLYPE.SHV 5kV, 4-TERM.CAB.S.SINGLE D 4,2X23,5mm ( 4 SA = 400 PC ), 16-BRASS SOLDER.CAB.T. BNC 50 OHM ( 16 SA = 320 PC ), 2-RUB.KAPTON AUTOCOL. 0,07X25mm
4549148 | MAG | (BAAN4549148) "TIG" welding and packing bags | Viatcheslav GRISHIN | 12.01.2011 | 423 | 20-ELECT.TUNGS. SOUD.TIG D 3,20, 1-Ø1, 6mm TIG WELD. ROD FOR STAINL.ST ( 1 PQ = 5 KG ), 5-SACHET POLYETHYLENE 220X310 MM ( 5 PQ = 500 PC )
4548629 | MAG | (BAAN4548629) Insert Olifes | Viatcheslav GRISHIN | 11.01.2011 | 750 | 300-FERRULE UNION/FRONT FE. SS 10, 300-FERRULE UNION/FRONT FE. SS 10
4550385 | DAI | BLM-LIC cleaning_Detergent | Viatcheslav GRISHIN | 13.01.2011 | 620 | 40-NGL detergent are used for cleaning of the Beam Loss Monitor-LIC
4553303 | DAI | BLM-LIC feed throughs | Viatcheslav GRISHIN | 17.01.2011 | 20208.45 | 750-feed throughs

## Protvino
# |  | Qty. | Price(CHF) | EDH Number of request
1 | Detergent NGL 17.40SP ALU III | 40 kg (2x20) | 630 | 4550385
2 | Insert Front Olifes | 300 | 390 | 4548629
3 | Insert Rear Olifes | 300 | 360 | 4548629
4 | Kapton tape | 2 | 120 | 4550300/5
5 | W electrode (WY-20) | 20 | 132 | 4549148
6 | Filler wire(filament) | 1 | 231 | 4549148
7 | Sachet polyeth 220x310 | 5 | 60 | 4549148