## Sheet1
2005-11-19 | [30 empty] | Beam Loss LHC installation planning
SECTOR | [5 empty] | 8 - 1 | [6 empty] | 7 - 8 | [5 empty] | 4 - 5 | [6 empty] | 3 - 4 | [6 empty] | 5 - 6 | [6 empty] | 6 - 7 | [6 empty] | 2 - 3 | [6 empty] | 1 - 2 | [5 empty] | BL section | 1 | Surface installation
[60 empty] | Cern | 1 | 1 week / point 2 persons
| Oct | [58 empty] | FSU (Russian) | 1 | 8 weeks / LHC 16 man weeks
Nov
| Dec | [58 empty] | BL section | 2 | Check location |  |  |  | 3756
2006 | Jan | [58 empty] | Cern | 1 | 1 week / sector 70 quad, 2 persons
[60 empty] | FSU (Russian) | 1 | 8 weeks / LHC 16 man weeks
Feb
[60 empty] | EXT | 3 | Fixing of support arc crate BYPLM |  |  |  | 360
| Mar | 2 | 2 | 2 | 2 | 2 | 2 | 1 | [53 empty] | Installation crate BYPLM + cover |  |  |  | 360
[12 empty] | Coll | [49 empty] | 1/2 day 8 support+ crate 2 persons
| Apr | [60 empty] | 70 quad 70 supp+ crate 9 days 2 weeks
|  | 1 | 1 | 2 | 4 | 4 | 2 | 4
| May | [58 empty] | External EL | 4 | Fiber patch pannel installation
[9 empty] | 1 | 1 | 2 | 5 | 5 | 2 | 5 | 1 | 1 | 2 | 4 | 4 | 2 | 4 | [37 empty] | persons | 2 | 1/2 day/ 4 quadrupole 32 fibers 2 persons
| Jun | [60 empty] | 70 quad 560 fibers 8.75 days 2 weeks
[33 empty] | Dump | [28 empty] | 16 weeks/LHC 32 man weeks
Jul
[60 empty] | BL section | 5 | Quad supports chambers installation |  |  |  | 3036
| Aug | [21 empty] | 1 | 1 | 2 | 4 | 4 | 2 | 4 | [10 empty] | Dump | [20 empty] | 6 | Straight section supports installation |  |  |  | 446
[40 empty] | Coll | [20 empty] | 7 | Chambers + SEM installation |  |  |  | 3756
| Sep | [28 empty] | 1 | 1 | 2 | 5 | 5 | 2 | 5 | [23 empty] | FSU (Russian) | 1 | 1/2 day/ 2 quadrupole 16 chambers 2 persons
[37 empty] | 1 | 1 | 2 | 5 | 5 | 2 | 5 | [16 empty] | FSU (Russian) | 1 | 70 quad 420 chambres 17.5 days 4 weeks
| Oct | [60 empty] | 35 weeks/LHC 70 man weeks
| Nov | [58 empty] | BL section | 8 | Quad Cupper cables installation BNC + BNCHT |  |  |  | 13156
|  | BEAM | [6 empty] | BEAM | [51 empty] | 9 | Stright Sesct. Cupper cables instal. BNC + BNCHT |  |  |  | 2612
| Dec | [42 empty] | 1 | 1 | 2 | 4 | 4 | 2 | 4 | 1 | 1 | 2 | 4 | 4 | 2 | 4 |  |  |  | 10 | Cupper cables connection on the chambers and crate
[60 empty] | Cern | 1 | 1/2 day/ 2 quadrupole 24 cables 2 persons
2007 | Jan | [58 empty] | FSU (Russian) | 1 | 70 quad 1680 cables 17.5 days 4 weeks
35 weeks/LHC 70 man weeks
Feb
| Mar | [58 empty] | BL section | 11 | High Voltage cables test (CBH50)
| Apr | [59 empty] | 12 | Analog cables test (CB50)
| May | [59 empty] | 13 | CFC installation and test
| Jun | [59 empty] | 14 | Optical fibres installation
| Jul | [57 empty] | Man |  | 15 | Test from surface
| Aug | BEAM | [13 empty] | BEAM | [6 empty] | BEAM | [6 empty] | BEAM | [6 empty] | BEAM | [6 empty] | BEAM | [6 empty] | BEAM | [6 empty] | weeks | weeks | Cern | 1 | 1/2 day 2 CFC, Alim, 4 otical cords, 1 person
70 quad 17.5 days 4 weeks
|  | W | P |  | P/W |  |  |  | W | P |  | P/W | [49 empty] | 35 weeks/LHC 35 man weeks
Works |  | 1 | 2 |  | 2 |  |  |  | 1 | 2 |  | 2 |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 16 | 32 | Transports
Works |  | 1 | 2 |  | 2 |  |  |  | 1 | 2 |  | 2 |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 16 | 32 | Voitures
Works | Ext | 2 | 2 | [5 empty] | 2 | 2 | [5 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 | [6 empty] | 20 | 40
Works |  | 4 | 2 |  | 8 |  |  |  | 5 | 2 |  | 10 |  |  |  | 4 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 5 | [6 empty] | 4 | [6 empty] | 4 | [6 empty] | 57 | 228
Works |  | 4 | 2 |  | 8 |  |  |  | 5 | 2 |  | 10 |  |  |  | 4 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 5 | [6 empty] | 4 | [6 empty] | 4 | [6 empty] | 57 | 114 | BL section | 1
Works | Ext | 2 | 2 | [5 empty] | 2 | 2 | [5 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 | [6 empty] | 20 | 40 | Cern | 1 | A/B
Works |  | 4 | 1 |  | 4 |  |  |  | 5 | 1 |  | 5 |  |  |  | 4 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 5 | [6 empty] | 4 | [6 empty] | 4 | [6 empty] | 46 | 46 | FSU (Russian) | 1 | A
[5 empty] | 24 | [6 empty] | 29
[60 empty] | BL section | 2
Works | BDI / BL |  |  | Works 1 | [8 empty] | Works 2 | [5 empty] | Works 5-7 | [6 empty] | Works 8-10 | [6 empty] | Works 11-15 | [25 empty] | 452 | Cern | 1 | A/B | CERN | A | Franco | Ewald
Works | EXT |  |  | Works 3 | [8 empty] | Works 4 | [45 empty] | 80 | FSU (Russian) | 1 | A |  | B | Ion | Raymond
[63 empty] | FSU (Russian) | A | X1 | Y1
1 sector | 6 weeks |  | 5 mans |  |  |  | 30 weeks/man | [6 empty] | works needs 24 weeks/man | [45 empty] | BL section | 5 |  | FSU (Russian) | B | X2 | Y2
[61 empty] | 6 |  | FSU (Russian) | C | X3 | Y3
7
[60 empty] | FSU (Russian) | 1 | B
[60 empty] | FSU (Russian) | 1 | C
[60 empty] | BL section | 8
9
10
[60 empty] | Cern | 1 | A/B
[60 empty] | FSU (Russian) | 1 | A
[60 empty] | BL section | 11
12
13
14
15
[60 empty] | Cern | 1 | A/B