## BLM chambers
Sub-System | Delivery by | DAI order # | per chamber | ordered by? | received | location | checked by? | shipped to Protvino 2005 | unit price | comments
LEGENDE: blue background means: to be cleaned for UHV
LEGENDE: green background means: not to be cleaned for UHV. Is there any cleaning necessary?
LHCBLM__0001
tube inox 304L 483x88.9x2.0 LHCBLM__0040 | Santrade, CH | 39.39.05.088.2 | 1 | CV | 4133 | pool | SG | 1394 | 12.00 | 59- still at CERN
Ceramics LHCBLM__0041 upper CNGS | FRIATEC (F) | ?? | 1 | BD/JMM | 50 | pool
Ceramics LHCBLM__0042 lower CNGS | FRIATEC (F) | ?? | 1 | BD/JMM | 50 | pool
Al electrodes production LHCBLM__0004 0.5X82 | Dutreive (F) | partially open, CA 1391681 | 61 | EBH | 25000 ? |  |  | 0
electrode spacer LHCBLM__0007 type A | Flueckiger (CH) | CA1390364 +?? | 183 | EBH/JMM | 23873 | pool, EBH | SG, EBH | 1830
electrode spacer LHCBLM__0007 type C | Flueckiger (CH) | CA1390364 +?? | 6 | EBH/JMM | 398 | pool, EBH | SG, EBH | 60
bottom cover disk LHCBLM__0006 | RPM (I) | CA1390102+CA1392889 | 1 | EBH/JMM | 598 |  |  | 50
bottom cover spacer LHCBLM__0006 | Dedecker (B) | CA1390111 | 1 | EBH/JMM | 3800 |  |  | 10 | 0.03
tighteners M4 LHCBLM__0016
type B Var 1 (incl. LHCBLM__0013) | JCM (F) |  | 2 | EBH/JMM |  |  |  | 0
type A Var 1 (incl. welded washer) | JCM (F) |  | 4 | EBH/JMM |  |  |  | 4
heads
50 IC heads (CNGS) | DG-technology (I) | CA1390214 | 1 | EBH/JMM | 50 | pool
small items
compressing spring 1.4310 ferroflex | Ferroflex | VD-180M-14 | 1 | CV | 3850 | pool |  | 0
alumina tube D15/10, L=25mm | CERN | 19.63.30.128.9 | 2 | EBH | 8322 | SG/pool | SG | 0 | 2
slotted screw M3x4, A2-ISO 1580 | Bossard BN652 | 47.62.72.996.0 | 2 | CV | 8400 | pool |  | 0 | 5
screw without head 6pc bt point.in.3x3 | Bossard BN618 | 47.62.72.995.0 | 4 | CV | 15400 | pool |  | 0
spring washer D8/4.2-0.2, 1.4310 | Bossard BN838 | 47.62.72.996.8 | 18 | CV | 2200 |  |  | 0
stop nut M4-A2 DIN980V | Bossard BN5242 | 47.62.72.998.2 | 6 | CV | 8900 |  |  | 0
label (self adhesive) for chambers |  |  | 1 | ?? |  |  |  | 0
electrical connectors ass LHCBLM__0036
tube inox 304L 105x88.9x2 LHCBLM__0038 v.AB |  | 39.39.05.088.2 | 1 | CV | 4271 | pool | SG | 1500 |  | 4 still at CERN
external plate LHCBLM__0037, manufacture | Solpey (E) | CA1390916 | 1 | EBH/JJM | 50 |  |  | 10
st steel sheet LHCBLM__0037, manufacture | Cherokee (B) | CA1391433 | 1 | EBH/JJM | 50 |  |  | 10
tube AlMgSi hard 4*7 L=60 |  | 39.64.05.012.1 | 3 | CV |  |  |  | 0
in.steel.thr.rods A4 316 M4 L=85 |  | 47.38.77.040.8 | 3 | CV |  |  |  | 0
hex.nuts inox A4 316 0.8D M4 |  | 47.43.77.040.1-? | 6 | CV | 25000 | pool |  | 0
washer contact medium M4 |  | 47.78.09.004.1 | 3 | CV |  |  |  | 0
head.hex.point.scr. M3x5, inox |  | 47.62.96.101.1? | 1 | CV | 4200 | pool |  | 0
BNC HT Polypenco SHV 5KV | CERN | 09.41.25.160.9 | 2 | GF | 8272 |  |  | 8200
BNC 50ohm, teflon | CERN | 09.46.11.360.4 | 1 | GF | 4136 |  |  | 4100
soldering lug, M4 | CERN | 04.76.26.448.1 | 1 | GF | 4100 |  |  | 1800
soldering lug, BNC | CERN | 09.46.11.520.6 | 1 | GF | 4200 |  |  | 4100
wires (L=100, 1.5mm2) | CERN | 04.01.61.900.1 | 0.15 | GF | 800 |  |  | 800
tinned cupper wires, without insulation, D=0.91mm |  | 04.01.02.091.5 | 0.1 | GF | 280 |  |  | 140
Resistor 10Mohm ,1W |  |  | 1 | GF | 4250 |  |  | 3950
Capacitor (0.47uF, 2000V) |  |  | 1 | GF | 4273 |  |  | 4000
Total | [7 empty] | 31958
Note on A29: grishinv: rondelle a plateau inox A2 M4
Note on A27: grishinv: vis tete aplatie in.A2 M3x4
Note on A28: grishinv: vis sans tete 6 p.cr.M3x3
Note on A30: grishinv: ecrou hexagonal in.autofr.M4
Note on A37: grishinv: tige filetee in.4.A4 M 4x85 47.62.82.908.1
Note on A40: grishinv: vis sans tete 6 p.cr.in N3x5; 47.62.72.995.5
Note on I41: dehning: expec. 31/11 grishinv: Lorry#2,Dec05
Note on I42: dehning: expec. 31.11 grishinv: Lorry#2,Dec05
Note on I43: grishinv: Lorry#2,Dec05;2300 to send
Note on I44: grishinv: Lorry#2,Dec05
Note on I45: grishinv: Lorry#2,Dec05
Note on I46: grishinv: Lorry#2,Dec05;140 to send
Note on I47: grishinv: Lorry#2,Dec05; 150 to send
Note on I48: grishinv: Lorry#2,Dec05; 100 to send
Note on F17: grishinv: 90+ 7/12:300+208
Note on F23: grishinv: 10+40(7/12)
Note on F18: grishinv: 50 +3750?
Note on F7: grishinv: + 2678 14/12/05
Note on F33: grishinv: + 2767 14/12/05
Note on F14: eholzer: 14600 on 6.1.2006 to be checked