## BLM chambers
Sub-System | Delivery by | DAI order # | per chamber | number IC | spare IC | number SEM | spare SEM | total needed quantity | total needed quantity Protvino | ordered | ordered by? | ordered - needed | order-needed to Protvino | received | received in Protvino (11.05):no Sh7,8 | received-needed | location | checked by? | latest delivery schedule | sh. to Protvino 2006 by hand | shipped to Protvino 2006 | shipped to Protvino 2005 | shipped to Protvino ALL | to be shippied Protvino06 | Exist in LZ For Shipping#8 | Exist in LZ - to be shipped to Protvino | Exist in LZ after LS/IC | shipped to Protvino / IC | shipped to Italy/IC | Head's:UK+IT+Pr+LZ | Needed:Exist - 4020 | Real in Protvino | Urgent
LEGENDE: blue background means entered or checked by EBH, grey letters means: obsolete, deleted by EBH, grey backround means: cannot be checked by EBH
In PROTVINO | [8 empty] | 3749+19
IC->4020 incl 5%spare |  |  |  | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | [18 empty] | 4020
LHCBLM__0001 and LHCBLM__0009
tube inox 304L 483x88.9x2.0 LHCBLM__0040, IC | Santrade, CH | 39.39.05.088.2 | 1 | 4050 | 20.25 |  |  | 4070.25 | 4020 | 3800 | CV | -270.25 | -270 | 4133 | 3773 | 62.75 | pool | SG |  |  | 2379 | 1394 | 3773 | -247 | 0 | -247 |  | 3773
tube inox 304L 109x88.9x2.0 LHCBLM__0040, SEM |  | 39.39.05.088.2 | 1 |  |  | 315 | 3.15 | 318.15 |  | 310 | CV | -8.15 |  | 118 |  | -200.15 | pool | Slava
tube inox 304L 105x88.9x2 LHCBLM__0038 v.AB | el. box | 39.39.05.088.2 | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4110 | CV | -278.4 | 40 | 4271 | 3818 | -117.4 | pool | SG |  |  | 2318 | 1500 | 3818 | -202 | 0 | -202 |  | 3818
Ceramics LHCBLM__0005 v.AC, IC |  |  | 2 | 4000 | 20 |  |  | 8040 | 8040 | 7110 | EBH | -930 | -1030 | 5902 | 2019 | -2138 |  | Slava |  | 10 | 2029 | 0 | 3948 | -4092 | 1378 | -2714 | 689 | 2663 |  |  |  | 3000
Ceramics LHCBLM__0005 v.AC, SEM |  | open | 1 |  |  | 315 | 3.15 | 318.15 |  |  |  | -318.15 |  |  |  | -318.15
Al electrodes production LHCBLM__0004 0.5X82, IC | Dutreive (F) | CA 1391681 | 61 | 4050 | 20.25 |  |  | 248285.25 | 245220 | 208020 | EBH | -40901.55 | -40250 | 207126 | 207000 | -41159.25 |  | Slava | Dec 05 | 126 | 207000 | 0 | 207126 | -38094 | 0 | -38094 | 0 | 3395.5082 |  |  |  | 3396
Al electrodes production LHCBLM__0004 0.5X82, SEM | Dutreive (F) | open | 2 |  |  | 315 | 3.15 | 636.3 |  | 0 | [5 empty] | -636.3 |  |  | Dec 05
electrode spacer LHCBLM__0007 type A | Flueckiger (CH) | CA1390364 +?? | 183 | 4050 | 81 |  |  | 758921.4 | 735660 | 698300 | EBH/JMM | -60621.4 | -46510 | 396319 | 169859 | -362602.4 | pool | SG, EBH | ?? | 390 | 168029 | 1830 | 290084 | -445576 | 57160 | -388416 | 312.3497 | 1897.5082 |  |  |  | 1895
electrode spacer LHCBLM__0007 type A, SEM | Flueckiger (CH) | CA1390364 +?? | 9 |  |  | 315 | 12.6 | [8 empty] | ? |  |  | ??
electrode spacer LHCBLM__0007 type B, SEM | Flueckiger (CH) | CA1390364 +?? | 3 |  |  | 315 | 12.6 | 982.8 |  | 930 | EBH/JMM | -52.8 |  | 948 |  | -34.8 |  |  | ??
electrode spacer LHCBLM__0007 type C | Flueckiger (CH) | CA1390364 +?? | 6 | 4050 | 81 |  |  | 24786 | 24120 | 22800 | EBH/JMM | -1986 | -1620 | 10625 | 10604 | -14161 | pool | SG, EBH | ?? | 15 | 10550 | 60 | 10625 | -13495 | 0 | -13495 | 0 | 1770.8333 |  |  |  | 1767
bottom cover disk LHCBLM__0006 | RPM (I) | CA1390102+CA1392889 | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4110 | EBH/JMM | -278.4 | 40 | 4432 | 4429 | 43.6 |  | Slava | Dec 05 | 2 | 4380 | 50 | 4432 | 412 |  |  |  | 4432
bottom cover spacer LHCBLM__0006 | Dedecker (B) | CA1390111 | 1 | 4050 | 20.25 |  |  | 4070.25 | 4020 | 3800 | EBH/JMM | -270.25 | -270 | 3592 | 3590 | -478.25 |  | Slava | Nov 05 | 2 | 3580 | 10 | 3592 | -428 | 0 | -428 | 0 | 3592 |  |  |  | 3590
tighteners M4 LHCBLM__0016
type B Var 1 (incl. LHCBLM__0013) | JCM (F) |  | 2 | 4050 | 20.25 |  |  | 8140.5 | 8040 | 7700 | EBH/JMM | -440.5 | -440 | 9909 | 5537 | -2818 |  | Slava |  | 4 | 2503 | 0 | 7747 | -293 |  | -293 | 0 | 3873.5 |  |  |  | 2611
type A Var 1 (incl. welded washer) | JCM (F) |  | 4 | 4050 | 20.25 |  |  | 16281 | 16080 | 15400 | EBH/JMM | -881 | -880 | 20228 | 2503 | -2300 |  | Slava |  | 8 | 5537 | 4 | 15233 | -847 |  | -847 | 0 | 3808.25 |  |  |  | 3445
heads
50 IC heads (CNGS) | DG-technology (I) | CA1390214 | 1 | 50 |  |  |  | 50 |  | 50 | EBH/JMM | 0 |  | 50 |  | 0 | pool |  | ?? |  |  | 5 | 5
heads (Alca/Italy) | [8 empty] | ? | [11 empty] | 0
500 IC heads (Aerovac) | AeroVac (GB) |  | 1 | 500 |  |  |  | 500 | ? | 500 | EBH/JMM | 0 |  | 342 |  | -158 |  | Slava |  |  | 42 |  | 292 |  | 50 |  | 50 | 347
small items
compressing spring 1.4310 ferroflex | Ferroflex | VD-180M-14 | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 3850 | CV | -538.4 | -220 | 3784 | 3780 | -604.4 | pool | Slava | Dec 05 | 4 | 3780 | 0 | 3784 | -236 |  |  |  | 3784
alumina tube D15/10, L=25mm | CERN | 19.63.30.128.9 | 2 | 4050 | 20.25 | 315 | 3.15 | 8776.8 | 8040 | 8220 | EBH | -556.8 | 80 | 8368 | 4563 | -408.8 | SG | SG |  | 119 | 4684 | 0 | 4803 | -3237 | 3565 | 328 | 1782.5 | 4184
slotted screw M3x4, A2-ISO 1580 | Bossard BN652 | 47.62.72.996.0 | 2 | 4050 | 20.25 | 315 | 3.15 | 8776.8 | 8040 | 8400 | CV | -376.8 | 260 | 8305 | 8300 | -471.8 | pool | Slava | Dec 05 | 5 | 8300 | 0 | 8305 | 265 |  |  |  | 4152.5
screw without head 6pc bt point.in.3x3 | Bossard BN618 | 47.62.72.995.0 | 4 | 4050 | 20.25 | 315 | 3.15 | 17553.6 | 16080 | 16600 | CV | -953.6 | 320 | 16406 | 16400 | -1147.6 | pool | Slava | Jan 06 | 6 | 16400 | 0 | 16406 | 326 |  |  |  | 4101.5
spring washer D8/4.2-0.2, 1.4310 | Bossard BN838 | 47.62.72.996.8 | 18 | 4050 | 20.25 | 315 | 3.15 | 78991.2 | 72360 | 75000 | CV | -3991.2 | 1740 | 73140 | 85500 | -5851.2 |  |  | Dec 05 | 40 | 73100 | 0 | 73140 | 780 |  |  |  | 4063.3333
nut M4-A4 ISO4032 |  | ?? | 12 | 4050 | 20.25 | 315 | 3.15 | 52660.8 | 48240 | 45600 | CV | -7060.8 |  | 45640 | 45600 | -7020.8 |  | Slava | Feb 06 | 40 | 45600 | 0 | 45640 | -2600 |  |  |  | 3803.3333
cover assembly LHCBLM__0002 | [25 empty] | ?? |  | I
cover plate LHCBLM__0003, 316L | Dedecker (B) | CL1932975 +?? | 1 | 3500 | 17.5 | 315 | 3.15 | 3835.65 | 4020 | 3610 | EBH/JJM | -225.65 | -460 | 1904 | 800 | -1931.65 |  | EBH | ?? | 2 | 2000 | 2 | 2004 |  | 929 | -1775 | 929 | 3204 | 515 | 3948 | -72
feed throughs | CERAMTEC (US) | 1889051/1937566 | 2 | 4050 | 20.25 | 315 | 3.15 | 8776.8 | 8040 | 7420 | EBH | -1356.8 | -1720 | 8482 | 1600 | -294.8 | pool | CC |  |  | 4000 | 4 | 4004 |  | 1076 | -2164 | 538 | 3202 | 650 | 3487 | -533
copper tube 10 x 8, L=120mm | CERN, MR 1887862 | 39.71.20.008.8 | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4110 | CV | -278.4 | -460 | 5375 | 810 | 986.6 |  | CV |  |  | 2010 | 2 | 2012 |  | 1265 | -1447 | 1265 | 3212 | 515 | 4292 | 272
cover spacer LHCBLM__0008 type A, 316L, IC | Solpey (E) | CA1390217 | 2 | 4050 | 20.25 |  |  | 8140.5 | 8040 | 6500 | EBH/JJM | -1640.5 | -2640 | 7395 | 1600 | -745.5 | pool | RT |  |  | 4000 | 4 | 4004 |  | 935 | -2234.5 | 467.5 | 3202 | 650 | 3416 | -604
cover spacer LHCBLM__0008 type B, 316L, SEM | Solpey (E) | CA1390217 | 2 |  |  | 315 | 3.15 | 636.3 |  | 620 | EBH/JJM | -16.3 |  | 605 |  | -31.3 | pool | RT
protection tube LHCBLM__0010, 316L | Solpey (E) | CA1390217 | 2 | 4050 | 20.25 | 315 | 3.15 | 8776.8 | 8040 | 7120 | EBH/JJM | -1656.8 | -2020 | 13759 | 2100 | 4982.2 | pool | RT |  |  | 4000 | 4 | 4004 |  | 595 | -2404.5 | 297.5 | 3202 | 650 | 3246 | -774
welded spacer LHCBLM__0035, 304L | Solpey (E) | CA1390217 | 3 | 4050 | 20.25 | 315 | 3.15 | 13165.2 | 12060 | 10680 | EBH/JJM | -2485.2 | -3030 | 10658 | 2400 | -2507.2 | pool | RT |  |  | 5700 | 6 | 5706 |  | 0 | -2602 | 0 | 3102 | 515 | 2714 | -1306 | 2714
TIG welding job
TIG welding of heads (IHEP or company) |  |  | 1 | 3500 | 17.5 | 315 | 3.15 | 3835.65 |  | 0 | EBH/JMM | -3835.65 |  |  |  | -3835.65
electrical connectors ass LHCBLM__0036
external plate LHCBLM__0037, manufacture | Solpey (E) | CA1390916 | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4110 | EBH/JJM | -278.4 | 40 | 4090 | 4089 | -298.4 |  | Slava | ?? |  | 4080 | 10 | 4090 | 70 |  |  |  | 4090
st steel sheet LHCBLM__0037, manufacture | Cherokee (B) | CA1391433 | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4160 | EBH/JJM | -228.4 | 90 | 4092 | 4080 | -296.4 |  | Slava | ?? | 2 | 4080 | 10 | 4092 | 72 |  |  |  | 4092
tube AlMgSi hard 4*7 L=60 |  | 39.64.05.012.1 | 3 | 4050 | 20.25 | 315 | 3.15 | 13165.2 | 12060 | 780 MT | CV |  | #VALUE! | 12570 | 19450 | -595.2 |  | Slava | 27.10+2wks | 156 | 10450 | 0 | 10606 | -1454 | 982 | -472 | 327.3333 | 3535.3333
in.steel.thr.rods A4 316 M4 L=85 |  | 47.38.77.040.8 | 3 | 4050 | 20.25 | 315 | 3.15 | 13165.2 | 12060 | 12300 | CV | -865.2 | 90 | 9536 | 9530 | -3629.2 |  | Slava | Jan 06 | 6 | 9530 | 0 | 9536 | -2524 | 0 | -2524 | 0 | 3178.6667 |  |  |  | 3179
hex.nuts inox A4 316 0.8D M4 |  | 47.43.77.040.1-? | 6 | 4050 | 20.25 | 315 | 3.15 | 26330.4 | 24120 | 25000 | CV | -1330.4 | 580 | 24000 | 24000 | -2330.4 | pool | Slava |  |  | 24000 | 0 | 24000 | -120 |  |  |  | 4000
washer contact medium M4 |  | 47.78.09.004.1 | 3 | 4050 | 20.25 | 315 | 3.15 | 13165.2 | 12060 | 12400 | CV | -765.2 | 190 | 14306 | 12000 | 1140.8 |  | Slava | Dec 05 | 6 | 12000 | 2300 | 14306 | 2246 |  |  |  | 4768.6667
head.hex.point.scr. M3x5, inox |  | 47.62.96.101.1? | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4200 | CV | -188.4 | 130 | 4200 | 4200 | -188.4 | pool | Slava |  |  | 4200 | 0 | 4200 | 180 |  |  |  | 4200
BNC HT Polypenco SHV 5KV | CERN | 09.41.25.160.9 | 2 | 4050 | 20.25 | 315 | 3.15 | 8776.8 | 8040 | 8272 | GF | -504.8 | 132 | 8204 | 8200 | -572.8 |  | Slava |  | 4 |  | 8200 | 8204 | 164 |  |  |  | 4102
BNC 50ohm, teflon | CERN | 09.46.11.360.4 | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4136 | GF | -252.4 | 66 | 4102 | 4100 | -286.4 |  | Slava |  | 2 |  | 4100 | 4102 | 82 |  |  |  | 4102
soldering lug, M4 | CERN | 04.76.26.448.1 | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4200 | GF | -188.4 | 130 | 4102 | 4100 | -286.4 |  | Slava |  | 2 | 2300 | 1800 | 4102 | 82 |  |  |  | 4102
soldering lug, BNC | CERN | 09.46.11.520.6 | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4200 | GF | -188.4 | 130 | 4102 | 4100 | -286.4 |  | Slava |  | 2 |  | 4100 | 4102 | 82 |  |  |  | 4102
wires (L=100, 1.5mm2) | CERN | 04.01.61.900.1 | 0.15 | 4050 | 20.25 | 315 | 3.15 | 658.26 | 603 | 800 | GF | 141.74 | 189.5 | 800 | 800 | 141.74 |  | Slava |  |  |  | 800 | 800 | 197 |  |  |  | 5333.3333
tinned cupper wires, without insulation, D=0.91mm |  | 04.01.02.091.5 | 0.1 | 4050 | 20.25 | 315 | 3.15 | 438.84 | 402 | 280 | GF | -158.84 | -127 | 331 | 140 | -107.84 |  | Slava |  |  | 191 | 140 | 331 | -71 | 51 |  |  | 3310
Resistor 10Mohm ,1W |  |  | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4250 | GF | -138.4 | 180 | 4100 | 4100 | -288.4 |  | Slava |  |  | 150 | 3950 | 4100 | 80 |  |  |  | 4100
Capacitor (0.47uF, 2000V) |  |  | 1 | 4050 | 20.25 | 315 | 3.15 | 4388.4 | 4020 | 4273 | GF | -115.4 | 203 | 4100 | 4100 | -288.4 |  | Slava |  |  | 100 | 4000 | 4100 | 80 |  |  |  | 4100
supports
arc support plate (Al) plus rilsan coating |  |  | 1 | 3482 | 17.41 | 274 | 2.74 | 3776.15
arc support bracket (inox) plus rilsan coating |  |  | 2 | 3482 | 17.41 | 274 | 2.74 | 7552.3
arc stainless steel ties |  |  | 2 | 3482 | 17.41 | 274 | 2.74 | 7552.3
support LSS |  |  | 1 | ?? |  |  |  | ??
SEM only
SEM Ti electrode |  |  | 1 |  |  | 315 | 3.15 | 318.15 |  |  |  | -318.15
cover spacers
screws
tighteners SEM
Total | [7 empty] | 1436885.75 |  | 1221651 |  | -137588.8 | [9 empty] | 34285 |  | -508398
Ceramics LHCBLM__0041 upper CNGS | FRIATEC (F) | ?? | 1 | 50 |  |  |  | 50 |  | 50 | BD/JMM | 0 |  | 50 | 29.11.2004 | 0 | pool
Ceramics LHCBLM__0042 lower CNGS | FRIATEC (F) | ?? | 1 | 50 |  |  |  | 50 |  | 50 | BD/JMM | 0 |  | 50 | 29.11.2005 | 0 | pool
Note on E4: eholzer: input field
Note on G4: eholzer: input field
Note on O6: grishinv: + 2678 14/12/05
Note on O8: grishinv: + 2767 14/12/05
Note on M13: eholzer: IC and SEM!!
Note on I16: eholzer: IC and SEM!!
Note on M16: eholzer: IC+SEM!!
Note on O16: eholzer: 14600 on 6.1.2006 to be checked
Note on O18: eholzer: 948 on 6.1.2006 to be checked
Note on O27: grishinv: 10+40(7/12)
Note on R29: dehning: 24.10+10d
Note on A33: grishinv: vis tete aplatie in.A2 M3x4
Note on T33: dehning: 24.10+10d
Note on A34: grishinv: vis sans tete 6 p.cr.M3x3
Note on T34: grishinv: 15000- 24.10+10days; 16600- +8 weeks
Note on A35: grishinv: rondelle a plateau inox A2 M4
Note on T35: grishinv: 2000- 24.11+10 days; 73000- 24.11 +2weeks
Note on A36: grishinv: ecrou hexagonal in.autofr.M4
Note on T36: grishinv: 12000- 24.11 + 10 days 11000- 24.11+8/12 weeks
Note on C39: dehning: 1. 20 2. 7420
Note on O39: grishinv: 3986+ 1025+ (6 spare washers) eholzer: wrong value correct value: 7406
Note on O41: grishinv: 1004+5bad; + 5456
Note on O43: grishinv: 1004+5bad; 12160 eholzer: wrong value! About 6120 have been sent for re-machining
Note on O44: grishinv: 1508+5bad; 9150
Note on A51: grishinv: tige filetee in.4.A4 M 4x85 47.62.82.908.1
Note on T51: grishinv: 14 m -24.11+10 days; rest - 24.11+6 weeks
Note on A54: grishinv: vis sans tete 6 p.cr.in N3x5; 47.62.72.995.5
Note on W55: dehning: expec. 31/11 grishinv: Lorry#2,Dec05
Note on W56: dehning: expec. 31.11 grishinv: Lorry#2,Dec05
Note on W57: grishinv: Lorry#2,Dec05;2300 to send
Note on W58: grishinv: Lorry#2,Dec05
Note on W59: grishinv: Lorry#2,Dec05
Note on W60: grishinv: Lorry#2,Dec05;140 to send
Note on W61: grishinv: Lorry#2,Dec05; 150 to send
Note on W62: grishinv: Lorry#2,Dec05; 100 to send
Note on E64: eholzer: minus number of singel supports
Note on I64: eholzer: minus number of single supports
Note on E65: eholzer: eholzer: minus number of singel supports
Note on I65: eholzer: eholzer: minus number of singel supports
Note on E66: eholzer: minus number of single supports
Note on I66: eholzer: minus number of single supports
Note on V13: grishinv: Must be checked in Protvino
Note on AC60: grishinv: Must be checked
Note on Z24: grishinv: Not agree with supply info!
Note on Z25: grishinv: Not agree with supply info?
Note on Z43: grishinv: 1700 - without modification of ext Dia 1375 -? ? - small box
Note on Z38: grishinv: type 1764 + type 859 + type 435 + Which machining?
Note on Z39: grishinv: Claudine info 5.05
Note on AE37: grishinv: AB+297(UK)+515(Italy)
Note on N39: grishinv: No take in account Italy
Note on N40: grishinv: No Itlay
Note on N41: grishinv: No Italy
Note on N43: grishinv: No Italy
Note on N44: grishinv: No Italy
Note on X29: grishinv: Shipping#7: 100(-6) - cleaning in UK and must rewelding!
Note on J4: grishinv: 3799-50(GSNC)+100(LHC)+150(PS)
Note on AC24: grishinv: Wrong number!
Note on AC25: grishinv: Wrong number
Note on AG10: grishinv: 8.06: 700pc ariived for Sh9

## Tighteners
TIGHTENERS |  | Date of receiption | Pieces | Pieces |  | Pieces | Pieces |  | Date of arrived | Per IC | Per IC
|  |  | type A | type B |  | type A | type B | counted by |  | type A | type B
|  |  | Note on boxes |  |  | Counted
| week |  |  |  | EBH
|  |  | 2200 | 0 |  | 2200 | 0 | EBH
0
0
| 11 | 13.03 | 278 | 825 |  | 278 | 825 | Slava
| 12 | 24.03 | 3279 | 676 |  | 2995 | 676 | Slava | 30.03
| 13 |  | 0
| 14 |  | 0
| 15 | 11.04 | 2000 | 1144 |  | 2000 | 1144 | Slava | 19.04
| 16 | 18.04 | 3000 | 558 |  | 3250 | 558 | Slava
| 17 | 28.04 | 1439 | 2270 |  | 1439 | 2520 | Slava | 5.06
| 23 | Summary (7.06) | 12196 | 5473 |  | 12162 | 5723 | Slava
|  | Protvino |  |  |  | 15233 | 7747 | Slava | send?
[6 empty] | 5537 | 2503 | Mikhail | 11.05
|  | Protvino |  |  |  | 13782 | 5223 | Mikhail with Sh7 |  | 3445.5 | 2611.5

## Time to sending
| wed | th | fr | sat | sun | mon | tues | wed | thur | Fr | sat | sun | mon | tu | wed | th | fr
Ready | EDH Shipping Request | bar: mon to th
Price |  | Signed Shipping Request | bar: mon to th
CHF! |  |  | Call Packing Service | bar: mon to th
PS saw the Packages | bar: mon to th
Packing by PS | bar: mon to th
| to add | to add | to add |  |  | to add | !No add | PS & Brigitte ready to order Lorry |  | Fr: Brigitte sent e-mail; mon: Brigitte; fr: Lorry to Protvino
[7 empty] | Ex weight |  |  | Fr: to Ext Tranpsort Company; mon: have a answer
about Lorry
at Fr
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
7-10 days
| Att&Ann to | [17 empty] | FINAL:
| L.Evans | Signed
|  |  | Transfer to Protvino | [15 empty] | 24-27 days
IHEP sign
IHEP sign
IHEP sign
[7 empty] | Rus Custom |  |  | tu: Rus Custom
[7 empty] | ask to permit |  |  | tu: permit

## ceramics
CERAMICS
week | date "le Geneve" | Pieces | Checked by | arrived date |  | Per IC
1
2
4
5
5
6
8
9
10 |  | 200
11 |  | 770
12 |  | 0
13 |  | 0
14 | 3.04 | 1080 | Slava
15 |  | 0
16 | 18.04 | 576 | Slava | 19.04
17 |  | 0
18 |  | 0
19 | 9.05 | 688 | Slava | 10.05
20 | 16.05 | 645 | Slava
21 | 23.05 | 898 | Slava | 23.05 | Shipping8
21 | 26.05 | 480 | Slava | 3.06 | Shipping8
23 | 7.06 | 700 | Slava | 8.06 | Shipping9
23 | Summary (8.06) | 6037 | Slava |  |  | 3018.5
23 | Protvino | 5326 | Slava | with Shipping8 |  | 2663
| Protvino (11.05) | 2019 | Mikhail |  |  | 1009.5
23 | Protvino | 6000 | Mikhail | with Sh7,Sh8,Sh9 |  | 3000

## Spacers
Spacer | [7 empty] | Per IC
| type | date of reception | quoted pieces | received by | counted pieces | counted by | week
January: | type A
47444 |  | pre-series | 9300 |  | 9170
February: |  |  |  |  | 103
52230 |  | 6.1.2006 | 14600 | EBH | 15824 | CC
| 3rd delivery | 24.1.2006 | 10000 | EBH | 10000 | CC
|  | 31.1.2006 | 10740 | EBH
| 5th delivery | 03.2.2006 | 11170 | EBH |  |  |  |  | EBH: 17 pieces measured (add to count)
| 6th delivery | 14.2.2006 | 12730 | EBH |  |  |  |  | EBH: 22 pieces measured (add to count)
| 7th delivery | 28.2.2006 | 15100 | EBH
March: | 8th delivery | 1.3.2006 | 13230 | EBH
| 9th delivery | 8.3.2006 | 15330 | EBH
| 10th delivry | 14.3.2006 | 18380 | EBH
| 11th delivery | 24.03.2006 | 25000 | Slava |  |  | 12
| 12th delivery | 30.03.2006 | 25000 | Slava |  |  | 13
April: | 13th delivery | 3.04.2006 | 25000 | Slava |  |  | 14
| 14th delivery | 19.04,2006 | 23075 | Slava |  |  | 16
| 15th delivery | 26.04.2006 | 21760 | Slava |  |  | 17
May: | 16th delivery | 5.05.2006 | 25000 | Slava |  |  | 18
| 17th delivery | 11.05.2006 | 25000 | Slava |  | 15.05-arrived | 19
| 18th delivery | 19.05.2006 | 25000 | Slava | Shipping8 | 22.05 - arrived | 20
| 19th | 29.05.2006 | 32160 | Slava | Shipping8 | 3.06 - arrived | 22
| Summary |  | 357575 |  |  | 7.06 | 23 | 1953.9617
June
| Protvino |  | 347244 | Slava | with Shipping8 |  |  | 1897.5082
| Protvino | 11.05.2006 | 169859 | Mikhail |  |  |  | 928.1913
| Protvino |  | 346854 | Mikhail | with Sh7,Sh8 |  |  | 1895.377
type B
|  | 6.1.2006 | 948 | EBH | 941 | CC
type C
|  | pre-series | 300 |  | 305
93
|  | 12.1.2006 | 606 | EBH
| 3rd delivery | 24.1.2006 | 10550 | EBH
| Suimmary |  | 10550
| Protvino |  | 10625 | Slava |  |  |  | 1770.8333
| Protvino |  | 10604 | Mikhail |  |  |  | 1767.3333