## BLM chambers
| Sub-System | Delivery by | DAI order # | per chamber | number IC | spare IC | number SEM | spare SEM | total needed quantity | for IHEP December 2005 | ordered | ordered by? | to be ordered | received | date of receiving | location | checked by? | delivery schedule | shipped to Protvino | unit price | total price | comments
LEGENDE: blue background means entered or checked by EBH, grey letters means: obsolete, deleted by EBH, grey backround means: cannot be checked by EBH
3818 IC +318 SEM (+4% spares) |  |  |  |  | 3799 | 18.995 | 315 | 3.15 | 4136.145
LHCBLM__0001 and LHCBLM__0009
| tube inox 304L 483x88.9x2.0 LHCBLM__0040 | Santrade, CH | 39.39.05.088.2 | 1 | 3799 | 18.995 |  |  | 3817.995 |  | 3800 | CV | 17.995 | 1455 |  | pool | SG |  | 1394 | 12.00 |  | 59- still at CERN
| tube inox 304L 109x88.9x2.0 LHCBLM__0040 |  |  | 1 |  |  | 315 | 3.15 | 318.15 |  | 310 | CV | 8.15
| tube inox 304L 105x88.9x2 LHCBLM__0038 v.AB |  |  | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 |  | 4110 | CV | 26.145 | 1504 |  |  | SG |  | 1500 |  |  | 4 still at CERN
| Ceramics LHCBLM__0005 v.AC |  | partially open, ?? | 2 | 3749 | 18.745 |  |  | 7535.49 | 4 | 7110 | EBH | 425.49
| Ceramics LHCBLM__0005 v.AC |  | open | 1 |  |  | 315 | 3.15 | 318.15
| Ceramics LHCBLM__0041 upper CNGS | FRIATEC (F) | ?? | 1 | 50 |  |  |  | 50 |  | 50 | BD/JMM | 0
| Ceramics LHCBLM__0042 lower CNGS | FRIATEC (F) | ?? | 1 | 50 |  |  |  | 50 |  | 50 | BD/JMM | 0
| Al electrodes production LHCBLM__0004 0.5X82 | Dutreive (F) | partially open, CA 1391681 | 61 | 3799 | 18.995 |  |  | 232897.695 | 70 | 208020 | EBH | 24877.695 | [5 empty] | 0 |  | #REF!
| Al electrodes production LHCBLM__0004 0.5X82 | Dutreive (F) | open | 2 |  |  | 315 | 3.15 | 636.3 | [9 empty] | 0 |  | #REF!
| Al electrodes 0.5 AL material | CERN | partially open, CA 1391681 | [8 empty] | 0 | [6 empty] | 16650 |  | #REF!
[19 empty] | 302 | Claudine | #REF!
check!!:
| electrode spacer LHCBLM__0007 type A | Flueckiger (CH) | CA1390364 +?? | 183 | 3799 | 18.995 |  |  | 698693.085 | 1830 | 698300 | EBH/JMM | 393.085 | 9170 |  | pool | SG
| electrode spacer LHCBLM__0007 type A | Flueckiger (CH) | CA1390364 +?? | 9 |  |  | 315 | 3.15 | 2863.35
| electrode spacer LHCBLM__0007 type B | Flueckiger (CH) | CA1390364 +?? | 3 |  |  | 315 | 3.15 | 954.45 |  | 930 | EBH/JMM | 24.45
| electrode spacer LHCBLM__0007 type C | Flueckiger (CH) | CA1390364 +?? | 6 | 3799 | 18.995 |  |  | 22907.97 | 60 | 22800 | EBH/JMM | 107.97 | 305 |  | pool | SG
| bot. cov. disk LHCBLM__0006, 316L, 5mm | CERN, material |  | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 |  | ?? | EBH??
| bottom cover disk LHCBLM__0006 | RPM (I) | CA1390102+CA1392889 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 50 | 4110 | EBH/JMM | 26.145 | 90
| bottom cover spacer LHCBLM__0006 | Dedecker (B) | CA1390111 | 1 | 3799 | 18.995 |  |  | 3817.995 | 10 | 3800 | EBH/JMM | 17.995 | 50 | [5 empty] | 0.03
SEM only
| SEM Ti electrode |  |  | 1 |  |  | 315 | 3.15 | 318.15
cover spacers
screws
tighteners SEM
tighteners M4 LHCBLM__0016
check!!:
| type B Var 1 (incl. LHCBLM__0013) | JCM (F) |  | 2 | 3799 | 18.995 |  |  | 7635.99 | 2 | 7600 | EBH/JMM | 35.99
| type A Var 1 (incl. welded washer) | JCM (F) |  | 4 | 3799 | 18.995 |  |  | 15271.98 | 4 | 15200 | EBH/JMM | 71.98
heads
| 50 IC heads (CNGS) | DG-technology (I) | CA1390214 | 1 | 50 |  |  |  | 50 | 0 | 50 | EBH/JMM | 0 | 10 |  | pool
| 500 IC heads (IHEP) | AeroVac (GB) |  | 1 | 500 |  |  |  | 500 | 500 | 0 | EBH/JMM | 500
small items
| compressing spring 1.4310 ferroflex | Ferroflex | VD-180M-14 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 |  | 3850 | CV | 286.145 |  |  |  |  | 24.10+10d
| alumina tube D15/10, L=25mm | CERN | 19.63.30.128.9 | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 | 20 | 8220 | EBH | 52.29 | 102? |  | SG | SG |  |  | 2
| slotted screw M3x4, A2-ISO 1580 | Bossard BN652 | 47.62.72.996.0 | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 |  | 8400 | CV | -127.71 |  |  |  |  | 24.10+10d |  | 5
| screw without head 6pc bt point.in.3x3 | Bossard BN618 | 47.62.72.995.0 | 4 | 3799 | 18.995 | 315 | 3.15 | 16544.58 |  | 16600 | CV | -55.42
| spring washer D8/4.2-0.2, 1.4310 | Bossard BN838 | 47.62.72.996.8 | 18 | 3799 | 18.995 | 315 | 3.15 | 74450.61 |  | 75000 | CV | -549.39
| stop nut M4-A2 DIN980V | Bossard BN5242 | 47.62.72.998.2 | 6 | 3799 | 18.995 | 315 | 3.15 | 24816.87 |  | 23000 | CV | 1816.87
cover assembly LHCBLM__0002
| cover plate LHCBLM__0003, 316L, material | CERN |  | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 |  | 8250 |  | 22.29
| cover plate LHCBLM__0003, 316L | Dedecker (B) | CL1932975 +?? | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 |  | 10 | EBH/JJM | 4126.145
| feed throughs | CERAMTEC (US) | 1889051/1937566 | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 |  | 7420 | EBH | 852.29 | 3986 |  | CC | CC |  | 4 | 20
| copper tube 10 x 8, L=120mm | CERN, MR 1887862 | 39.71.20.008.8 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 |  | 4110 | CV | 26.145 |  |  |  | CV |  | 2
| cover spacer LHCBLM__0008 type A, 316L | Solpey (E) | CA1390217 | 2 | 3799 | 18.995 |  |  | 7635.99 |  | 6500 | EBH/JJM | 1135.99
| cover spacer LHCBLM__0008 type B, 316L | Solpey (E) | CA1390217 | 2 |  |  | 315 | 3.15 | 636.3 |  | 620 | EBH/JJM | 16.3
| protection tube LHCBLM__0010, 316L | Solpey (E) | CA1390217 | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 |  | 7120 | EBH/JJM | 1152.29 | [5 empty] | 102 | Slava
| welded spacer LHCBLM__0035, 304L | Solpey (E) | CA1390217 | 3 | 3799 | 18.995 | 315 | 3.15 | 12408.435 |  | 10680 | EBH/JJM | 1728.435
electrical connectors ass LHCBLM__0036
| el.box cover rondel, 304L, 5mm, material | CERN |  | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 |  | 4110 |  | 26.145
| external plate LHCBLM__0037, manufacture | Solpey (E) | CA1390916 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 10 | 4110 | EBH/JJM | 26.145 | 50
| st steel sheet LHCBLM__0037, material | CERN | [6 empty] | ??
| st steel sheet LHCBLM__0037, manufacture | Cherokee (B) | CA1391433 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 10 | 4110 | EBH/JJM | 26.145
| tube AlMgSi hard 4*7 L=60 |  | 39.64.05.012.1 | 3 | 3799 | 18.995 | 315 | 3.15 | 12408.435 |  | 780 MT | CV | #VALUE! |  |  |  |  | 27.10+2wks
| in.steel.thr.rods A4 316 M4 L=85 |  | 47.38.77.040.8 | 3 | 3799 | 18.995 | 315 | 3.15 | 12408.435 |  | 12300 | CV | 108.435
| hex.nuts inox A4 316 0.8D M4 |  | 47.43.77.040.1 | 6 | 3799 | 18.995 | 315 | 3.15 | 24816.87 |  | 25000 | CV | -183.13
| washer contact medium M4 |  | 47.78.09.004.1 | 3 | 3799 | 18.995 | 315 | 3.15 | 12408.435 |  | 12400 | CV | 8.435 |  |  |  |  | 27.10+2wks
| head.hex.point.scr. M3x5, inox |  | 47.62.96.101.1 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 |  | 4200 | CV | -63.855
| BNC HT Polypenco SHV 5KV | CERN | 09.41.25.160.9 | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 | 8200 | 8272 | GF | 0.29 | 8272 |  |  |  |  | 8200 |  | #REF!
| BNC 50ohm, teflon | CERN | 09.46.11.360.4 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4100 | 4136 | GF | 0.145 | 4136 |  |  |  |  | 4100 |  | #REF!
| soldering lug, M4 | CERN | 04.76.26.448.1 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 1800 | 4200 | GF | -63.855 | 1800 |  |  |  |  | 1800 |  | #REF!
| soldering lug, BNC |  | 09.46.11.520.6 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4100 | 4200 | GF | -63.855 | 4200 |  |  |  |  | 4100
| washer, same thickness as soldering lug | CERN | ?? | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 |  | 0 | CV | 8272.29
| wires (L=100, 1.5mm2) | CERN | 04.01.61.900.1 | 0.15 | 3799 | 18.995 | 315 | 3.15 | 620.4217 | 800 | 800 | GF | -179.5783 | 800 |  |  |  |  | 800 |  | #REF!
| tinned cupper wires, without insulation, D=0.91mm |  | 04.01.02.091.5 | 0.1 | 3799 | 18.995 | 315 | 3.15 | 413.6145 | 140 | 280 | GF | 133.6145 | 280 |  |  |  |  | 140
| Resistor 10Mohm ,1W |  |  | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 3950 | 4250 | GF | -113.855 | 4250 |  |  |  |  | 3950 |  | #REF!
| Capacitor (0.47uF, 2000V) |  |  | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4100 | 4273 | GF | -136.855 | 4273 |  |  |  |  | 4000 |  | #REF!
ion chamber + SEM (common material) | [6 empty] | #REF! | #REF! | #REF! |  |  | #REF!
| Total | [10 empty] | #REF!
Note on M17: dehning: in m 0.082 /ion
Note on D52: dehning: 1. 20 2. 7420
Note on T68: dehning: expec. 31/11 grishinv: Lorry#2,Dec05
Note on T69: dehning: expec. 31.11 grishinv: Lorry#2,Dec05
Note on T18: dehning 1. 061005 350 0 2. 121005 282 144 3. 131005 138 138
Note on F4: eholzer: input field
Note on H4: eholzer: input field
Note on T70: grishinv: Lorry#2,Dec05;2300 to send
Note on T71: grishinv: Lorry#2,Dec05
Note on T75: grishinv: Lorry#2,Dec05; 150 to send
Note on T76: grishinv: Lorry#2,Dec05; 100 to send
Note on T73: grishinv: Lorry#2,Dec05
Note on T74: grishinv: Lorry#2,Dec05;140 to send
Note on S46: grishinv: 15000- 24.10+10days; 16600- +8 weeks
Note on B47: grishinv: rondelle a plateau inox A2 M4
Note on B45: grishinv: vis tete aplatie in.A2 M3x4
Note on B46: grishinv: vis sans tete 6 p.cr.M3x3
Note on S47: grishinv: 2000- 24.11+10 days; 73000- 24.11 +2weeks
Note on B48: grishinv: ecrou hexagonal in.autofr.M4
Note on S48: grishinv: 12000- 24.11 + 10 days 11000- 24.11+8/12 weeks
Note on B64: grishinv: tige filetee in.4.A4 M 4x85 47.62.82.908.1
Note on S64: grishinv: 14 m -24.11+10 days; rest - 24.11+6 weeks
Note on B67: grishinv: vis sans tete 6 p.cr.in N3x5; 47.62.72.995.5