## BLM chambers
Sub-System | Delivery by | DAI order # | per chamber | number IC | spare IC | number SEM | spare SEM | total needed quantity | total needed quantity Pr (IC+SEM) | total needed quantity Pr (IC) | ordered | ordered by? | ordered - needed | order-needed to Pr (IC) | received | received in Pr_IC (11.05):no Sh7,8,9 | received-needed | location | checked by? | latest delivery schedule | sh. to Protvino 2006 by hand | shipped to Protvino 2006 | shipped to Protvino 2005 | shipped to Protvino ALL | Mishas counting in Protvino (up to sh 7) | Mishas counting plus LZ and LS | to be shippied Protvino06 IC+SEM | to be shippied Protvino06 IC | Exist in LZ For Shipp_9 | shipment 7 | shipment 8 | Exist in LZ after LS | shipped to Protvino plus LZ per IC, slavas num. | Slavas still to buy | TO ORDER | Comment |  | order with JMM
14.6.2006 | [24 empty] | fill SG |  |  |  | check SG |  |  | check SG |  | ?? |  |  | check! | order with DAI
In PROTVINO | [9 empty] | 4305 | [21 empty] | check Ion
|  |  |  | 4100 | 205 | 350 | 35 | 4690 | 4690 | 4305 | [22 empty] | 4020
LHCBLM__0001 and LHCBLM__0009
tube inox 304L 483x88.9x2.0 LHCBLM__0040, IC | Santrade, CH | 39.39.05.088.2 | 1 | 4100 | 205 |  |  | 4305 | 4305 | 4305 | 3800 | CV | -505 | -505 | 4133 | 3773 | -172 | pool | SG |  |  | 2379 | 1394 | 3773 | 3773 | 3781 | -532 | -532 | 0 |  |  | 8 | 3781 | -532 | 524 |  | -8
tube inox 304L 109x88.9x2.0 LHCBLM__0040, SEM |  | 39.39.05.088.2 | 1 |  |  | 350 | 35 | 385 | 385 |  | 310 | CV | -75 | 310 | 118 |  | -267 | pool | Slava | [12 empty] | 210 | 210 |  | 385 |  | 385
tube inox 304L 105x88.9x2 LHCBLM__0038 v.AB | el. box | 39.39.05.088.2 | 1 | 4100 | 205 | 350 | 35 | 4690 | 4690 | 4305 | 4110 | CV | -580 | -195 | 4271 | 3818 | -419 | pool | SG |  |  | 2318 | 1500 | 3818 | 3818 | 4029 | -872 | -487 | 0 |  |  | 211 | 4029 | -872 | 661 | minus count SEM tubes | -211
Ceramics LHCBLM__0005 v.AC, IC |  |  | 2 | 4100 | 205 |  |  | 8610 | 8610 | 8610 | 7110 | EBH | -1500 | -1500 | 7696 | 2019 | -914 |  | Slava |  | 10 | 3407 | 0 | 5326 | 2019 | 7094 | -3284 | -3284 | 1794 | 1903 | 1378 | 1794 | 4457 | -1490 | 1516 | calculate | 26 | 1550
Ceramics LHCBLM__0005 v.AC, SEM |  | open | 1 |  |  | 350 | 35 | ?? | ?? |  |  |  | #VALUE! | 0 |  |  | #VALUE! | [15 empty] | 0
Al electrodes production LHCBLM__0004 0.5X82, IC | Dutreive (F) | CA 1391681 | 61 | 4100 | 205 |  |  | 262605 | 262605 | 262605 | 208020 | EBH | -55355 | -54585 | 207126 | 207000 | -55479 |  | Slava | Dec 05 | 126 | 207000 | 0 | 207126 | 207000 | 209363 | -55479 | -55479 | 0 |  |  | 2363 | 5758.5082 | -55479 | 53242 |  | -2237 | 57000
Ti electrodes production LHCBLM__0004 0.5X82, SEM | Dutreive (F) | open | 2 |  |  | 350 | 35 | 770 | 770 |  | 0 |  |  | 0 |  |  | -770 |  |  | Dec 05 | [12 empty] | 0 |  | 770 |  | 770
electrode spacer LHCBLM__0007 type A | Flueckiger (CH) | CA1390364 +?? | 183 | 4100 | 205 |  |  | 791280 | 791280 | 787815 | 712900 | EBH/JMM | -78380 | -74915 | 492060 | 169859 | -299220 | pool | SG, EBH | ?? | 390 | 355355 | 1830 | 357575 | 10604 | 273009 | -433705 | -430240 | 85410 | 119835 | 57160 | 85410 | 87363.9617 | -348295 | 78380 | calculate | -269915 | 80000
electrode spacer LHCBLM__0007 type A, SEM | Flueckiger (CH) | CA1390364 +?? | 9 |  |  | 350 | 35 | [6 empty] | 0 |  |  | ? |  |  | ?? | [12 empty] | 0 |  | 0
electrode spacer LHCBLM__0007 type B, SEM | Flueckiger (CH) | CA1390364 +?? | 3 |  |  | ? | ? | #VALUE! | #VALUE! |  | 990 | EBH/JMM | #VALUE! | 990 | 948 |  | #VALUE! |  |  | ?? | [12 empty] | 0
electrode spacer LHCBLM__0007 type C | Flueckiger (CH) | CA1390364 +?? | 6 | 4100 | 205 |  |  | 25830 | 25830 | 25830 | 23300 | EBH/JMM | -2530 | -2530 | 10625 | 10604 | -15205 | pool | SG, EBH | ?? | 15 | 10550 | 60 | 10625 | 10604 | 10604 | -15205 | -15205 | 0 |  |  |  | 1770.8333 | -15205 | 2530 | calculate | -12675 | 3000
bottom cover disk LHCBLM__0006 | RPM (I) | CA1390102+CA1392889 | 1 | 4100 | 205 | 350 | 35 | 4690 | 4690 | 4305 | 4110 | EBH/JMM | -580 | -195 | 4432 | 4429 | -258 |  | Slava | Dec 05 | 2 | 4380 | 50 | 4432 | 4429 | 4438 | -258 | 127 |  |  |  | 9 | 4441 | -258 | 252 | 580!! | -6 | 650 |  |  | 1750
bottom cover spacer LHCBLM__0006 | Dedecker (B) | CA1390111 | 1 | 4100 | 205 |  |  | 4305 | 4305 | 4305 | 3800 | EBH/JMM | -505 | -505 | 3592 | 3590 | -713 |  | Slava | Nov 05 | 2 | 3580 | 10 | 3592 | 3590 | 3590 | -713 | -713 | 0 |  |  |  | 3592 | -713 | 715 |  | 2 | 800
tighteners M4 LHCBLM__0016 | [13 empty] | 0
type A Var 1 (incl. welded washer) | JCM (F) |  | 4 | 4100 | 410 |  |  | 18040 | 18040 | 18040 | 15400 | EBH/JMM | -3040 | -2640 | 17039 | 2503 | #REF! |  | Slava |  | 8 | 12032 | 4 | 12044 | 14497 | 14497 | -5996 | -5996 | 0 | 8245 |  | 0 | 3445 | -5996 | 3543 |  | -2453
type B Var 1 (incl. LHCBLM__0013) | JCM (F) |  | 2 | 4100 | 410 |  |  | 9020 | 9020 | 9020 | 7700 | EBH/JMM | -1520 | -1320 | 6639 | 5537 | #REF! |  | Slava |  | 4 | 4473 | 0 | 4477 | 6905 | 6905 | -4543 | -4543 | 0 | 2720 |  | 0 | 2611 | -4543 | 2115 |  | -2428
heads | [13 empty] | 0
50 IC heads (CNGS) | DG-technology (I) | CA1390214 | 1 | 50 |  |  |  | 50 |  |  | 50 | EBH/JMM | 0 | 50 | 50 |  | 0 | pool |  | ?? |  |  | 5 | 5 | [10 empty] | 0
heads (Alca/Italy) | [8 empty] | ? | ? |  |  |  | #VALUE! | [7 empty] | 0
500 IC heads (Aerovac) | AeroVac (GB) |  | 1 | 500 |  |  |  | 500 | 480 | 480 | 500 | EBH/JMM | 0 | 20 | 347 |  | -153 |  | Slava |  |  | 347 |  | 347 |  | 300 | -133 | -133 |  | 250 | 50 | 0 | 347 |  | 180 |  | 180
small items | [13 empty] | 0
compressing spring 1.4310 ferroflex | Ferroflex | VD-180M-14 | 1 | 4100 | 205 |  |  | 4305 | 4305 | 4305 | 3850 | CV | -455 | -455 | 3784 | 3780 | -521 | pool | Slava | Dec 05 | 4 | 3780 | 0 | 3784 | 3780 | 3780 | -521 | -521 |  |  |  | 0 | 3784 | -521 | 525 |  | 4
alumina tube D15/10, L=25mm | CERN | 19.63.30.128.9 | 2 | 4100 | 205 |  |  | 8610 | 8610 | 8610 | 8220 | EBH | -390 | -390 | 11551 | 4563 | 2941 | SG | SG |  | 119 | 11432 | 0 | 11551 | 4563 | 8197 | 2941 | 2941 |  | 3565 |  | 69 | 5844.5 | 2941 | 413 |  | 3354
slotted screw M3x4, A2-ISO 1580 | Bossard BN652 | 47.62.72.996.0 | 2 | 4100 | 205 | 350 | 35 | 9380 | 9380 | 8610 | 8400 | CV | -980 | -210 | 8305 | 8300 | -1075 | pool | Slava | Dec 05 | 5 | 8300 | 0 | 8305 | 8300 | 8300 | -1075 | -305 |  |  |  | 0 | 4152.5 | -1075 | 1080 |  | 5
screw without head 6pc bt point.in.3x3 | Bossard BN618 | 47.62.72.995.0 | 4 | 4100 | 1230 | 350 | 105 | 23140 | 23140 | 17220 | 16600 | CV | -6540 | -620 | 16406 | 16400 | -6734 | pool | Slava | Jan 06 | 6 | 16400 | 0 | 16406 | 16400 | 16400 | -6734 | -814 |  |  |  | 0 | 4101.5 | -6734 | 6740 |  | 6
spring washer D8/4.2-0.2, 1.4310 | Bossard BN838 | 47.62.72.996.8 | 18 | 4100 | 205 | 350 | 35 | 84420 | 84420 | 77490 | 75000 | CV | -9420 | -2490 | 73140 | 85500 | -11280 |  |  | Dec 05 | 40 | 73100 | 0 | 73140 | 85500 | 85500 | -11280 | -4350 |  |  |  | 0 | 4063.3333 | -11280 | -1080 |  | -12360
hex.nuts inox A4 316 0.8D M4 |  | 47.43.77.040.1-? | 6 | 4100 | 205 | 350 | 35 | 28140 | 28140 | 25830 | 45600 | CV | 17460 | 19770 | 45640 | 45600 | 17500 |  | Slava | Feb 06 | 40 | 45600 | 0 | 45640 | 45600 | 45600 | 17500 | 19810 |  |  |  | 0 | 7606.6667 | 17500 | -17460 |  | 40
TIG welding job
TIG welding of heads (IHEP or company) |  |  | 1 | 3620 | 18.1 | 350 | 35 | 4023.1 |  |  | 0 | EBH/JMM | -4023.1 |  |  |  | -4023.1
electrical connectors ass LHCBLM__0036
external plate LHCBLM__0037, manufacture | Solpey (E) | CA1390916 | 1 | 4100 | 205 | 350 | 35 | 4690 | 4690 | 4305 | 4110 | EBH/JJM | -580 | -195 | 4090 | 4089 | -600 |  | Slava | ?? |  | 4080 | 10 | 4090 | 4089 | 4133 | -600 | -215 |  |  |  | 44 | 4090 | -600 | 557 |  | -43 | 600
st steel sheet LHCBLM__0037, manufacture | Cherokee (B) | CA1391433 | 1 | 4100 | 205 | 350 | 35 | 4690 | 4690 | 4305 | 4160 | EBH/JJM | -530 | -145 | 4092 | 4080 | -598 |  | Slava | ?? | 2 | 4080 | 10 | 4092 | 4080 | 4094 | -598 | -213 |  |  |  | 14 | 4092 | -598 | 596 |  | -2 | 650
tube AlMgSi hard 4*7 L=60 |  | 39.64.05.012.1 | 3 | 4100 | 205 | 350 | 35 | 14070 | 14070 | 12915 | 780 MT | CV |  |  | 9266 | 19450 | -4804 |  | Slava | 27.10+2wks | 156 | 8128 | 0 | 8284 | 19450 | 20432 | -5786 | -4631 | 0 | 982 |  | 0 | 2761.3333 | -5786 | -6362 | ??? | -12148
in.steel.thr.rods A4 316 M4 L=85 |  | 47.38.77.040.8 | 3 | 4100 | 205 | 350 | 35 | 14070 | 14070 | 12915 | 12300 | CV | -1770 | -615 | 11336 | 9530 | -2734 |  | Slava | Jan 06 | 6 | 9530 | 0 | 11336 | 9530 | 11330 | -2734 | -1579 | 1800 |  |  | 1800 | 3778.6667 | -934 | 2740 |  | 1806
hex.nuts inox A4 316 0.8D M4 |  | 47.43.77.040.1-? | 6 | 4100 | 205 | 350 | 35 | 28140 | 28140 | 25830 | 25000 | CV | -3140 | -830 | 24000 | 24000 | -4140 | pool | Slava |  |  | 24000 | 0 | 24000 | 24000 | 24000 | -4140 | -1830 |  |  |  |  | 4000 | -4140 | 4140 |  | 0
washer contact medium M4 |  | 47.78.09.004.1 | 3 | 4100 | 205 | 350 | 35 | 14070 | 14070 | 12915 | 12400 | CV | -1670 | -515 | 14306 | 12000 | 236 |  | Slava | Dec 05 | 6 | 12000 | 2300 | 14306 | 12000 | 12000 | 236 | 1391 |  |  |  |  | 4768.6667 | 236 | 2070 |  | 2306
head.hex.point.scr. M3x5, inox |  | 47.62.96.101.1? | 2 | 4100 | 1230 | 350 | 105 | 11570 | 11570 | 8610 | 4200 | CV | -7370 | -4410 | 4200 | 4200 | -7370 | pool | Slava |  |  | 4200 | 0 | 4200 | 4200 | 4200 | -7370 | -4410 |  |  |  |  | 2100 | -7370 | 7370 |  | 0
BNC HT Polypenco SHV 5KV | CERN | 09.41.25.160.9 | 2 | 4100 | 205 | 350 | 35 | 9380 | 9380 | 8610 | 8272 | GF | -1108 | -338 | 8204 | 8200 | -1176 |  | Slava |  | 4 |  | 8200 | 8204 | 8200 | 8200 | -1176 | -406 |  |  |  |  | 4102 | -1176 | 1180 |  | 4
BNC 50ohm, teflon | CERN | 09.46.11.360.4 | 1 | 4100 | 205 | 350 | 35 | 4690 | 4690 | 4305 | 4136 | GF | -554 | -169 | 4102 | 4100 | -588 |  | Slava |  | 2 |  | 4100 | 4102 | 4100 | 4100 | -588 | -203 |  |  |  |  | 4102 | -588 | 590 |  | 2
soldering lug, M4 | CERN | 04.76.26.448.1 | 1 | 4100 | 205 | 350 | 35 | 4690 | 4690 | 4305 | 4200 | GF | -490 | -105 | 4102 | 4100 | -588 |  | Slava |  | 2 | 2300 | 1800 | 4102 | 4100 | 4100 | -588 | -203 |  |  |  |  | 4102 | -588 | 590 |  | 2
soldering lug, BNC | CERN | 09.46.11.520.6 | 1 | 4100 | 205 | 350 | 35 | 4690 | 4690 | 4305 | 4200 | GF | -490 | -105 | 4102 | 4100 | -588 |  | Slava |  | 2 |  | 4100 | 4102 | 4100 | 4100 | -588 | -203 |  |  |  |  | 4102 | -588 | 590 |  | 2
wires (L=100, 1.5mm2) | CERN | 04.01.61.900.1 | 0.15 | 4100 | 205 | 350 | 35 | 703.5 | 703.5 | 645.75 | 800 | GF | 96.5 | 154.25 | 800 | 800 | 96.5 |  | Slava |  |  |  | 800 | 800 | 800 | 800 | 96.5 | 154.25 |  |  |  |  | 5333.3333 | 96.5 | -96.5 |  | 0
tinned cupper wires, without insulation, D=0.91mm |  | 04.01.02.091.5 | 0.1 | 4100 | 205 | 350 | 35 | 469 | 469 | 430.5 | 280 | GF | -189 | -150.5 | 331 | 140 | -138 |  | Slava |  |  | 191 | 140 | 331 |  | #VALUE! | -138 | -99.5 |  |  | 51 |  | 3310 | -138
Resistor 10Mohm ,1W |  |  | 1 | 4100 | 205 | 350 | 35 | 4690 | 4690 | 4305 | 4250 | GF | -440 | -55 | 4100 | 4100 | -590 |  | Slava |  |  | 150 | 3950 | 4100 | 4100 | 4100 | -590 | -205 |  |  |  |  | 4100 | -590 | 590 |  | 0
Capacitor (0.47uF, 2000V) |  |  | 1 | 4100 | 205 | 350 | 35 | 4690 | 4690 | 4305 | 4273 | GF | -417 | -32 | 4100 | 4100 | -590 |  | Slava |  |  | 100 | 4000 | 4100 | 4100 | 4100 | -590 | -205 |  |  |  |  | 4100 | -590 | 590 |  | 0
shrinking tube | 5 cm per IC |  | 0.05 | 4100 | 205 | 350 | 35 | 234.5 | 234.5 | [12 empty] | 200 |  |  |  | 0 | [7 empty] | 0 | 234.5
Total | [7 empty] | #VALUE! |  |  | 1196751 |  | #VALUE! | [9 empty] | 34263 |  |  |  | -545042.5 | -512581.25
Sub-System | Delivery by | DAI order # | per chamber | number IC | spare IC | number SEM | spare SEM | total needed quantity | total needed quantity Pr (IC+SEM) | total needed quantity Pr (IC) | ordered | ordered by? | ordered - needed | order-needed to Pr (IC) | received | received in Pr_IC (11.05):no Sh7,8,9 | received-needed | location | checked by? | latest delivery schedule | sh. to Protvino 2006 by hand | shipped to Protvino 2006 | shipped to Protvino 2005 | shipped to Protvino ALL | Mishas counting in Protvino | Mishas counting plus LZ and LS | In Pr or available for Pr / IC | in LZ (seperately) | Exist in LZ for next Shipping |  |  | Exist in LZ after LS/IC | shipped to Protvino per IC, slavas num. | Slavas still to buy | TO ORDER | order with JMM | Heads: shipped to Italy/IC | Head's:UK+IT+Pr+LZ | Heads: Needed:Exist - 4305 | Heads: shipped to UK/IC
[28 empty] | check Ion | [7 empty] | order with DAI
cover assembly LHCBLM__0002 | [13 empty] | 0
cover plate LHCBLM__0003, 316L | Dedecker (B) | CL1932975 +?? | 1 | 3620 | 250 |  |  | 3870 | 3870 | #REF! | 3610 | EBH/JJM | -260 | #REF! | 1904 | 800 | -1966 |  | EBH | ?? | 2 | 2000 | 2 | 2004 | 800 |  | 3438 | 5 | 929 |  |  | 934 | 2004 | -570 | 432 | 500 | 515 | 3069 | -1236
feed throughs | CERAMTEC (US) | 1889051/1937566 | 2 | 4100 | 250 | 350 | 35 | 9470 | 8510 | 7740 | 7440 | EBH/JJM | -2030 | -300 | 7214 | 1600 | -2256 | pool | CC |  | 0 | 4000 | 4 | 4004 | 1600 |  | 3143 |  | 1076 |  |  | 538 | 2002 | -964 | 2224 | 2240 | 515 | 3067 | -1238
cover plate LHCBLM__0003, 316L, SEM new desingn | Dedecker (B) | CL1932975 +?? | 1 |  |  | 350 | 35 | 385 | 385
copper tube 10 x 8, L=120mm | CERN, MR 1887862 | 39.71.20.008.8 | 1 | 4100 | 250 | 350 | 35 | 4735 | 4255 | 0 | 4110 | CV | -625 | 3630 | 5375 | 810 | 640 |  | CV |  |  | 2010 | 2 | 2012 | 810 |  | 3777 |  | 1265 |  |  | 1265 | 2012 | -247 | 478 |  | 515 | 3077 | -1228
cover spacer LHCBLM__0008 type A, 316L, IC | Solpey (E) | CA1390217 | 2 | 4100 | 250 |  |  | 8700 | 7740 | 8040 | 6500 | EBH/JJM | -2200 | -2500 | 7395 | 1600 | -1305 | pool | RT |  |  | 4000 | 4 | 4004 | 1600 |  | 3014.5 | 90 | 935 |  |  | 512.5 | 2002 | -989.5 | 1711 | 1900 | 515 | 3067 | -1238
cover spacer LHCBLM__0008 type B, 316L, SEM | Solpey (E) | CA1390217 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 620 | EBH/JJM | 620 |  | 605 |  | 605 | pool | RT
protection tube LHCBLM__0010, 316L | Solpey (E) | CA1390217 | 2 | 4100 | 250 |  |  | 8700 | 7740 | 8040 | 7120 | EBH/JJM | -1580 | -1880 | 13759 | 2100 | 5059 | pool | RT |  |  | 4000 | 4 | 4004 | 1600 |  | 2799.5 |  | 595 |  |  | 297.5 | 2002 | -1204.5 | 2141 | 2300 | 515 | 3067 | -1238
welded spacer LHCBLM__0035, 304L, IC | Solpey (E) | CA1390217 | 3 | 4100 | 250 | 350 | 35 | 14205 | 12765 | 12060 | 10680 | EBH/JJM | -3525 | -2820 | 11300 | 2400 | -2905 | pool | RT |  | 0 | 5700 | 6 | 5706 | 2400 |  | 2616 | 642 | 0 |  |  | 214 | 1902 | -1188 | 4917 | 5500 | 515 | 2967 | -1338
welded spacer LHCBLM__0035??, 316L, SEM - new design!! | Solpey (E) | CA1390217 | 4 |  |  | 350 | 35 | 1540
Ceramics LHCBLM__0041 upper CNGS | FRIATEC (F) | ?? | 1 | 50 |  |  |  | 50 |  |  | 50 | BD/JMM | 0 |  | 50 | 29.11.2004 | 0 | pool
Ceramics LHCBLM__0042 lower CNGS | FRIATEC (F) | ?? | 1 | 50 |  |  |  | 50 |  |  | 50 | BD/JMM | 0 |  | 50 | 29.11.2005 | 0 | pool
|  | 2170 | [29 empty] | 1076 | 1094
Note on E4: eholzer: input field
Note on G4: eholzer: input field
Note on P6: grishinv: + 2678 14/12/05
Note on P8: grishinv: + 2767 14/12/05
Note on N11: eholzer: IC and SEM!!
Note on I13: eholzer: IC and SEM!!
Note on N13: eholzer: IC+SEM!!
Note on P13: eholzer: 14600 on 6.1.2006 to be checked
Note on P15: eholzer: 948 on 6.1.2006 to be checked
Note on P23: grishinv: 10+40(7/12)
Note on S25: dehning: 24.10+10d
Note on A29: grishinv: vis tete aplatie in.A2 M3x4
Note on U29: dehning: 24.10+10d
Note on A30: grishinv: vis sans tete 6 p.cr.M3x3
Note on U30: grishinv: 15000- 24.10+10days; 16600- +8 weeks
Note on A31: grishinv: rondelle a plateau inox A2 M4
Note on U31: grishinv: 2000- 24.11+10 days; 73000- 24.11 +2weeks
Note on U32: grishinv: 12000- 24.11 + 10 days 11000- 24.11+8/12 weeks
Note on A39: grishinv: tige filetee in.4.A4 M 4x85 47.62.82.908.1
Note on U39: grishinv: 14 m -24.11+10 days; rest - 24.11+6 weeks
Note on A42: grishinv: vis sans tete 6 p.cr.in N3x5; 47.62.72.995.5
Note on X43: dehning: expec. 31/11 grishinv: Lorry#2,Dec05
Note on X44: dehning: expec. 31.11 grishinv: Lorry#2,Dec05
Note on X45: grishinv: Lorry#2,Dec05;2300 to send
Note on X46: grishinv: Lorry#2,Dec05
Note on X47: grishinv: Lorry#2,Dec05
Note on X48: grishinv: Lorry#2,Dec05;140 to send
Note on X49: grishinv: Lorry#2,Dec05; 150 to send
Note on X50: grishinv: Lorry#2,Dec05; 100 to send
Note on W11: grishinv: Must be checked in Protvino
Note on AH48: grishinv: Must be checked
Note on AD21: grishinv: Not agree with supply info!
Note on AD20: grishinv: Not agree with supply info?
Note on Y25: grishinv: Shipping#7: 100(-6) - cleaning in UK and must rewelding!
Note on K4: grishinv: 3799-50(GSNC)+100(LHC)+150(PS)
Note on K3: grishinv: 3799-50(GSNC)+100(LHC)+150(PS)
Note on AH21: grishinv: real in Protvino
Note on AH20: grishinv: real in Protvino
Note on J3: grishinv: 3799-50(GSNC)+100(LHC)+150(PS)
Note on J4: grishinv: 3799-50(GSNC)+100(LHC)+150(PS)
Note on AM59: grishinv: AB+297(UK)+515(Italy)
Note on AD60: grishinv: type 1764 + type 859 + type 435 + Which machining?
Note on C61: dehning: 1. 20 2. 7420
Note on J61: eholzer: subtract Aerovac heads (480)
Note on AD61: Claudine info 5.05.
Note on J63: eholzer: subtract Aerovac heads (480)
Note on O63: grishinv: No Itlay
Note on J64: eholzer: subtract Aerovac heads (480)
Note on O64: grishinv: No Italy
Note on P64: grishinv: 1004+5bad; + 5456
Note on J66: eholzer: subtract Aerovac heads (480)
Note on O66: grishinv: No Italy
Note on P66: grishinv: 1004+5bad; 12160 eholzer: wrong value! About 6120 have been sent for re-machining
Note on AD66: grishinv: 1700 - without modification of ext Dia 1375 -? ? - small box
Note on J67: eholzer: subtract Aerovac heads (480)
Note on O67: grishinv: No Italy
Note on P67: grishinv: 1508+5bad; 9150
Note on O68: grishinv: No Italy
Note on P68: grishinv: 1508+5bad; 9150
Note on Z38: grishinv: Must be checked?
Note on AK17: eholzer: must be at least 580 missing!
Note on AB61: eholzer: add 206 feed throughs which were sent back

## Tighteners
TIGHTENERS |  | Date of receiption | Pieces | Pieces |  |  | Pieces | Pieces |  |  |  |  | Date of arrived | Date of shipping
|  |  | type A | type B | type A | type B | type A | type B | type A | type B |  |  | by Slava
Counted
counted by
Barbara
Note on boxes
Malzaker
Slava
Mikhail
Shipping | week
|  | 12.12 | 200 | 100 | 200 | 100 | 200 | 100
|  | 20.01 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 1750 | 950
| 11 | 13.03 | 278 | 825 | 278 | 825 | 278 | 825 | 278 | 575 | 230 | 252 |  | 17.03 | Sh5
| 12 | 24.03 | 3279 | 676 | 3279 | 676 | 2995 | 676 | 3029 | 676 |  |  | 30.03
| 13 | 31.03 | 0 | 0 | 2995 | 1018 | 0 | 0 |  |  | 3557 | 1501 |  | 7.04 | Sh6
| 15 | 11.04 | 2000 | 1144 | 2000 | 1144 | 2000 | 1144 |  |  |  |  | 19.04
| 16 | 18.04 | 3000 | 558 | 3000 | 558 | 3250 | 558
| 17 | 28.04 | 1439 | 2270 | 1439 | 2270 | 1439 | 2520 | 9440 | 4704 | 8245 | 2720 | 5.05 | 29.05 | Sh7
| 23 | Summary (20.06) | 12196 | 5573 | 15191 | 6591 | 12162 | 5823 | 14497 | 6905 | 12032 | 4473
[11 empty] | 5057 | 2201
[10 empty] | Sh5&6 | 3787 | 1753
[11 empty] | 5557 | 2645
[11 empty] | 5757 | 1601
|  | In Protvino(29.06) | type A | type B
|  | Mikhail | 14497 | 6905 | Pcs
|  |  | 3624.25 | 3452.5 | IC
|  | ordered | 15400 | 7700

## Time to sending
| wed | th | fr | sat | sun | mon | tues | wed | thur | Fr | sat | sun | mon | tu | wed | th | fr
Ready | EDH Shipping Request | bar: mon to th
Price |  | Signed Shipping Request | bar: mon to th
CHF! |  |  | Call Packing Service | bar: mon to th
PS saw the Packages | bar: mon to th
Packing by PS | bar: mon to th
| to add | to add | to add |  |  | to add | !No add | PS & Brigitte ready to order Lorry |  | Fr: Brigitte sent e-mail; mon: Brigitte; fr: Lorry to Protvino
[7 empty] | Ex weight |  |  | Fr: to Ext Tranpsort Company; mon: have a answer
about Lorry
at Fr
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
7-10 days
| Att&Ann to | [17 empty] | FINAL:
| L.Evans | Signed
|  |  | Transfer to Protvino | [15 empty] | 24-27 days
IHEP sign
IHEP sign
IHEP sign
[7 empty] | Rus Custom |  |  | tu: Rus Custom
[7 empty] | ask to permit |  |  | tu: permit

## ceramics
CERAMICS
week | date "le Geneve" | Pieces | Checked by | arrived date |  | Per IC
1
2
4
5
5
6
8
9
10 |  | 200
11 |  | 770
12 |  | 0
13 |  | 0
14 | 3.04 | 1080 | Slava
15 |  | 0
16 | 18.04 | 576 | Slava | 19.04
17 |  | 0
18 |  | 0
19 | 9.05 | 688 | Slava | 10.05
20 | 16.05 | 645 | Slava
21 | 23.05 | 898 | Slava | 23.05 | Shipping8
21 | 26.05 | 480 | Slava | 3.06 | Shipping8
23 | 7.06 | 700 | Slava | 8.06 | Shipping9
24 | 12.06 | 689 | Slava | 14.06 | Shipping 9 |  | sum for sheet "BLM chambers" in loading zone
24 | 16.06 | 405 | Slava | 19.06 | Shipping 9
23 | Summary (8.06) | 7131 | Slava |  |  | 3565.5 | 2767
23 | Protvino | 5326 | Slava | with Shipping8 |  | 2663
| Protvino (11.05) | 2019 | Mikhail |  |  | 1009.5
23 | Protvino | 7094 | Mikhail | with Sh7,Sh8,Sh9 |  | 3547
30.6.2006 | tel convers with Mr.. Gagau
they have received the new contract and will deliver before 21.7.
from 21.7. holidays for 3 weeks

## Spacers
Spacer | [7 empty] | Per IC
| type | date of reception | quoted pieces | received by | counted pieces | counted by | week
January: | type A
47444 |  | pre-series | 9300 |  | 9170
February: |  |  | 0 |  | 103
52230 |  | 6.1.2006 | 14600 | EBH | 15824 | CC | 1
|  |  | 0 |  |  |  | 2
|  |  | 0 |  |  |  | 3
| 3rd delivery | 24.1.2006 | 10000 | EBH | 10000 | CC | 4
|  | 31.1.2006 | 10740 | EBH |  |  | 5
| 5th delivery | 03.2.2006 | 11170 | EBH |  |  | 5 |  | EBH: 17 pieces measured (add to count)
|  |  | 0 |  |  |  | 6
| 6th delivery | 14.2.2006 | 12730 | EBH |  |  | 7 |  | EBH: 22 pieces measured (add to count)
|  |  | 0 |  |  |  | 8
| 7th delivery | 28.2.2006 | 15100 | EBH |  |  | 9
March: | 8th delivery | 1.3.2006 | 13230 | EBH |  |  | 9 |  |  | 355355
| 9th delivery | 8.3.2006 | 15330 | EBH |  |  | 10 |  |  | 49910
| 10th delivry | 14.3.2006 | 18380 | EBH |  |  | 11 |  |  | 405265
| 11th delivery | 24.03.2006 | 25000 | Slava |  |  | 12
| 12th delivery | 30.03.2006 | 25000 | Slava |  |  | 13
April: | 13th delivery | 3.04.2006 | 25000 | Slava |  |  | 14
|  |  | 0 |  |  |  | 15
| 14th delivery | 19.04,2006 | 23075 | Slava |  |  | 16
| 15th delivery | 26.04.2006 | 21760 | Slava |  |  | 17
May: | 16th delivery | 5.05.2006 | 25000 | Slava |  |  | 18
| 17th delivery | 11.05.2006 | 25000 | Slava |  | 15.05-arrived | 19
| 18th delivery | 19.05.2006 | 25000 | Slava | Shipping8 | 22.05 - arrived | 20
|  |  | 0 |  |  |  | 21
| 19th | 29.05.2006 | 20160 | Slava | Shipping8 | 3.06 - arrived | 22
| 20th | 29.05.2006 | 12000 | Slava | Shipping8 | 3.06 - arrived | 22
June: | 21th | 05.06.2006 | 15250 | Slava | Shipping9 | 9.06 - arrived | 23
| 22th | 05.06.2006 | 9660 | Slava | Shipping9 | 9.06 - arrived | 23
| 23th | 12.06.2006 | 12400 | Slava | Shipping9 | 14.06 - arrived | 24
| 24th | 12.06.2006 | 12600 | Slava | Shipping9 | 14.06 - arrived | 24 |  |  | sum for sheet "BLM chambers" in loading zone
| 25th | 19.02.2006 | 13500 | Slava | Shipping9 | 21.06 - arrived | 25
| 26th | 19.02.2006 | 12000 | Slava | Shipping9 | 21.06 - arrived | 25
| 27th | 22.06.2006 | 10000 | Slava | Shipping9 | 26.06 - arrived | 26
| Summary |  | 442985 | Slava |  | 26.06 | 26 | 2420.6831 |  | 107070
Shipping9
| Protvino |  | 347244 | Slava | with Shipping8 |  |  | 1897.5082 |  | 15250
| Protvino | 11.05.2006 | 169859 | Mikhail |  |  |  | 928.1913 |  | 9660
| Protvino |  | 432264 | Mikhail | with Sh7,Sh8,Sh9 |  |  | 2362.0984 |  | 12400
12600
| type B | [8 empty] | 13500
|  | 6.1.2006 | 948 | EBH | 941 | CC |  |  |  | 12000
10000
85410
type C
|  | pre-series | 300 |  | 305
93
|  | 12.1.2006 | 606 | EBH
| 3rd delivery | 24.1.2006 | 10550 | EBH
| Suimmary |  | 10550
| Protvino |  | 10625 | Slava |  |  |  | 1770.8333
| Protvino |  | 10604 | Mikhail |  |  |  | 1767.3333