## IC components
Sub-System | per chamber | total needed quantity | ordered | ordered - needed | received | received-needed | shipped to Protvino / IC | To Order | Comments
3818 IC +318 SEM (+4% spares) |  | 4300 |  |  |  |  | 3768
LHCBLM__0001
tube inox 304L 483x88.9x2.0 LHCBLM__0040, IC | 1 | 3817.995 | 3800 | -17.995 | 4133 | 315.005 | 3773 | count
tube inox 304L 105x88.9x2 LHCBLM__0038 v.AB | 1 | 4136.145 | 4110 | -26.145 | 4271 | 134.855 | 3818 | count
Ceramics LHCBLM__0005 v.AC, IC | 2 | 7535.49 | 7110 | -425.49 | 200 | -7335.49 | 50 | option on additional pieces, contract | see extra slide
Al electrodes production LHCBLM__0004 0.5X82, IC | 61 | 232897.695 | 208020 | -24877.695 | 25000 | -207897.695 | 2254.0984 | option on additional pieces, contract
electrode spacer LHCBLM__0007 type A | 183 | 712070 | 698300 | -13770 | 112200 | -599870 | 293.6284 | follow up of addition to contract, critical | see extra slide
electrode spacer LHCBLM__0007 type C | 6 | 23249.88 | 22800 | -449.88 | 10948 | -12301.88 | 1768.3333 | follow up of addition to contract
bottom cover disk LHCBLM__0006 | 1 | 4136.145 | 4110 | -26.145 | 4430 | 293.855 | 4430 | count - new contract?
bottom cover spacer LHCBLM__0006 | 1 | 3817.995 | 3800 | -17.995 | 3800 | -17.995 | 3590 | count - new contract?
tighteners M4 LHCBLM__0016
type B Var 1 (incl. LHCBLM__0013) | 2 | 7635.99 | 7700 | 64.01 | 1100 | -6535.99 | 375 | follow up of addition to contract | see extra slide
type A Var 1 (incl. welded washer) | 4 | 15271.98 | 15400 | 128.02 | 2200 | -13071.98 | 438.5 | follow up of addition to contract | see extra slide
heads
50 IC heads (CNGS) | 1 | 50 | 50 | 0 | 50 | 0 | 5
500 IC heads (Aerovac) | 1 | 500 | 500 | 0 | 45 | -455 | 0 | critical contract
TIG welding of heads (IHEP and Italy) | 1 | 3583.395 | 0 | -3583.395 |  | -3583.395 |  | critical contract
small items
compressing spring 1.4310 ferroflex | 1 | 4136.145 | 3850 | -286.145 | 25kg | #VALUE! | 3780 | count
alumina tube D15/10, L=25mm | 2 | 8272.29 | 8220 | -52.29 | 8322 | 49.71 | 57.5 | count | all at CERN, packing
slotted screw M3x4, A2-ISO 1580 | 2 | 8272.29 | 8400 | 127.71 | 8400 | 127.71 | 4150
screw without head 6pc bt point.in.3x3 | 4 | 16544.58 | 16600 | 55.42 | 15400 | -1144.58 | 4100
spring washer D8/4.2-0.2, 1.4310 | 18 | 74450.61 | 75000 | 549.39 | 4500 | -69950.61 | 4061.1111 | count
nut M4-A4 ISO4032 | 12 | 49633.74 | 49634 | 0.26 | 0 | -49633.74 | 0 | follow up of order
cover assembly LHCBLM__0002
cover plate LHCBLM__0003, 316L | 1 | 3583.395 | 3610 | 26.605 | 2731 | -852.395 | 102 | follow up of addition to contract
feed throughs | 2 | 8272.29 | 7420 | -852.29 | 7406 | -866.29 | 102 | option on additional pieces, contract
cutting and anealing of copper tube | 1 | 4136.145 | ?? |  | 709 | -3427.145 | 112 | follow up, critical (production of heads) | this week some ???
cover spacer LHCBLM__0008 type A, 316L, IC | 2 | 7635.99 | 6500 | -1135.99 | 6460 | -1175.99 | 102 | new contract
protection tube LHCBLM__0010, 316L | 2 | 8272.29 | 7120 | -1152.29 | 7120 | -1152.29 | 102
welded spacer LHCBLM__0035, 304L | 3 | 12408.435 | 10680 | -1728.435 | 10658 | -1750.435 | 102
electrical connectors ass LHCBLM__0036
external plate LHCBLM__0037, manufacture | 1 | 4136.145 | 4110 | -26.145 | 4140 | 3.855 | 4090 | follow up of addition to contract
st steel sheet LHCBLM__0037, manufacture | 1 | 4136.145 | 4160 | 23.855 | 4160 | 23.855 | 4090 | follow up of addition to contract
tube AlMgSi hard 4*7 L=60 | 3 | 12408.435 | 780 MT |  | 52 | -12356.435 | 52 | follow up of tube cutting | 1500 on 15.3. ???
in.steel.thr.rods A4 316 M4 L=85 | 3 | 12408.435 | 12300 | -108.435 | 9000 | -3408.435 | 3176.6667 | count
hex.nuts inox A4 316 0.8D M4 | 6 | 24816.87 | 25000 | 183.13 | 25000 | 183.13 | 4000 | count
washer contact medium M4 | 3 | 12408.435 | 12400 | -8.435 | 12400 | -8.435 | 4133.3333
head.hex.point.scr. M3x5, inox | 1 | 4136.145 | 4200 | 63.855 | 4200 | 63.855 | 4200
BNC HT Polypenco SHV 5KV | 2 | 8272.29 | 8272 | -0.29 | 8272 | -0.29 | 4100
BNC 50ohm, teflon | 1 | 4136.145 | 4136 | -0.145 | 4136 | -0.145 | 4100
soldering lug, M4 | 1 | 4136.145 | 4200 | 63.855 | 4100 | -36.145 | 4100
soldering lug, BNC | 1 | 4136.145 | 4200 | 63.855 | 4200 | 63.855 | 4100
wires (L=100, 1.5mm2) | 0.15 | 620.4217 | 800 | 179.5783 | 800 | 179.5783 | 5333.3333
tinned cupper wires, without insulation, D=0.91mm | 0.1 | 413.6145 | 280 | -133.6145 | 280 | -133.6145 | 2800 | count
Resistor 10Mohm ,1W | 1 | 4136.145 | 4250 | 113.855 | 4250 | 113.855 | 4100
Capacitor (0.47uF, 2000V) | 1 | 4136.145 | 4273 | 136.855 | 4273 | 136.855 | 4100
Note on C9: eholzer: IC and SEM!!

## delivery schedule
Spacers | Weeks | Sum | Sum/IC
23900 | 1 | 23900 | 130.6011
0 | 2 | 23900 | 130.6011
0 | 3 | 23900 | 130.6011
10000 | 4 | 33900 | 185.2459
10740 | 5 | 44640 | 243.9344
11170 | 5 | 55810 | 304.9727
0 | 6 | 55810 | 304.9727
12730 | 7 | 68540 | 374.5355
0 | 8 | 68540 | 374.5355
15100 | 9 | 83640 | 457.0492
13230 | 9 | 96870 | 529.3443
15330 | 10 | 112200 | 613.1148
18380 | 11 | 130580 | 713.5519
25000 | 12 | 155580 | 850.1639
25000 | 13 | 180580 | 986.776
25000 | 14 | 205580 | 1123.388
0 | 15 | 205580 | 1123.388
23075 | 16 | 228655 | 1249.4809
21760 | 17 | 250415 | 1368.388
25000 | 18 | 275415 | 1505
25000 | 19 | 300415 | 1641.612
25000 | 20 | 325415 | 1778.224
0 | 21 | 325415 | 1778.224
20160 | 22 | 345575 | 1888.388
12000 | 22 | 357575 | 1953.9617
15250 | 23 | 372825 | 2037.2951
9660 | 23 | 382485 | 2090.082
12400 | 24 | 394885 | 2157.8415
12600 | 24 | 407485 | 2226.694
13500 | 25
12000 | 25
10000 | 26
29707 | 27
30850 | 28
Tightener
2200 | 8 | 2200 | 550
0 | 9 | 2200 | 550
0 | 10 | 2200 | 550
278 | 11 | 2478 | 619.5
2995 | 12 | 5473 | 1368.25
0 | 13 | 5473 | 1368.25
0 | 14 | 5473 | 1368.25
2000 | 15 | 7473 | 1868.25
3250 | 16 | 10723 | 2680.75
1439 | 17 | 12162 | 3040.5
Ceramics
200 | 10 | 200 | 100
770 | 11 | 970 | 485
0 | 12 | 970 | 485
0 | 13 | 970 | 485
1080 | 14 | 2050 | 1025
0 | 15 | 2050 | 1025
576 | 16 | 2626 | 1313
0 | 17 | 2626 | 1313
0 | 18 | 2626 | 1313
688 | 19 | 3314 | 1657
645 | 20 | 3959 | 1979.5
898 | 21 | 4857 | 2428.5
480 | 21 | 5337 | 2668.5
700 | 23 | 6037 | 3018.5
689 | 24 | 6726 | 3363