## SEM
Sub-System | Delivery by | DAI order # | per chamber | number SEM | spare SEM | total needed quantity | ordered | ordered by | ordered - needed | received | date of receiving first/next | received-needed
SEM |  |  |  | 350 | 70 | 420
tube inox 304L 109x88.9x2.0 LHCBLM__0040, SEM |  | 39.39.05.088.2 | 1 | 350 | 70 | 420
tube inox 304L 105x88.9x2 LHCBLM__0038 v.AB | el. box | 39.39.05.088.2 | 1 | 350 | 70 | 420
Al electrodes production LHCBLM__0004 0.5X82, SEM | Dutreive (F) | open | 2 | 700 | 140 | 840
electrode spacer LHCBLM__0007 type A, SEM | Flueckiger (CH) | CA1390364 +?? | 9 | 3150 | 630 | 3780 | OK
electrode spacer LHCBLM__0007 type B, SEM | Flueckiger (CH) | CA1390364 +?? | 3 | 1050 | 210 | 1260
bottom cover disk LHCBLM__0006 | RPM (I) | CA1390102+CA1392889 | 1 | 350 | 70 | 420 | OK
tighteners M4 LHCBLM__0016
type B Var 2 (incl. LHCBLM__0013 + 0016) | JCM (F) |  | 1 | 350 | 70 | 420
type A Var 2 (incl. welded washer) | JCM (F) |  | 2 | 700 | 140 | 840
type B Var 3 (incl. LHCBLM__0013 + 0016) | JCM (F) |  | 1 | 350 | 70 | 420
type A Var 3 (incl. welded washer) | JCM (F) |  | 2 | 700 | 140 | 840
NEG strip ST707 (30*0.2mm2) (units in m) | CERN Chiagato |  | 0.3 | 105 | 21 | 126 | 150 | BD
small items
screw without head 6pc bt point.in.3x3 | Bossard BN618 | 47.62.72.995.0 | 4 | 1400 | 280 | 1680 | OK
spring washer D8/4.2-0.2, 1.4310 | Bossard BN838 | 47.62.72.996.8 | 18 | 6300 | 1260 | 7560 | OK
nut M4-A4 ISO4032 |  | ?? | 12 | 4200 | 840 | 5040 | OK
cover assembly LHCBLM__0002
cover plate LHCBLM__0003, 316L | Dedecker (B) | CL1932975 +?? | 1 | 350 | 70 | 420
feed throughs | CERAMTEC (US) | 1889051/1937566 | 2 | 700 | 140 | 840
copper tube 10 x 8, L=120mm | CERN, MR 1887862 | 39.71.20.008.8 | 1 | 350 | 70 | 420 | OK
welded spacer LHCBLM__0035, 304L | Solpey (E) | CA1390217 | 3 | 1050 | 210 | 1260 | OK
st steel sheet LHCBLM__0037, manufacture | Cherokee (B) | CA1391433 | 1 | 350 | 70 | 420 | OK
tube AlMgSi hard 4*7 L=60 |  | 39.64.05.012.1 | 3 | 1050 | 210 | 1260 | OK
in.steel.thr.rods A4 316 M4 L=85 |  | 47.38.77.040.8 | 3 | 1050 | 210 | 1260 | OK
hex.nuts inox A4 316 0.8D M4 |  | 47.43.77.040.1-? | 6 | 2100 | 420 | 2520 | OK
washer contact medium M4 |  | 47.78.09.004.1 | 3 | 1050 | 210 | 1260 | OK
head.hex.point.scr. M3x5, inox |  | 47.62.96.101.1? | 1 | 350 | 70 | 420 | OK
BNC HT Polypenco SHV 5KV | CERN | 09.41.25.160.9 | 2 | 700 | 140 | 840 | OK
BNC 50ohm, teflon | CERN | 09.46.11.360.4 | 1 | 350 | 70 | 420 | OK
soldering lug, M4 | CERN | 04.76.26.448.1 | 1 | 350 | 70 | 420 | OK
soldering lug, BNC | CERN | 09.46.11.520.6 | 1 | 350 | 70 | 420 | OK
wires (L=100, 1.5mm2) | CERN | 04.01.61.900.1 | 0.15 | 52.5 | 10.5 | 63 | OK
tinned cupper wires, without insulation, D=0.91mm |  | 04.01.02.091.5 | 0.1 | 35 | 7 | 42 | OK
Resistor 10Mohm ,1W |  |  | 1 | 350 | 70 | 420 | OK
Capacitor (0.47uF, 2000V) |  |  | 1 | 350 | 70 | 420 | OK
SEM Ti electrode |  |  | 1 | 350 | 70 | 420 | SEM Ti electrode
Total | [5 empty] | 37611 |  |  | 0
Note on E3: eholzer: input field dehning: changed to 350 300806
Note on A17: grishinv: vis sans tete 6 p.cr.M3x3
Note on A18: grishinv: rondelle a plateau inox A2 M4
Note on A19: grishinv: ecrou hexagonal in.autofr.M4
Note on C22: dehning: 1. 20 2. 7420
Note on A27: grishinv: tige filetee in.4.A4 M 4x85 47.62.82.908.1
Note on A30: grishinv: vis sans tete 6 p.cr.in N3x5; 47.62.72.995.5
Note on B15: dehning: ordered per mail by Chigato, 290806