## IC inst
week11:10/03 |  | 15 | week |  |  | 13 |  |  |  | 15 | LHC Beam Loss installation | [10 empty] | 12 |  |  |  | 8 |  |  |  | 12 | [16 empty] | LHC Beam Loss installation
Cell | R 1 |  | L 2 |  | R 2 |  | L 3 |  | R 3 |  | L 4 |  | R 4 | clos | L 5 |  | R 5 | 5 | L 6 |  | R 6 |  | L 7 |  | R 7 |  | L 8 |  | R 8 |  | L 1 |  |  |  |  | Cell | R 1 |  | L 2 |  | R 2 |  | L 3 |  | R 3 |  | L 4 |  | R 4 |  | L 5 |  | R 5 |  | L 6 |  | R 6 |  | L 7 |  | R 7 |  | L 8 |  | R 8 |  | L 1
| IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S |  |  |  |  | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S
1 | [12 empty] | open |  |  |  | 6 | 1 | [8 empty] | 5 | 1 | 5 | 1 | 5 | 1 | 1 |  |  | 1 | 5 | 1 | 5 | 1 | 5 | 1 | [8 empty] | 6 | 1 | 6 | 1 | [8 empty] | 5 | 1 | 5 | 1 | 5 | 1 | 1
2 | [12 empty] | 11 | 21 |  |  | 6 | [5 empty] | week 7 no acces |  |  |  | 8 |  | 8 |  | 8 |  | 2 |  |  | 2 | 8 |  | 8 |  | 8 | [9 empty] | 6 |  | 6 | [9 empty] | 8 |  | 8 |  | 8 |  | 2
3 | [16 empty] | 6 |  |  |  | cntr |  |  |  | open |  | 5 |  | 5 |  | 5 |  | 3 |  |  | 3 | 5 |  | 5 |  | 5 | [9 empty] | 6 |  | 6 | [9 empty] | 5 |  | 5 |  | 5 |  | 3
4 | [6 empty] | 8 | 2 | 8 | 2 | 2 |  | 2 |  | 11 | 4 | 11 | 4 | 31 | 24 | 31 | 24 | 18 | 12 | 18 | 12 | 13 | 3 | 15 | 5 | 10 | 4 | 4 |  |  | 4 | 10 | 4 | 15 | 5 | 13 | 4 | 8 | 2 | 8 | 2 | 2 |  | 2 |  | 11 | 4 | 11 | 4 | 31 | 24 | 31 | 24 | 18 | 12 | 18 | 12 | 13 | 3 | 15 | 5 | 10 | 4 | 4
5 | [6 empty] | 14 | 8 | 14 | 8 | 8 |  | 8 |  | 7 | 1 | 7 | 1 | 11 | 3 | 11 | 3 | 20 | 14 | 10 | 7 | 6 |  | 6 |  | 7 | 1 | 5 |  |  | 5 | 7 | 1 | 6 |  | 6 |  | 14 | 8 | 14 | 8 | 8 |  | 8 |  | 7 | 1 | 7 | 1 | 11 | 3 | 11 | 3 | 20 | 14 | 20 | 14 | 6 |  | 6 |  | 7 | 1 | 5
6 | [6 empty] | 10 | 4 | 10 | 4 | 6 |  | 6 |  | 8 |  | 7 | [5 empty] | 27 | 21 |  |  | 7 | 1 | 12 | 6 | 6 |  | 6 |  |  | 6 | 6 |  | 12 | 6 | 7 | 1 | 10 | 4 | 10 | 4 | 6 |  | 6 |  | 8 |  | 7 | [5 empty] | 27 | 21 | 27 | 21 | 7 | 1 | 12 | 6 | 6 |  | 6
7 | [6 empty] | 12 | 1 | 7 | 1 | 6 |  | 6 |  | 6 |  | 6 | [5 empty] | 8 | 2 | 8 | 2 | 6 |  | 6 |  | 8 |  | 7 |  |  | 7 | 8 |  | 6 |  | 6 |  | 7 | 1 | 7 | 1 | 6 |  | 6 |  | 6 |  | 6 | [5 empty] | 8 | 2 | 8 | 2 | 6 |  | 6 |  | 8 |  | 7
8 | [6 empty] | 7 |  | 12 |  | 6 |  | 6 |  | 12 |  | 12 |  | 6 |  | 6 |  | 9 |  | 9 |  | 12 | 6 | 12 | 6 | 12 |  | 8 |  |  | 8 | 12 |  | 12 | 6 | 12 | 6 | 12 |  | 12 |  | 6 |  | 6 |  | 12 |  | 12 |  | 6 |  | 6 |  | 9 |  | 9 |  | 12 | 6 | 12 | 6 | 12 |  | 8
9 | [6 empty] | 21 |  | 21 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 16 |  | 16 |  | 6 |  | 6 |  | 6 |  | 9 |  |  | 9 | 6 |  | 6 |  | 6 |  | 21 |  | 21 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 16 |  | 16 |  | 6 |  | 6 |  | 6 |  | 9
10 | [6 empty] | 11 |  | 11 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 7 |  | 9 |  | 6 |  | 6 |  | 8 |  | 10 |  |  | 10 | 8 |  | 13 |  | 12 |  | 11 |  | 11 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 7 |  | 9 |  | 6 |  | 6 |  | 8 |  | 10
11 | [6 empty] | 19 |  | 19 |  | 6 |  | 6 |  | 13 |  | 13 |  | 6 |  | 6 |  | 19 |  | 19 |  | 12 | 6 | 12 | 6 | 16 |  | 11 |  |  | 11 | 17 |  | 12 | 6 | 12 | 6 | 19 |  | 19 |  | 6 |  | 6 |  | 13 |  | 13 |  | 6 |  | 6 |  | 19 |  | 19 |  | 12 | 6 | 12 | 6 | 16 |  | 11
12 |  |  | 8 |  | 8 |  | 10 |  | 10 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 12 |  |  | 12 | 6 |  | 8 |  | 8 |  | 10 |  | 10 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 12
13 | 8 |  | 6 |  | 6 |  | 10 |  | 10 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 7 |  | 8 |  | 6 |  | 6 |  | 8 |  | 13 |  |  | 13 | 8 |  | 6 |  | 6 |  | 10 |  | 10 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 8 |  | 13
14 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 14 |  |  | 14 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 14
15 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 15 |  |  | 15 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 15
16 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 16 |  |  | 16 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 16
17 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 17 |  |  | 17 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 17
18 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 18 |  |  | 18 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 18
19 |  |  |  |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 10 |  | 6 |  | 6 |  | 6 |  | 6 |  | 19 |  |  | 19 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 10 |  | 6 |  | 6 |  | 6 |  | 6 |  | 19
20 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 20 |  |  | 20 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 20
21 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 21 |  |  | 21 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 21
22 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 22 |  |  | 22 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 22
23 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 23 |  |  | 23 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 23
24 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 24 |  |  | 24 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 24
25 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 25 |  |  | 25 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 25
26 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 26 |  |  | 26 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 26
27 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 27 |  |  | 27 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 27
28 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 28 |  |  | 28 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 28
29 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 29 |  |  | 29 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 29
30 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 30 |  |  | 30 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 30
31 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 31 |  |  | 31 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 31
32 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 32 |  |  | 32 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 32
33 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 33 |  |  | 33 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 33
34 | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 | cntr |  |  | 6 |  |  |  | 6 |  |  |  | 34 |  |  | 34 | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 34
Dump | cntr | cntr | cntr | cntr | cntr | cntr | cntr | cntr | cntr | cntr | cntr | cntr | [6 empty] | 19 | 7 | 19 | 7 | cntr | cntr |  |  |  |  | cntr | cntr | cntr | cntr | Dump |  |  | Dump | [18 empty] | 19 | 7 | 19 | 7 | [10 empty] | Dump
IC inst | 128 |  | 128 |  | 140 |  | 242 |  | 248 |  | 178 |  | 184 |  | 205 |  | 228 |  | 217 |  | 223 |  | 261 |  | 229 |  | 218 |  | 231 |  | 225 |  | 3285 | 90.1729 | % | IC to inst | 232 |  | 234 |  | 232 |  | 242 |  | 248 |  | 178 |  | 184 |  | 223 |  | 228 |  | 217 |  | 223 |  | 262 |  | 266 |  | 218 |  | 231 |  | 225 |  | 3643
S inst |  | 0 |  | 0 |  | 0 |  | 15 |  | 15 |  | 0 |  | 0 |  | 5 |  | 6 |  | 34 |  | 34 |  | 49 |  | 21 |  | 17 |  | 24 |  | 6 | 226 | 74.5875 | % | S to inst |  | 6 |  | 24 |  | 18 |  | 15 |  | 15 |  | 0 |  | 0 |  | 6 |  | 6 |  | 34 |  | 34 |  | 49 |  | 49 |  | 17 |  | 24 |  | 6 | 303
IC to inst | 104 |  | 106 |  | 92 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18 |  | 0 |  | 0 |  | 0 |  | 1 |  | 37 |  | 0 |  | 0 |  | 0 |  | 358 | 9.8271 | % |  |  |  | 466 | 42 |  |  | 490 | 30 |  |  | 362 | 0 |  |  | 451 | 12 |  |  | 440 | 68 |  |  | 528 | 98 |  |  | 449 | 41 |  |  | 457 | 12
S to inst |  | 6 |  | 24 |  | 18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 28 |  | 0 |  | 0 |  | 0 | 77 | 25.4125 | %
|  | finished |  |  |  | on work |  |  |  | to be done |  |  |  |  | NO cover
Note on H26: ferioli: 2 IC dismounted + cablofil
Note on H9: ferioli: Connectors A5 not mounted
Note on I9: ferioli: connectors B5 not mounted
Note on K11: ferioli: A7 + SEM no connectors
Note on J11: ferioli: IC 7 no connectors IC 1 bad positin
Note on J16: ferioli: No cover
Note on J17: ferioli: No cover
Note on J18: ferioli: No cover
Note on J19: ferioli: NO cover
Note on J20: ferioli: No cover
Note on L15: ferioli: 2 IC dismounted + cablofil
Note on AF15: ferioli: 2 IC dismounted + cablofil
Note on AD15: ferioli: 1 IC dismounted + cablofil
Note on H15: ferioli: 1 IC dismounted + cablofil
Note on P37: ferioli: No power
Note on Q8: ferioli: SEM not installed
Note on Q9: ferioli: SEM not installed
Note on P6: ferioli: IC, cables, cablofil not installed
Note on P7: ferioli: IC, cables, cablofil not installed
Note on T39: ferioli: Position of 4 IC to be modif. Replace 2IC with 2 SEM
Note on V39: ferioli: Position of 4 IC to be modified Replace 2IC with 2 SEM
Note on V8: ferioli: Q4 modif on position IC5
Note on Y8: ferioli: HV cables not inst + cablofil NO SEM
Note on Y9: ferioli: HV cables not inst + cablofil NO SEM
Note on Y10: ferioli: HV cables not inst + cablofil IC in tunnel not fixed NO SEM
Note on AC5: ferioli: Sem not installed
Note on AC8: ferioli: Sem not installed
Note on AC10: ferioli: Sem not installed
Note on AC12: ferioli: Sem not installed
Note on AC15: ferioli: Sem not installed
Note on X8: ferioli: HV cables not inst + cablofi lIC in tunnel not fixed
Note on X9: ferioli: HV cables not inst + cablofil IC in tunnel not fixed
Note on X10: ferioli: Q6 ok HV cables not inst + cablofil IC in tunnel not fixed NO SEM
Note on X15: ferioli: 2 IC dismounted n:1, 5
Note on X16: ferioli: 1 IC dismounted
Note on X23: ferioli: 1 IC dismounted
Note on D16: ferioli: 2 IC dismounted + cablofil
Note on B17: ferioli: 2 IC dismounted n 7,8 + cablofil
Note on AB5: ferioli: IC, cables, cablofil to be mounted
Note on AB6: ferioli: IC, cables, cablofil to be mounted
Note on AB7: ferioli: IC, cables, cablofil to be mounted
Note on AF11: ferioli: IC n:6 position different from drawing
Note on AF24: ferioli: 1 IC dismounted n: 1
Note on AF25: ferioli: 1 IC dismounted n: 1
Note on X31: ferioli: 1 IC dismounted
Note on V15: ferioli: 1 IC dismounted
Note on Z8: ferioli: A4 OK HV cables not inst + cablofi lIC in tunnel not fixed
Note on AA8: ferioli: HV cables not inst + cablofil NO SEM