## 1-2
[6 empty] | Installation 1-2 | [12 empty] | 22/01/2008
|  |  |  | not finished |  |  |  | all work finished |  |  |  |  | Magnet open |  |  | Drawings OK |  |  | wrong
Sector 1-2 | Cell | Cell | Rack crate cover installed | Week 2008, when job was done | BL Position Marked | BL support | BL Cables support | BL Cables | IC to be installed | SEM to be installed | Numbers of BL Ionisation chamber or SEM installed | [5 empty] | BL Sig, HV, Fip, Power, Earth | BL 240 V | comments | "Arc leak Detection"(Paul, 21/01/2008)
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6
RIGHT 1 |  | 1 | [6 empty] | 5 | 1 | [9 empty] | w
|  | 2 | [6 empty] | 8 | [10 empty] | w
|  | 3 | [6 empty] | 4 | [10 empty] | w
|  | 4 | [6 empty] | 10 | 4
|  | 5 | [6 empty] | 6 | 1
|  | 6 | [6 empty] | 6
|  | 7 | [6 empty] | 7 | [10 empty] | n/a
|  | 8 | [6 empty] | 12 | [10 empty] | n/a
|  | 9 | [6 empty] | 6 | [10 empty] | n/a
|  | 10 | [6 empty] | 8 | [10 empty] | n/a
|  | 11 | [6 empty] | 16
| ARC | 12 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007
|  | 13 |  |  | 2007 |  |  |  | 8 | [8 empty] | 2007
|  | 14 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007
|  | 15 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007 |  | c'k
|  | 16 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007 |  | c'k
|  | 17 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007 |  | c'k
|  | 18 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007 |  | c'k
|  | 19 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007
|  | 20 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007
|  | 21 |  |  | 2007 |  |  |  | 6 | [8 empty] | 207
|  | 22 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007
|  | 23 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007
|  | 24 |  | 4 |  |  |  |  | 6 |  | 3957 | 2942 | 2981 | 2951 | 2968 | 3001 |  |  | V&V&Y
|  | 25 |  | 4 |  |  |  |  | 6 |  | 2923 | 3041 | 2932 | 2954 | 2961 | 3544 |  |  | V&V&Y
|  | 26 |  | 4 |  |  |  |  | 6 |  | 2988 | 3889 | 3482 | 3481 | 3868 | 3542 |  |  | V&V&Y
|  | 27 |  | 4 |  |  |  |  | 6 |  | 3012 | 3043 | 3021 | 3017 | 3888 | 2995 |  |  | Victor &Vladimir
|  | 28 |  | 4 |  |  |  |  | 6 |  | 3397 | 3309 | 3087 | 3389 | 3328 | 2976 |  |  | Victor &Vladimir
|  | 29 |  | 4 |  |  |  |  | 6 |  | 3348 | 4012 | 3322 | 3307 | 2908 | 3394 |  |  | Victor &Vladimir
|  | 30 |  | 4 |  |  |  |  | 6 |  | 3025 | 2931 | 3355 | 3929 | 3436 | 3418 |  |  | Victor &Vladimir
|  | 31 |  | 4 |  |  |  |  | 6 |  | 2911 | 3380 | 3995 | 3344 | 3061 | 3396 |  |  | Victor &Vladimir
|  | 32 |  | 4 |  |  |  |  | 6 |  | 3056 | 3053 | 3451 | 3417 | 3390 | 2992 |  |  | Victor &Vladimir
|  | 33 |  | 4 |  |  |  |  | 6 |  | 3476 | 2934 | 3018 | 3405 | 3076 | 1181 |  |  | Sasha&Revaliy
|  | 34 |  | 4 |  |  |  |  | 6 |  | 2975 | 2993 | 3459 | 2939 | 2967 | 3407 |  |  | Victor &Vladimir
Left 2 | ARC | 33 |  | 4 |  |  |  |  | 6 |  | 3466 | 3961 | 3081 | 3404 | 3432 | 3428 |  |  | Sasha&Revaliy
|  | 32 |  | 3 |  |  |  |  | 6 |  | 3877 | 3411 | 3440 | 4000 | 2997 | 3991 |  |  | Victor &Vladimir
|  | 31 |  | 3 |  |  |  |  | 6 |  | 3924 | 2963 | 3941 | 2948 | 2970 | 3250 |  |  | Sasha&Revaliy
|  | 30 |  | 3 |  |  |  |  | 6 |  | 3381 | 3395 | 2958 | 3962 | 2982 | 2947 |  |  | Victor &Vladimir
|  | 29 |  | 3 |  |  |  |  | 6 |  | 2941 | 2940 | 3337 | 1170 | 3976 | 2978 |  |  | Victor &Vladimir
|  | 28 |  | 3 |  |  |  |  | 6 |  | 3427 | 2927 | 3902 | 3433 | 3911 | 3937 |  |  | Victor &Vladimir
|  | 27 |  | 3 | Victor &Vladimir |  |  |  | 6 |  | 3334 | 2936 | 2986 | 2950 | 2973 | 3306 |  |  | Victor &Vladimir
|  | 26 |  | 3 |  |  |  |  | 6 |  | 3409 | 2964 | 3443 | 2937 | 2974 | 3420 |  |  | Victor &Vladimir
|  | 25 |  | 3 |  |  |  |  | 6 |  | 3435 | 4003 | 3473 | 3415 | 3487 | 3450 |  |  | Victor &Vladimir
|  | 24 |  | 3 |  |  |  |  | 6 |  | 3810 | 3895 | 3830 | 3832 | 3825 | 3884 |  |  | Victor &Vladimir
|  | 23 |  | 3 | Sasha&Revaliy |  |  |  | 6 |  | 3892 | 3849 | 3898 | 3874 | 3872 | 3809 |  |  | Sasha&Revaliy
|  | 22 |  | 3 |  |  |  |  | 6 |  | 3326 | 3913 | 2922 | 3316 | 3431 | 3336 |  |  | Victor &Vladimir | v2
|  | 21 |  | 3 |  |  |  |  | 6 |  | 1577 | 3993 | 3452 | 3441 | 246 | 3471 |  |  | Victor &Vladimir | v2
|  | 20 |  | 3 |  |  |  |  | 6 |  | 3873 | 3905 | 3971 | 3398 | 3847 | 3399 |  |  | Sasha&Revaliy | v2
|  | 19 |  | 3 |  |  |  |  | 6 | [8 empty] | No | Open | v2
|  | 18 |  | 3 |  |  |  |  | 6 |  | 3447 | 3004 | 3100 | 3445 | 3107 | 2967 |  |  | Sasha&Revaliy
|  | 17 |  | 3 |  |  |  |  | 6 |  | 3375 | 3080 | 2984 | 2994 | 3430 | 3403 |  |  | Victor &Vladimir
|  | 16 |  | 3 |  |  |  |  | 6 |  | 3341 | 3401 | 3997 | 3335 | 3750 | 3963 |  |  | Victor &Vladimir
|  | 15 |  | 4 |  |  |  |  | 6 |  | 3383 | 3368 | 3413 | 3965 | 3365 | 3852 |  |  | V&V&Y
|  | 14 |  | 3 |  |  |  |  | 6 |  | 3429 | 3410 | 1167 | 3770 | 3882 | 2998 |  |  | Victor &Vladimir
|  | 13 |  | 3 |  |  |  |  | 6 |  | 3008 | 3814 | 3049 | 3856 | 3423 | 2935 |  |  | Sasha&Revaliy
|  | 12! |  | 3 |  |  |  |  | 8 |  | 3480 | 3899 | 3887 | 3819 | 3879 | 3869
|  | 11 | [6 empty] | 12 | 6
|  | 10 | [6 empty] | 13
|  | 9 | [6 empty] | 6
|  | 8 | [6 empty] | 12 | 6
|  | 7 | [6 empty] | 6
|  | 6 | [6 empty] | 12 | 6
|  | 5 | [6 empty] | 6
|  | 4 | [6 empty] | 15 | 5
|  | 3 | [6 empty] | 4
|  | 2 | [6 empty] | 8
|  | 1 | [6 empty] | 5 | 1
Sum to be installed | [8 empty] | 227 | 24
To be installed (Franco) | [8 empty] | 222+12 | 24
Note on U54: cruikshank: Leak at level gauge does not allow subsector to be pumped. Level gauge bellows repaired. Cold mass validated with residual of 2.2 e-7 mbarl/s on 26/11/07. During venting of V2 beam vacuum in Nov/Dec 2007, total pressure rise in insulation vacuum subsector A19R1 observed. Check of QA records showed that V1 & V2 beam vac from Q19R1 to Q23R1 had not been leak test (ie PIMs). All interceonnects reopened. Leak testing showed a few minor leak ~ e-9 mbarl/s but not the expected large communication between vacua. Subsector to be reclosed, and localisation tests made with helium injection into the insulation vacuum and leak detectors on beam vacuum at Q19 and Q23R1
Note on U55: cruikshank: Leak at level gauge does not allow subsector to be pumped. Level gauge bellows repaired. Cold mass validated with residual of 2.2 e-7 mbarl/s on 26/11/07. During venting of V2 beam vacuum in Nov/Dec 2007, total pressure rise in insulation vacuum subsector A19R1 observed. Check of QA records showed that V1 & V2 beam vac from Q19R1 to Q23R1 had not been leak test (ie PIMs). All interceonnects reopened. Leak testing showed a few minor leak ~ e-9 mbarl/s but not the expected large communication between vacua. Subsector to be reclosed, and localisation tests made with helium injection into the insulation vacuum and leak detectors on beam vacuum at Q19 and Q23R1
Note on U56: cruikshank: Leak at level gauge does not allow subsector to be pumped. Level gauge bellows repaired. Cold mass validated with residual of 2.2 e-7 mbarl/s on 26/11/07. During venting of V2 beam vacuum in Nov/Dec 2007, total pressure rise in insulation vacuum subsector A19R1 observed. Check of QA records showed that V1 & V2 beam vac from Q19R1 to Q23R1 had not been leak test (ie PIMs). All interceonnects reopened. Leak testing showed a few minor leak ~ e-9 mbarl/s but not the expected large communication between vacua. Subsector to be reclosed, and localisation tests made with helium injection into the insulation vacuum and leak detectors on beam vacuum at Q19 and Q23R1
Note on U57: cruikshank: Leak at level gauge does not allow subsector to be pumped. Level gauge bellows repaired. Cold mass validated with residual of 2.2 e-7 mbarl/s on 26/11/07. During venting of V2 beam vacuum in Nov/Dec 2007, total pressure rise in insulation vacuum subsector A19R1 observed. Check of QA records showed that V1 & V2 beam vac from Q19R1 to Q23R1 had not been leak test (ie PIMs). All interceonnects reopened. Leak testing showed a few minor leak ~ e-9 mbarl/s but not the expected large communication between vacua. Subsector to be reclosed, and localisation tests made with helium injection into the insulation vacuum and leak detectors on beam vacuum at Q19 and Q23R1
Note on U8: cruikshank: Envelope leak
Note on U9: cruikshank: Envelope leak
Note on U10: cruikshank: Envelope leak
Note on U14: cruikshank:
Note on U15: cruikshank:
Note on U16: cruikshank:
Note on U17: cruikshank:
Note on U18: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual
Note on U19: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual
Note on U20: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual
Note on U21: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual
Note on U22: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired. Leak ~e-3 mbarl/s after pressure test. Localised to QQBI.19L2 at beam screen F collector V1. To be repaired by P. Garritty. Weld repair made week 2. Awaiting QUI sleeve installation at P2 to pressurise c'k to 3 bar.
Note on U23: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired. Leak ~e-3 mbarl/s after pressure test. Localised to QQBI.19L2 at beam screen F collector V1. To be repaired by P. Garritty. Weld repair made week 2. Awaiting QUI sleeve installation at P2 to pressurise c'k to 3 bar.
Note on U24: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired. Leak ~e-3 mbarl/s after pressure test. Localised to QQBI.19L2 at beam screen F collector V1. To be repaired by P. Garritty. Weld repair made week 2. Awaiting QUI sleeve installation at P2 to pressurise c'k to 3 bar.
Note on U25: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired. Leak ~e-3 mbarl/s after pressure test. Localised to QQBI.19L2 at beam screen F collector V1. To be repaired by P. Garritty. Weld repair made week 2. Awaiting QUI sleeve installation at P2 to pressurise c'k to 3 bar.
Note on U26: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U27: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U28: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U29: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U30: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U31: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U32: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U33: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U34: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U35: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U36: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U37: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U38: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U39: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U40: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired
Note on U41: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired