## 1-2
[6 empty] | Installation 1-2 | [12 empty] | 25/01/2008
|  |  |  | not finished |  |  |  | all work finished |  |  |  |  | Magnet open |  |  | Drawings OK |  |  | wrong
Sector 1-2 | Cell | Cell | Rack crate cover installed | Week 2008, when job was done | BL Position Marked | BL support | BL Cables support | BL Cables | IC to be installed | SEM to be installed | Numbers of BL Ionisation chamber or SEM installed | [5 empty] | BL Sig, HV, Fip, Power, Earth | BL 240 V | comments | "Arc leak Detection"(Paul, 24/01/2008)
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6
RIGHT 1 |  | 1 | [6 empty] | 5 | 1
|  | 2 | [6 empty] | 8
|  | 3 | [6 empty] | 4
|  | 4 | [6 empty] | 10 | 4 | [9 empty] | w
|  | 5 | [6 empty] | 6 | 1
|  | 6 | [6 empty] | 6
|  | 7 | [6 empty] | 7
|  | 8 | [6 empty] | 12
|  | 9 | [6 empty] | 6
|  | 10 | [6 empty] | 8
|  | 11 | [6 empty] | 16
| ARC | 12 | [6 empty] | 6 | [8 empty] | 2007
|  | 13 | [6 empty] | 8 | Add 2 IC to 6 installed | 3881 | 3886 | 3923 | 3013 | 3904 | 2854 |  | 2008!!! | No 240V,no interconnection, no power cable, no position
|  | 14 |  | 4 |  |  |  |  | 6 |  | 3900 | 4005 | 3848 | 3897 | 2996 | 3885
|  | 15 |  | 4 |  |  |  |  | 6 |  | 3000 | 3982 | 3525 | 2977 | 3876 | 3870 |  |  |  | level
|  | 16 |  | 4 |  |  |  |  | 6 |  | 2933 | 3891 | 3855 | 3850 | 3490 | 2945 |  |  |  | level
|  | 17 |  | 4 |  |  |  |  | 6 |  | 3917 | 3908 | 3894 | 2972 | 3919 | 3833 |  |  |  | level
|  | 18 |  | 4 |  |  |  |  | 6 |  | 3999 | 3836 | 3022 | 3920 | 3858 | 3922 |  |  |  | level
|  | 19 |  |  | 2007 |  |  |  | 6 | [8 empty] | 2007 | Not MARKED:24/01/08 | v2
|  | 20 |  | 4 |  |  |  |  | 6 |  | 2983 | 2946 | 2906 | 2985 | 2965 | 2947 |  |  |  | v2
|  | 21 |  | 4 |  |  |  |  | 6 |  | 2938 | 2944 | 2957 | 2952 | 3011 | 2909 |  | 2008 | No 240 V! | v2
|  | 22 |  | 4 |  |  |  |  | 6 |  | 2930 | 2916 | 2980 | 1310 | 2989 | 3221 |  |  |  | v2
|  | 23 |  | 4 |  |  |  |  | 6 |  | 1093 | 3030 | 2956 | 2959 | 3003 | 3026 |  | 2008 | No 240 V! | level
|  | 24 |  | 4 |  |  |  |  | 6 |  | 3957 | 2942 | 2981 | 2951 | 2968 | 3001 |  |  | V&V&Y | level
|  | 25 |  | 4 |  |  |  |  | 6 |  | 2923 | 3041 | 2932 | 2954 | 2961 | 3544 |  |  | V&V&Y | level
|  | 26 |  | 4 |  |  |  |  | 6 |  | 2988 | 3889 | 3482 | 3481 | 3868 | 3542 |  |  | V&V&Y | level
|  | 27 |  | 4 |  |  |  |  | 6 |  | 3012 | 3043 | 3021 | 3017 | 3888 | 2995 |  |  | Victor &Vladimir
|  | 28 |  | 4 |  |  |  |  | 6 |  | 3397 | 3309 | 3087 | 3389 | 3328 | 2976 |  |  | Victor &Vladimir
|  | 29 |  | 4 |  |  |  |  | 6 |  | 3348 | 4012 | 3322 | 3307 | 2908 | 3394 |  |  | Victor &Vladimir
|  | 30 |  | 4 |  |  |  |  | 6 |  | 3025 | 2931 | 3355 | 3929 | 3436 | 3418 |  |  | Victor &Vladimir
|  | 31 |  | 4 |  |  |  |  | 6 |  | 2911 | 3380 | 3995 | 3344 | 3061 | 3396 |  |  | Victor &Vladimir | level
|  | 32 |  | 4 |  |  |  |  | 6 |  | 3056 | 3053 | 3451 | 3417 | 3390 | 2992 |  |  | Victor &Vladimir | level
|  | 33 |  | 4 |  |  |  |  | 6 |  | 3476 | 2934 | 3018 | 3405 | 3076 | 1181 |  |  | Sasha&Revaliy | level
|  | 34 |  | 4 |  |  |  |  | 6 |  | 2975 | 2993 | 3459 | 2939 | 2967 | 3407 |  |  | Victor &Vladimir | level
Left 2 | ARC | 33 |  | 4 |  |  |  |  | 6 |  | 3466 | 3961 | 3081 | 3404 | 3432 | 3428 |  |  | Sasha&Revaliy
|  | 32 |  | 3 |  |  |  |  | 6 |  | 3877 | 3411 | 3440 | 4000 | 2997 | 3991 |  |  | Victor &Vladimir
|  | 31 |  | 3 |  |  |  |  | 6 |  | 3924 | 2963 | 3941 | 2948 | 2970 | 3250 |  |  | Sasha&Revaliy
|  | 30 |  | 3 |  |  |  |  | 6 |  | 3381 | 3395 | 2958 | 3962 | 2982 | 2947 |  |  | Victor &Vladimir | level
|  | 29 |  | 3 |  |  |  |  | 6 |  | 2941 | 2940 | 3337 | 1170 | 3976 | 2978 |  |  | Victor &Vladimir | level
|  | 28 |  | 3 |  |  |  |  | 6 |  | 3427 | 2927 | 3902 | 3433 | 3911 | 3937 |  |  | Victor &Vladimir | level
|  | 27 |  | 3 | Victor &Vladimir |  |  |  | 6 |  | 3334 | 2936 | 2986 | 2950 | 2973 | 3306 |  |  | Victor &Vladimir | level
|  | 26 |  | 3 |  |  |  |  | 6 |  | 3409 | 2964 | 3443 | 2937 | 2974 | 3420 |  |  | Victor &Vladimir | level
|  | 25 |  | 3 |  |  |  |  | 6 |  | 3435 | 4003 | 3473 | 3415 | 3487 | 3450 |  |  | Victor &Vladimir | level
|  | 24 |  | 3 |  |  |  |  | 6 |  | 3810 | 3895 | 3830 | 3832 | 3825 | 3884 |  |  | Victor &Vladimir | level
|  | 23 |  | 3 | Sasha&Revaliy |  |  |  | 6 |  | 3892 | 3849 | 3898 | 3874 | 3872 | 3809 |  |  | Sasha&Revaliy | level
|  | 22 |  | 3 |  |  |  |  | 6 |  | 3326 | 3913 | 2922 | 3316 | 3431 | 3336 |  |  | Victor &Vladimir | level
|  | 21 |  | 3 |  |  |  |  | 6 |  | 1577 | 3993 | 3452 | 3441 | 246 | 3471 |  |  | Victor &Vladimir | level
|  | 20 |  | 3 |  |  |  |  | 6 |  | 3873 | 3905 | 3971 | 3398 | 3847 | 3399 |  |  | Sasha&Revaliy | level
|  | 19 |  | 3 |  |  |  |  | 6 | [8 empty] | No | Open | level
|  | 18 |  | 3 |  |  |  |  | 6 |  | 3447 | 3004 | 3100 | 3445 | 3107 | 2967 |  |  | Sasha&Revaliy | c'k
|  | 17 |  | 3 |  |  |  |  | 6 |  | 3375 | 3080 | 2984 | 2994 | 3430 | 3403 |  |  | Victor &Vladimir | c'k
|  | 16 |  | 3 |  |  |  |  | 6 |  | 3341 | 3401 | 3997 | 3335 | 3750 | 3963 |  |  | Victor &Vladimir | c'k
|  | 15 |  | 4 |  |  |  |  | 6 |  | 3383 | 3368 | 3413 | 3965 | 3365 | 3852 |  |  | V&V&Y | c'k
|  | 14 |  | 3 |  |  |  |  | 6 |  | 3429 | 3410 | 1167 | 3770 | 3882 | 2998 |  |  | Victor &Vladimir | level
|  | 13 |  | 3 |  |  |  |  | 6 |  | 3008 | 3814 | 3049 | 3856 | 3423 | 2935 |  |  | Sasha&Revaliy | level
|  | 12! |  | 3 |  |  |  |  | 8 |  | 3480 | 3899 | 3887 | 3819 | 3879 | 3869 |  |  |  | level
|  | 11 | [6 empty] | 12 | 6 | [9 empty] | level
|  | 10 | [6 empty] | 13
|  | 9 | [6 empty] | 6
|  | 8 | [6 empty] | 12 | 6
|  | 7 | [6 empty] | 6
|  | 6 | [6 empty] | 12 | 6
|  | 5 | [6 empty] | 6
|  | 4 | [6 empty] | 15 | 5
|  | 3 | [6 empty] | 4 | [10 empty] | w
|  | 2 | [6 empty] | 8 | [10 empty] | w
|  | 1 | [6 empty] | 5 | 1 | [9 empty] | w
Sum to be installed | [8 empty] | 227 | 24
To be installed (Franco) | [8 empty] | 222+12 | 24
Note on U8: cruikshank: Vented to repair PIM at q2/Q3. Repumped. Pressure test of cold mass 22/1/08. Validated 23/1/08
Note on U9: cruikshank: Vented to repair PIM at q2/Q3. Repumped. Pressure test of cold mass 22/1/08. Validated 23/1/08
Note on U10: cruikshank: Vented to repair PIM at q2/Q3. Repumped. Pressure test of cold mass 22/1/08. Validated 23/1/08
Note on U11: cruikshank: Envelope leak on safety valve wk4, 2008
Note on U14: cruikshank: cold mass validated with residual of 3.8 e-9 mbarl/s on 26/11/07.
Note on U15: cruikshank: cold mass validated with residual of 3.8 e-9 mbarl/s on 26/11/07.
Note on U16: cruikshank: cold mass validated with residual of 3.8 e-9 mbarl/s on 26/11/07.
Note on U17: cruikshank: cold mass validated with residual of 3.8 e-9 mbarl/s on 26/11/07.
Note on U18: cruikshank: cold mass validated with residual of 3.8 e-9 mbarl/s on 26/11/07.
Note on U19: cruikshank: cold mass validated with residual of 3.8 e-9 mbarl/s on 26/11/07.
Note on U20: cruikshank: cold mass validated with residual of 3.8 e-9 mbarl/s on 26/11/07.
Note on U21: cruikshank: cold mass validated with residual of 3.8 e-9 mbarl/s on 26/11/07.
Note on U22: cruikshank: Cold mass validated 7/11/07.
Note on U23: cruikshank: Cold mass validated 7/11/07.
Note on U24: cruikshank: Cold mass validated 7/11/07.
Note on U25: cruikshank: Cold mass validated 7/11/07.
Note on U26: cruikshank: Leak at level gauge does not allow subsector to be pumped. Level gauge bellows repaired. Cold mass validated with residual of 2.2 e-7 mbarl/s on 26/11/07. During venting of V2 beam vacuum in Nov/Dec 2007, total pressure rise in insulation vacuum subsector A19R1 observed. Check of QA records showed that V1 & V2 beam vac from Q19R1 to Q23R1 had not been leak test (ie PIMs). All interceonnects reopened. Leak testing showed a few minor leak ~ e-9 mbarl/s but not the expected large communication between vacua. Subsector to be reclosed, and localisation tests made with helium injection into the insulation vacuum and leak detectors on beam vacuum at Q19 and Q23R1
Note on U27: cruikshank: Leak at level gauge does not allow subsector to be pumped. Level gauge bellows repaired. Cold mass validated with residual of 2.2 e-7 mbarl/s on 26/11/07. During venting of V2 beam vacuum in Nov/Dec 2007, total pressure rise in insulation vacuum subsector A19R1 observed. Check of QA records showed that V1 & V2 beam vac from Q19R1 to Q23R1 had not been leak test (ie PIMs). All interceonnects reopened. Leak testing showed a few minor leak ~ e-9 mbarl/s but not the expected large communication between vacua. Subsector to be reclosed, and localisation tests made with helium injection into the insulation vacuum and leak detectors on beam vacuum at Q19 and Q23R1
Note on U28: cruikshank: Leak at level gauge does not allow subsector to be pumped. Level gauge bellows repaired. Cold mass validated with residual of 2.2 e-7 mbarl/s on 26/11/07. During venting of V2 beam vacuum in Nov/Dec 2007, total pressure rise in insulation vacuum subsector A19R1 observed. Check of QA records showed that V1 & V2 beam vac from Q19R1 to Q23R1 had not been leak test (ie PIMs). All interceonnects reopened. Leak testing showed a few minor leak ~ e-9 mbarl/s but not the expected large communication between vacua. Subsector to be reclosed, and localisation tests made with helium injection into the insulation vacuum and leak detectors on beam vacuum at Q19 and Q23R1
Note on U29: cruikshank: Leak at level gauge does not allow subsector to be pumped. Level gauge bellows repaired. Cold mass validated with residual of 2.2 e-7 mbarl/s on 26/11/07. During venting of V2 beam vacuum in Nov/Dec 2007, total pressure rise in insulation vacuum subsector A19R1 observed. Check of QA records showed that V1 & V2 beam vac from Q19R1 to Q23R1 had not been leak test (ie PIMs). All interceonnects reopened. Leak testing showed a few minor leak ~ e-9 mbarl/s but not the expected large communication between vacua. Subsector to be reclosed, and localisation tests made with helium injection into the insulation vacuum and leak detectors on beam vacuum at Q19 and Q23R1
Note on U30: cruikshank: on turbo 5/11/07 validated 2 e-7 mbarl/s residual. Level gauge repaired
Note on U31: cruikshank: on turbo 5/11/07 validated 2 e-7 mbarl/s residual. Level gauge repaired
Note on U32: cruikshank: on turbo 5/11/07 validated 2 e-7 mbarl/s residual. Level gauge repaired
Note on U33: cruikshank: on turbo 5/11/07 validated 2 e-7 mbarl/s residual. Level gauge repaired
Note on U34: cruikshank: evacuation blocked at 4 mbar. Leak due to damage at SSS level. Cold mass validated with residual of 7.1 e-8 mbarl/s on 26/11/07
Note on U35: cruikshank: evacuation blocked at 4 mbar. Leak due to damage at SSS level. Cold mass validated with residual of 7.1 e-8 mbarl/s on 26/11/07
Note on U36: cruikshank: evacuation blocked at 4 mbar. Leak due to damage at SSS level. Cold mass validated with residual of 7.1 e-8 mbarl/s on 26/11/07
Note on U37: cruikshank: evacuation blocked at 4 mbar. Leak due to damage at SSS level. Cold mass validated with residual of 7.1 e-8 mbarl/s on 26/11/07
Note on U38: cruikshank: by-pass turbo problem at < 80%. Cold mass validated 7/11/07.
Note on U39: cruikshank: by-pass turbo problem at < 80%. Cold mass validated 7/11/07.
Note on U40: cruikshank: by-pass turbo problem at < 80%. Cold mass validated 7/11/07.
Note on U41: cruikshank: by-pass turbo problem at < 80%. Cold mass validated 7/11/07.
Note on U73: cruikshank: Envelope leak at DFBX connector. Awaiting repair by J.Kerby wk 4,2008
Note on U74: cruikshank: Envelope leak at DFBX connector. Awaiting repair by J.Kerby wk 4,2008
Note on U75: cruikshank: Envelope leak at DFBX connector. Awaiting repair by J.Kerby wk 4,2008
Note on U62: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual
Note on U63: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual
Note on U64: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual
Note on U65: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual
Note on U58: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired. Leak ~e-3 mbarl/s after pressure test. Localised to QQBI.19L2 at beam screen F collector V1. To be repaired by P. Garritty. Weld repair made week 2. Awaiting QUI sleeve installation at P2 to pressurise c'k to 3 bar.
Note on U59: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired. Leak ~e-3 mbarl/s after pressure test. Localised to QQBI.19L2 at beam screen F collector V1. To be repaired by P. Garritty. Weld repair made week 2. Awaiting QUI sleeve installation at P2 to pressurise c'k to 3 bar.
Note on U60: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired. Leak ~e-3 mbarl/s after pressure test. Localised to QQBI.19L2 at beam screen F collector V1. To be repaired by P. Garritty. Weld repair made week 2. Awaiting QUI sleeve installation at P2 to pressurise c'k to 3 bar.
Note on U61: cruikshank: cold mass validated 9/11/07 at 2 e-8 mbarl/s residual. Level gauge repaired. Leak ~e-3 mbarl/s after pressure test. Localised to QQBI.19L2 at beam screen F collector V1. To be repaired by P. Garritty. Weld repair made week 2. Awaiting QUI sleeve installation at P2 to pressurise c'k to 3 bar.
Note on U46: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U47: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U48: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U49: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U50: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U51: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U52: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U53: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U54: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U55: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U56: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U57: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07.Level gauge repaired
Note on U43: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07 Level gauge repaired
Note on U44: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07 Level gauge repaired
Note on U45: cruikshank: Put on turbo pumping 5/11/07. Cold mass validated 7/11/07 Level gauge repaired