## Sheet1
Results |  | Comments:
11/03/2016 (today)
| Reset of cards and check of channels in IP6, 5, 2, and 1 | IP2 and 1 not complete; 5 cards remain
Global Reset of statuses
Force reprogram of all surface electronics
Generate all settings and drive
| First check of interlocks | firmware version has not been updated; Done needs genrate and drive -> Monday
12-13/03/2016 (weekend):
Quiet period to acquire data for noise analysis
First check of non-conformities from the UPS test
14/03/2016 (Mon):
Generate all settings and drive
Check of interlocks
| Reset of cards and check of channels in IP2, and 1 | If all goes well should be the end. | all cards have been reset
Check once more if new status errors recorded over the weekend
| Start correction/cleaning of fibre channels that have few errors per day | 5 links already known in various IPs | TC card number 11 in 8R need to be exchanged
Check thermalized racks in SR8 (temperature too high)
Automatic check of non-conformities from the UPS test
(Overnight) initiate loops for modulation (aim to make more than 100)
15/03/2016 (Tue):
Synchronise LAYOUT to LSA
Check propagation of all the name and DCUM changes
Check new channels become available
Request CO to update all Logging variables affected and create the new ones
(cont) fibre and status checks and corrections
(Overnight) initiate loops for modulation (aim to make more than 100)
16/03/2016 (Wed):
Add the new channels to families and generate monitor factors
Global generation of setting and drive
(Overnight) initiate loops for modulation (aim to make more than 100)
17/03/2016 (Thu):
Analysis and calculation of limits
Check once more if new status errors recorded over the week
18/03/2016 (Fri):
Upload modulation limits
Global generation of settings and drive
Execute Modulations from CCC (Sequencer)
Execute Sanity Checks from CCC (Sequencer)
Check interlocks