## Tunnel Inst 2006 2007
04.10.06 | [16 empty] | Beam Loss LHC installation planning
(7-8 and 8-1 uptodate)
SECTOR |  |  |  |  | 7 - 8 |  |  | 8 - 1 |  |  | 4 - 5 |  |  | 3 - 4 |  |  |  | 5 - 6 |  |  | 6 - 7 |  |  | 2 - 3 |  |  | 1 - 2 | [9 empty] | hours
[29 empty] | IHEP ionisation @ CERN | needed for installation | shipments in advance | SEM detectors @ CERN | BL section | 1 | Check location
number of channels IP: right ¦ left |  | 292 |  |  | 234 |  | 260 | 230 |  | 186 |  | 232 | 226 |  | 180 | 238 |  |  | 224 | 230 |  | 286 | 242 |  | 220 | 230 |  | 256 | [6 empty] | 1 week/sector, 70 quad, 2 persons
total of channels |  | 526 |  |  |  |  | 490 |  |  | 418 |  |  | 406 |  |  | 462 |  |  |  | 516 |  |  | 462 |  |  | 486 | [8 empty] | 8 weeks / LHC 16 man weeks
total numbers of days (4 quad/day) |  | 21.9167 |  |  |  |  | 20.4167 |  |  | 17.4167 |  |  | 16.9167 |  |  | 19.25 |  |  |  | 21.5 |  |  | 19.25 |  |  | 20.25 | [8 empty] | 70 quad, 910 cables, 17.5 days, 4 weeks
source testing of ion chambers |  | 3 |  |  |  |  | 3 |  |  | 3 |  |  | 3 |  |  | 3 |  |  |  | 3 |  |  | 3 |  |  | 3
special installations | [15 empty] | 2 |  |  |  | 2 | [14 empty] | 35 weeks/LHC, 70 man weeks
total number of channels | 3766 | [33 empty] | 70 quad, 910 cables, 17.5 days, 4 weeks
total number of days | 184.9167 | [31 empty] | External EL | 8 | Fiber patch pannel installation
total number of days arc | 160.9167
Jul
[29 empty] | 400 |  |  |  | External BI | 2 | Supports chambers installation |  | 0.5
| Aug | [32 empty] | 3 | Chambers installation |  | 0.5
[34 empty] | 4 | Mounting of crate and fan unit ( BPM BLM) under quad |  | 0.2
( bicycle in the tunnel)
[29 empty] | 720 | [6 empty] | sum | 1.2
| Sep | [28 empty] | 526
0.53889
[29 empty] | 1080 |  |  |  |  | 5 | Cupper cables installation |  | 0.4
| Oct | [32 empty] | 6 | Cupper cables connection on the chambers (signal) |  | 0.2
[34 empty] | 7 | Cupper cables connection on the chambers (high voltage) |  | 0.2
[36 empty] | sum | 0.8
1440
Nov
[34 empty] | 9 | High Voltage cables test (CBH50) |  | 0.1
[29 empty] | 1800 | 1016 | 2.1778 |  |  | 10 | Analog cables test (CB50) (with picometer and current source) |  | 0.4
| Dec | [32 empty] | 11 | Cables connection on the chassis |  | 0
[34 empty] | 12 | CFC installation and test |  | 0.1
[34 empty] | 13 | Optical fibres installation |  | 0.1
[29 empty] | 2160 |  |  |  |  | 14 | Test of whole system (CFC + TC) |  | 0.3
2007 | Jan | [34 empty] | sum | 1
[29 empty] | 2520 | 1434 | 3.0167
Feb
1 day for 4 quadrupole,
6 chambers/quad, 24 chambers, 13 cable/quad, 52 cables
2880
| Mar | [28 empty] | 1840 | 2.8889
70 quad, 910 cables, 17.5 days, 4 weeks
35 weeks/LHC, 70 man weeks
[29 empty] | 3240 |  |  | 36
Apr
[33 empty] | External EL | 8 | Fiber patch pannel installation
[30 empty] | 2302 | 2.6056 | 314 | BL section | 15 | Surface installation
May
[29 empty] | 3600 | 2818 | 2.1722
| Jun | [28 empty] | 3280 | 0.88889
| Jul | [27 empty] | 3960 | 3766 | 0.53889
Aug
Sep
Works | BI / BL |  |  | Works 1 |  |  |  |  | Works 15
| BI / EXT |  |  | Works 2 - 4 |  |  |  |  | Works 5 - 7 |  |  |  | Works 9 - 14
| TS/EL EXT |  |  | Works 8
|  |  |  | bake out and NEG activation | [5 empty] | Works 1 to 14 in LSS
98053.4289 | 6128.3393 | 16 | 1 |  |  | 0.39847 |  |  | 0.41585
132383.9567 | 8273.9973 | 16 | 2 |  |  | 0.4 |  |  | 0.5593
6033.715 | 3016.8575 | 2 | 3 |  |  | 0.4 |  |  | 0.025491
98429.9234 | 6151.8702 | 16 | 4 |  |  | 0.4
132383.9567 | 8273.9973 | 16 | 5 |  |  | 0.4
6033.715 | 3016.8575 | 2 | 6 |  |  | 0.4
118423.7976 | 6579.0999 | 18 | 7 |  |  | 0.2
88255.9712 | 8023.2701 | 11 | 8 |  |  | 7.4
679998.4645 | [8 empty] | 1.0006
680000
arc (days) | 11.25