## BLM chambers
Sub-System | Delivery by | Code EDH | DAI order # | per chamber or magnet | needed | ordered | ordered by? | ordered - needed | received | date of receiving first/next | received-needed | location | checked by? | latest delivery schedule
version 29082006
cable try mounting clamps, magnets: | 544 |  |  | 6 | 3264
ATTACHES CABLOFILS | ISNARD, |  |  |  | 400 | 400 | Tissier | 0 | 0 | Sep | -400
ECLISSAGES ? | ISNARD, |  |  |  |  | 500 | Tissier | 500 | 0 | Oct | 0
ETRIER DE FIXATION POUR CABLOFILS | BE |  | 2259792 |  | 2000 |  |  | -2000 |  |  | -2000
Telex -rails pour Cables LHC TX 30 (3m) | ISNARD, |  | 2244699 |  | 400 | 200 | Tissier | -200 | 0 |  | -400
Telex -rails pour Cables LHC TX 50 (3m) | ISNARD, |  | 2244699 |  | 400 | 200 | Tissier | -200 | 0 |  | -400
bouchon
vis
0
Cablofil 30x50 (units m) | ISNARD, |  | 2222941 |  | 4800 | 4800 | Ferioli | 0 | 4800 | Jul | 0 | 865 RB01 | Ferioli
shrink tube (units m) |  |  |  | ionisation | 2542 | SEM | 73 | total: | 2615 | spare | 3268.75
Gaine Thermoretractable (units m) | CERN (Srati) |  | DAI 2189424 | 0.62 | 800 | 800 | Tissier | 0 | 800 | Aug | 0 | 865 RB01 | Tissier
Gaine Thermoretractable | CERN (Srati) |  | DAI 2260141 | 0.62 | 2469 | 2675 | Tissier | 206 | 0 | Nov | -2469
Total | [5 empty] | 9575 |  | -1694
Note on K18: dehning: spare 25 % (some quality problem)

## Time to sending
| wed | th | fr | sat | sun | mon | tues | wed | thur | Fr | sat | sun | mon | tu | wed | th | fr
Ready | EDH Shipping Request | bar: mon to th
Price |  | Signed Shipping Request | bar: mon to th
CHF! |  |  | Call Packing Service | bar: mon to th
PS saw the Packages | bar: mon to th
Packing by PS | bar: mon to th
| to add | to add | to add |  |  | to add | !No add | PS & Brigitte ready to order Lorry |  | Fr: Brigitte sent e-mail; mon: Brigitte; fr: Lorry to Protvino
[7 empty] | Ex weight |  |  | Fr: to Ext Tranpsort Company; mon: have a answer
about Lorry
at Fr
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
7-10 days
| Att&Ann to | [17 empty] | FINAL:
| L.Evans | Signed
|  |  | Transfer to Protvino | [15 empty] | 24-27 days
IHEP sign
IHEP sign
IHEP sign
[7 empty] | Rus Custom |  |  | tu: Rus Custom
[7 empty] | ask to permit |  |  | tu: permit

## Spacers
| type | date of reception | quoted pieces | received by | counted pieces | counted by
January: | type A
47444 |  | pre-series | 9300 |  | 9170
February: |  |  |  |  | 103 |  |  | 91500
52230 |  | 6.1.2006 | 14600 | EBH | 15824 | CC
| 3rd delivery | 24.1.2006 | 10000 | EBH | 10000 | CC
|  | 31.1.2006 | 10740 | EBH
| 5th delivery | 03.2.2006 | 11170 | EBH |  |  | EBH: 17 pieces measured (add to count)
| 6th delivery | 14.2.2006 | 12730 | EBH |  |  | EBH: 22 pieces measured (add to count)
| 7th delivery | 28.2.2006 | 15100 | EBH
March: | 8th delivery | 1.3.2006 | 13230 | EBH
| 9th delivery | 8.3.2006 | 15330 | EBH
| 10th delivry | 14.3.2006 | 18380 | EBH
| 11th delivery | 30.03.2006 | 25000 | Slava
type B
|  | 6.1.2006 | 948 | EBH | 941 | CC
type C
|  | pre-series | 300 |  | 305
93
|  | 12.1.2006 | 606 | EBH
| 3rd delivery | 24.1.2006 | 10550 | EBH
|  |  | 167984 | 96870