## Sheet1
Sub-System | Delivery by | DAI order # NEW | DAI order # old | order with JMM | old | first batch not less than # pieces | not later than date | arrived | mising
electrode spacer LHCBLM__0007 type A | Flueckiger (CH) |  | CA1390364 +?? | 103700 | 94000 |  | asap
electrode spacer LHCBLM__0007 type C | Flueckiger (CH) |  | CA1390364 +?? | 3400 | 3500 |  | asap
bottom cover disk LHCBLM__0006, manufacture | Dedecker (B) (was RMP) |  | CA1390102+CA1392889 | 650 |  | 650 | 2006-09-30 |  | 650
bottom cover spacer LHCBLM__0006 | Dedecker (B) | CA1406014 | CA1390111 | 800 |  | 800 | 2006-09-30 |  | 800
tighteners M4 LHCBLM__0016 type A Var 1 (incl. welded washer) | JCM (F) | CA1406022 |  | 3600 |  | 3000 | 2006-09-30 | 1622 | 1978
tighteners M4 LHCBLM__0016 type B Var 1 (incl. LHCBLM__0013) | JCM (F) | CA1406022 |  | 2200 |  | 1000 | 2006-09-30 | 2107 | 93
st steel sheet LHCBLM__0037, manufacture and material ! | Cherokee (B) | CA1406027 | CA1391433 | 650 |  | 650 | 2006-09-30 | 660 | -10
cover plate LHCBLM__0003, 316L | Dedecker (B) | CA1406014 | CL1932975 +?? | 500 | NEW DRAWING | 500 | 2006-09-15
cover spacer LHCBLM__0008 type A, 316L, IC | Solpey (E) | CA1405955 | CA1390217 | 1900 |  | 1900 | 2006-09-15 | 1916 | -16
protection tube LHCBLM__0010, 316L | Solpey (E) | CA1405955 | CA1390217 | 2300 | NEW DRAWING | 2300 | 2006-08-30 | 2300 | 0
welded spacer LHCBLM__0035, 304L, IC | Solpey (E) | CA1405955 | CA1390217 | 5500 | material !! | 5500 | 2006-08-15 | 5510 | -10
external plate LHCBLM__0037, manufacture | Solpey (E) | CA1405954 | CA1390916 | 600 |  | 600 | 2006-09-30 | 600 | 0
ceramics disks |  |  |  | 1550
feed throughs |  |  |  | 2240 |  |  |  | 2240 | 0
Al electrodes |  |  |  | 60000
el.box tubes |  |  |  | 500 |  |  |  | 501 | -1
Ion. Chamber tubes |  |  |  | 600
|  |  | in the hall | with L DeParis
Cu tubes |  |  | 509 | 530 |  |  |  | 568 | 38
Al tubes |  |  |  | 2700 |  |  |  | 2700 | 0
inox thred rod |  |  |  | 2800 |  |  |  | 2780 | -20