## BLM chambers
Sub-System | Delivery by | DAI order # | per chamber | number IC | spare IC | number SEM | spare SEM | total needed quantity | ordered | ordered by? | ordered - needed | received | date of receiving first/next | still to arrive | location | checked by? | latest delivery schedule | shipped to Protvino 2005 | to be shippied Protvino06 | unit price | total price | comments
LEGENDE: blue background means entered or checked by EBH, grey letters means: obsolete, deleted by EBH, grey backround means: cannot be checked by EBH
3818 IC +318 SEM (+4% spares) |  |  |  | 3799 | 18.995 | 315 | 3.15 | 4136.145
LHCBLM__0001 and LHCBLM__0009
tube inox 304L 483x88.9x2.0 LHCBLM__0040 | Santrade, CH | 39.39.05.088.2 | 1 | 3799 | 18.995 |  |  | 3817.995 | 3800 | CV | -17.995 | 1455 |  | -2345 | pool | SG |  | 1394 | -2423.995 | 12.00 |  | 59- still at CERN
tube inox 304L 109x88.9x2.0 LHCBLM__0040 |  | 39.39.05.088.2 | 1 |  |  | 315 | 3.15 | 318.15 | 310 | CV | -8.15 | 118 |  | -192 |  | Slava |  |  | -318
tube inox 304L 105x88.9x2 LHCBLM__0038 v.AB |  | 39.39.05.088.2 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4110 | CV | -26.145 | 1504 |  | -2606 |  | SG |  | 1500 | -2636.145 |  |  | 4 still at CERN
0
Ceramics LHCBLM__0005 v.AC |  | partially open, ?? | 2 | 3749 | 18.745 |  |  | 7535.49 | 7110 | EBH | -425.49 |  |  | -7110 |  |  |  | 0 | -7535.49
Ceramics LHCBLM__0005 v.AC |  | open | 1 |  |  | 315 | 3.15 | 318.15 |  |  | -318.15 |  |  | 0
Ceramics LHCBLM__0041 upper CNGS | FRIATEC (F) | ?? | 1 | 50 |  |  |  | 50 | 50 | BD/JMM | 0 | 50 | 29.11.2004 | 0 | pool
Ceramics LHCBLM__0042 lower CNGS | FRIATEC (F) | ?? | 1 | 50 |  |  |  | 50 | 50 | BD/JMM | 0 | 50 | 29.11.2005 | 0 | pool
[11 empty] | 0 |  |  | 0
Al electrodes production LHCBLM__0004 0.5X82 | Dutreive (F) | partially open, CA 1391681 | 61 | 3799 | 18.995 |  |  | 232897.695 | 208020 | EBH | -25513.995 | :25000 | 07.12.2005 | #VALUE! |  |  | Dec 05 | 0 | -232897.695
Al electrodes production LHCBLM__0004 0.5X82 | Dutreive (F) | open | 2 |  |  | 315 | 3.15 | 636.3 | 0 |  |  |  |  | 0 |  |  | Dec 05
Al electrodes 0.5 AL material | CERN | partially open, CA 1391681 | [5 empty] | 19776 | 16650 | EBH | -3126 | 16650 |  | 0
check!!:
electrode spacer LHCBLM__0007 type A | Flueckiger (CH) | CA1390364 +?? | 183 | 3799 | 75.98 |  |  | 712069.74 | 698300 | EBH/JMM | -13769.74 | 9273 |  | -689027 | pool, EBH | SG, EBH | ?? | 1830 | -710239.74
electrode spacer LHCBLM__0007 type A | Flueckiger (CH) | CA1390364 +?? | 9 |  |  | 315 | 12.6 | [6 empty] | 0 |  |  | ??
electrode spacer LHCBLM__0007 type B | Flueckiger (CH) | CA1390364 +?? | 3 |  |  | 315 | 12.6 | 982.8 | 930 | EBH/JMM | -52.8 |  |  | -930 |  |  | ??
electrode spacer LHCBLM__0007 type C | Flueckiger (CH) | CA1390364 +?? | 6 | 3799 | 75.98 |  |  | 23249.88 | 22800 | EBH/JMM | -449.88 | 398 |  | -22402 | pool, EBH | SG, EBH | ?? | 60 | -23189.88
0
bot. cov. disk LHCBLM__0006, 316L, 5mm | CERN, material |  | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 34 "spare" | EBH?? | #VALUE!
bottom cover disk LHCBLM__0006 | RPM (I) | CA1390102+CA1392889 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4110 | EBH/JMM | -26.145 | 90 |  | -4020 |  |  | Dec 05 | 50 | -4086.145
bottom cover spacer LHCBLM__0006 | Dedecker (B) | CA1390111 | 1 | 3799 | 18.995 |  |  | 3817.995 | 3800 | EBH/JMM | -17.995 | 50+?? |  | #VALUE! |  |  | Nov 05 | 10 | -3807.995 | 0.03
tighteners M4 LHCBLM__0016
type B Var 1 (incl. LHCBLM__0013) | JCM (F) |  | 2 | 3799 | 18.995 |  |  | 7635.99 | 7600 | EBH/JMM | -35.99 |  | Jan 06 | -7600 |  |  |  | 0 | -7636
type A Var 1 (incl. welded washer) | JCM (F) |  | 4 | 3799 | 18.995 |  |  | 15271.98 | 15200 | EBH/JMM | -71.98 |  | Jan 06 | -15200 |  |  |  | 4 | -15272
heads
50 IC heads (CNGS) | DG-technology (I) | CA1390214 | 1 | 50 |  |  |  | 50 | 50 | EBH/JMM | 0 | 10 | 38626 | -40 | pool |  | ??
500 IC heads (Aerovac) | AeroVac (GB) |  | 1 | 500 |  |  |  | 500 | 0 | EBH/JMM | -500 |  |  | 0 |  |  |  | 5 | -495
small items
compressing spring 1.4310 ferroflex | Ferroflex | VD-180M-14 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 3850 | CV | -286.145 |  |  | -3850 |  |  | Dec 05 | 0 | -4136.145
alumina tube D15/10, L=25mm | CERN | 19.63.30.128.9 | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 | 8220 | EBH | -52.29 | 102? |  | #VALUE! | SG | SG |  | 0 | -8272.29 | 2
slotted screw M3x4, A2-ISO 1580 | Bossard BN652 | 47.62.72.996.0 | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 | 8400 | CV | 127.71 |  | Dec 05 | -8400 |  |  | Dec 05 | 0 | -8272.29 | 5
screw without head 6pc bt point.in.3x3 | Bossard BN618 | 47.62.72.995.0 | 4 | 3799 | 18.995 | 315 | 3.15 | 16544.58 | 16600 | CV | 55.42 |  | Dec 05 | -16600 |  |  | Jan 06 | 0 | -16544.58
spring washer D8/4.2-0.2, 1.4310 | Bossard BN838 | 47.62.72.996.8 | 18 | 3799 | 18.995 | 315 | 3.15 | 74450.61 | 75000 | CV | 549.39 |  | Dec 05 | -75000 |  |  | Dec 05 | 0 | -74450.61
stop nut M4-A2 DIN980V | Bossard BN5242 | 47.62.72.998.2 | 6 | 3799 | 18.995 | 315 | 3.15 | 24816.87 | 23000 | CV | -1816.87 |  | Dec 05 | -23000 |  |  | Feb 06 | 0 | -24816.87
label (self adhesive) for chambers |  |  | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 0 | ?? | -4136.145 |  |  | 0 |  |  |  | 0 | -4136.145
cover assembly LHCBLM__0002
cover plate LHCBLM__0003, 316L, material | CERN |  | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 | 8250 |  | -22.29 |  |  | -8250
cover plate LHCBLM__0003, 316L | Dedecker (B) | CL1932975 +?? | 1 | 3249 | 16.245 | 315 | 3.15 | 3583.395 | 3610 | EBH/JJM | 26.605 | 8 | 28.11.2005 | -3602 |  | EBH | ?? | 2
feed throughs | CERAMTEC (US) | 1889051/1937566 | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 | 7420 | EBH | -852.29 | 3986 |  | -3434 | CC | CC |  | 4 |  | 20
copper tube 10 x 8, L=120mm | CERN, MR 1887862 | 39.71.20.008.8 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4110 | CV | -26.145 | received |  | #VALUE! |  | CV |  | 2
cutting and anealing of copper tube | [9 empty] | CV
cover spacer LHCBLM__0008 type A, 316L | Solpey (E) | CA1390217 | 2 | 3799 | 18.995 |  |  | 7635.99 | 6500 | EBH/JJM | -1135.99 | received |  | #VALUE! |  |  |  | 4
cover spacer LHCBLM__0008 type B, 316L | Solpey (E) | CA1390217 | 2 |  |  | 315 | 3.15 | 636.3 | 620 | EBH/JJM | -16.3 | received |  | #VALUE!
protection tube LHCBLM__0010, 316L | Solpey (E) | CA1390217 | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 | 7120 | EBH/JJM | -1152.29 | received |  | #VALUE! |  |  |  | 4
welded spacer LHCBLM__0035, 304L | Solpey (E) | CA1390217 | 3 | 3799 | 18.995 | 315 | 3.15 | 12408.435 | 10680 | EBH/JJM | -1728.435 | received |  | #VALUE! |  |  |  | 6
TIG welding job
TIG welding of heads (IHEP or company) |  |  | 1 | 3249 | 16.245 | 315 | 3.15 | 3583.395 | 0 | EBH/JMM | -3583.395 |  |  | 0
electrical connectors ass LHCBLM__0036
el.box cover rondel, 304L, 5mm, material | CERN |  | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4110 |  | -26.145 |  |  | -4110 |  |  |  | 0 | -4136.145
external plate LHCBLM__0037, manufacture | Solpey (E) | CA1390916 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4110 | EBH/JJM | -26.145 | 50 |  | -4060 |  |  | ?? | 10 | -4126.145
st steel sheet LHCBLM__0037, material | CERN | [6 empty] | ?? | [5 empty] | 0
st steel sheet LHCBLM__0037, manufacture | Cherokee (B) | CA1391433 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4160 | EBH/JJM | 23.855 |  |  | -4160 |  |  | ?? | 10 | -4126.145
tube AlMgSi hard 4*7 L=60 |  | 39.64.05.012.1 | 3 | 3799 | 18.995 | 315 | 3.15 | 12408.435 | 780 MT | CV | [6 empty] | 27.10+2wks | 0 | -12408.435
in.steel.thr.rods A4 316 M4 L=85 |  | 47.38.77.040.8 | 3 | 3799 | 18.995 | 315 | 3.15 | 12408.435 | 12300 | CV | -108.435 |  | Dec 05 | -12300 |  |  | Jan 06 | 0 | -12408.435
hex.nuts inox A4 316 0.8D M4 |  | 47.43.77.040.1 | 6 | 3799 | 18.995 | 315 | 3.15 | 24816.87 | 25000 | CV | 183.13 |  |  | -25000 |  |  |  | 0 | -24816.87
washer contact medium M4 |  | 47.78.09.004.1 | 3 | 3799 | 18.995 | 315 | 3.15 | 12408.435 | 12400 | CV | -8.435 |  |  | -12400 |  |  | Dec 05 | 0 | -12408.435
head.hex.point.scr. M3x5, inox |  | 47.62.96.101.1 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4200 | CV | 63.855 |  |  | -4200 |  |  |  | 0 | -4136
BNC HT Polypenco SHV 5KV | CERN | 09.41.25.160.9 | 2 | 3799 | 18.995 | 315 | 3.15 | 8272.29 | 8272 | GF | -0.29 | 8272 |  | 0 |  |  |  | 8200
BNC 50ohm, teflon | CERN | 09.46.11.360.4 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4136 | GF | -0.145 | 4136 |  | 0 |  |  |  | 4100
soldering lug, M4 | CERN | 04.76.26.448.1 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4200 | GF | 63.855 | 1800 |  | -2400 |  |  |  | 1800
soldering lug, BNC | CERN | 09.46.11.520.6 | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4200 | GF | 63.855 | 4200 |  | 0 |  |  |  | 4100
wires (L=100, 1.5mm2) | CERN | 04.01.61.900.1 | 0.15 | 3799 | 18.995 | 315 | 3.15 | 620.4217 | 800 | GF | 179.5783 | 800 |  | 0 |  |  |  | 800
tinned cupper wires, without insulation, D=0.91mm |  | 04.01.02.091.5 | 0.1 | 3799 | 18.995 | 315 | 3.15 | 413.6145 | 280 | GF | -133.6145 | 280 |  | 0 |  |  |  | 140
Resistor 10Mohm ,1W |  |  | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4250 | GF | 113.855 | 4250 |  | 0 |  |  |  | 3950
Capacitor (0.47uF, 2000V) |  |  | 1 | 3799 | 18.995 | 315 | 3.15 | 4136.145 | 4273 | GF | 136.855 | 4273 |  | 0 |  |  |  | 4000 | -100
supports
arc support plate (Al) plus rilsan coating |  |  | 1 | 3482 | 17.41 | 274 | 2.74 | 3776.15
arc support bracket (inox) plus rilsan coating |  |  | 2 | 3482 | 17.41 | 274 | 2.74 | 7552.3
arc stainless steel ties |  |  | 2 | 3482 | 17.41 | 274 | 2.74 | 7552.3
support LSS |  |  | 1 | ?? |  |  |  | ??
SEM only
SEM Ti electrode |  |  | 1 |  |  | 315 | 3.15 | 318.15 |  |  | -318.15
cover spacers
screws
tighteners SEM
Total | [7 empty] | 1366588.7663 | 1272961 |  | #VALUE! | [6 empty] | 31985 | -1229833.625
Note on K17: dehning: in m 0.082 /ion
Note on C44: dehning: 1. 20 2. 7420
Note on T63: dehning: expec. 31/11 grishinv: Lorry#2,Dec05
Note on T64: dehning: expec. 31.11 grishinv: Lorry#2,Dec05
Note on E4: eholzer: input field
Note on G4: eholzer: input field
Note on T65: grishinv: Lorry#2,Dec05;2300 to send
Note on T66: grishinv: Lorry#2,Dec05
Note on T69: grishinv: Lorry#2,Dec05; 150 to send
Note on T70: grishinv: Lorry#2,Dec05; 100 to send
Note on T67: grishinv: Lorry#2,Dec05
Note on T68: grishinv: Lorry#2,Dec05;140 to send
Note on R37: grishinv: 15000- 24.10+10days; 16600- +8 weeks
Note on A38: grishinv: rondelle a plateau inox A2 M4
Note on A36: grishinv: vis tete aplatie in.A2 M3x4
Note on A37: grishinv: vis sans tete 6 p.cr.M3x3
Note on R38: grishinv: 2000- 24.11+10 days; 73000- 24.11 +2weeks
Note on A39: grishinv: ecrou hexagonal in.autofr.M4
Note on R39: grishinv: 12000- 24.11 + 10 days 11000- 24.11+8/12 weeks
Note on A59: grishinv: tige filetee in.4.A4 M 4x85 47.62.82.908.1
Note on R59: grishinv: 14 m -24.11+10 days; rest - 24.11+6 weeks
Note on A62: grishinv: vis sans tete 6 p.cr.in N3x5; 47.62.72.995.5
Note on I72: eholzer: minus number of single supports
Note on E72: eholzer: minus number of singel supports
Note on E73: eholzer: eholzer: minus number of singel supports
Note on I73: eholzer: eholzer: minus number of singel supports
Note on E74: eholzer: minus number of single supports
Note on I74: eholzer: minus number of single supports
Note on S63: dehning: expec. 31/11 grishinv: Lorry#2,Dec05
Note on S64: dehning: expec. 31.11 grishinv: Lorry#2,Dec05
Note on S65: grishinv: Lorry#2,Dec05;2300 to send
Note on S66: grishinv: Lorry#2,Dec05
Note on S67: grishinv: Lorry#2,Dec05
Note on S68: grishinv: Lorry#2,Dec05;140 to send
Note on S69: grishinv: Lorry#2,Dec05; 150 to send
Note on S70: grishinv: Lorry#2,Dec05; 100 to send
Note on L15: eholzer: IC and SEM!!
Note on L19: eholzer: IC+SEM!!
Note on R36: dehning: 24.10+10d
Note on P32: dehning: 24.10+10d
Note on O58: dehning: 27.10+2wks
Note on I19: eholzer: IC and SEM!!