## Slide 1: Week 43 ( LHC only)
Installation of BLECF in LSS 4L and LSS 4R (Adrien and Mounir) - Done
Check and repairs of BLECF in LSS 4L and LSS 4R (Steve) -?
Installation of BLECF in LSS 5L ( Mounir and Steve) – Done
Check and repairs of BLECF in LSS 5L (Steve) -?
Preparation of BLECF for LSS 5R and ARC 5R ( Ion) - Done
Re-installation and modification of BLMs at TCDQ@L6 ( RT) – Done
RSM at s23: repairs, exchange of ICs, connections (RT) – Done and OK
Check of LiCs in s23 by hammer and installation of 2 HVD at L3 (Adrien and Ion) – Done
Seems sector 23 is ready to beam… ( up to the door at 07L3)
Preparation ( supports) for MKI@L2 installation ( RT and Remo) – Done
BLM installation Totem@L5 (RT) – in Progress
Change of IC orientation by Tauro’s request at Alice ( RT) - Done

## Slide 2: Week 44 ( LHC only)
IMPACT for BLM works in sector 56 – OK
Preparation and IMPACT for BLM works at MKI@L2 – at work
We need to finish the MKI@L2 works on week 44
Transvers or “standard” longitudinal ( along beam direction) installation of BLM@MKI?
CONSTRAINS of access to sector 5-6:
no pass thru doors
from P5 up to 21R5
from Point 6 to LSS up to 05L6
from Point 6 to Arc up to 21R5
L6 accessible up to 2 pm(!) Powering Test PH‐II
RSM at s56: from Wednesday 29/10 to 11/11
Marzia was I informed about BLM request to make re-RSM of sector 67, 12,81 later.
Marzia: possible after NY but with some constrains.

## Slide 3: Week 44 ( LHC only)
Installation of BLECF in LSS 5R and ARC 5R (Adrien and Mounir)
Preparation of BLECF for next RSM in s78 ( Ion)
Checking if all NES 18 cables in s56 are connected ( Adrien and Mounir)
Re-installation and modification of BLMs at TCDQ@R6 (RT) – Monday – Tuesday ( up to 1pm)
Installation and re-cabling of BLMs at MK2@L2 ( RT)– Tuesday – Friday
Re-cabling(new cabling) of BLM for injection@L2 – Tuesday-Friday - ???
BLM installation and new cabling Totem@R5 (RT) – Monday-Tuesday( after 2pm) – Wednesday
BLM@BPMSW (triplet) installation ( RT) - Tuesday-Friday
Verification and re-Installation of BLMs in ARC 56( RT) – Tuesday-Friday
RSM at s56: repairs, exchange of ICs, connections (RT) – from Wednesday up to November 11