## IC inst
2008-04-02 | [10 empty] | LHC Beam Loss installation | [33 empty] | LHC Beam Loss installation
|  | 11 | week |  |  | 8 |  |  |  | 14 |  |  |  | clos |  |  |  | 5 |  |  |  | 8 |  |  |  | 4 |  |  |  | 6
Cell | R 1 |  | L 2 |  | R 2 |  | L 3 |  | R 3 |  | L 4 |  | R 4 |  | L 5 |  | R 5 |  | L 6 |  | R 6 |  | L 7 |  | R 7 |  | L 8 |  | R 8 |  | L 1 |  |  | Cell | R 1 |  | L 2 |  | R 2 |  | L 3 |  | R 3 |  | L 4 |  | R 4 |  | L 5 |  | R 5 |  | L 6 |  | R 6 |  | L 7 |  | R 7 |  | L 8 |  | R 8 |  | L 1
| IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S |  |  | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S
1 | [12 empty] | open 11 |  |  |  | 6 | 1 | [8 empty] | 5 | 1 | 5 | 1 | 5 | 1 | 1 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | [8 empty] | 6 | 1 | 6 | 1 | [8 empty] | 5 | 1 | 5 | 1 | 5 | 1 | 1
2 | [16 empty] | 6 | [5 empty] | week 7 no acces |  |  |  | 8 |  | 8 |  | 8 |  | 2 | 2 | 8 |  | 8 |  | 8 | [9 empty] | 6 |  | 6 | [9 empty] | 8 |  | 8 |  | 8 |  | 2
3 | [16 empty] | 6 | [7 empty] | open |  | 5 |  | 5 |  | 5 |  | 3 | 3 | 5 |  | 5 |  | 5 | [9 empty] | 6 |  | 6 | [9 empty] | 5 |  | 5 |  | 5 |  | 3
4 |  |  | D | [11 empty] | 11 | 4 | 11 | 4 | 31 | 15 | 31 | 15 |  |  |  |  | 13 | 3 | 15 | 5 | 10 | 4 | 4 | 4 | 10 | 4 | 15 | 5 | 13 | 4 | 8 | 2 | 8 | 2 | 2 |  | 2 |  | 11 | 4 | 11 | 4 | 31 | 24 | 31 | 24 | 18 | 12 | 18 | 12 | 13 | 3 | 15 | 5 | 10 | 4 | 4
5 | [12 empty] | 8 |  | 7 | 1 | 7 | 1 | 11 | 3 | 11 | 3 |  |  |  |  | 6 |  | 6 |  | 7 | 1 | 5 | 5 | 7 | 1 | 6 |  | 6 |  | 14 | 8 | 14 | 8 | 8 |  | 8 |  | 7 | 1 | 7 | 1 | 11 | 3 | 11 | 3 | 20 | 14 | 20 | 14 | 6 |  | 6 |  | 7 | 1 | 5
6 | [12 empty] | 6 |  | 8 |  | 7 | [9 empty] | 7 | 1 | 12 | 6 | 6 |  | 6 | 6 | 6 |  | 12 | 6 | 7 | 1 | 10 | 4 | 10 | 4 | 6 |  | 6 |  | 8 |  | 7 | [5 empty] | 27 | 21 | 27 | 21 | 7 | 1 | 12 | 6 | 6 |  | 6
7 | [12 empty] | 6 |  | 6 |  | 6 | [5 empty] | 7+1 | 2 | 8 | 2 | 6 |  | 6 |  | 8 |  | 7 | 7 | 8 |  | 6 |  | 6 |  | 7 | 1 | 7 | 1 | 6 |  | 6 |  | 6 |  | 6 | [5 empty] | 8 | 2 | 8 | 2 | 6 |  | 6 |  | 8 |  | 7
8 | [6 empty] | 12 |  |  |  | 6 |  | 6 |  | 12 |  | 12 |  | 6 |  | 6 |  | 9 |  | 9 |  | 12 | 6 | 12 | 6 | 12 |  | 8 | 8 | 12 |  | 12 | 6 | 12 | 6 | 12 |  | 12 |  | 6 |  | 6 |  | 12 |  | 12 |  | 6 |  | 6 |  | 9 |  | 9 |  | 12 | 6 | 12 | 6 | 12 |  | 8
9 | [6 empty] | 16 |  |  |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 16 |  | 16 |  | 6 |  | 6 |  | 6 |  | 9 | 9 | 6 |  | 6 |  | 6 |  | 21 |  | 21 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 16 |  | 16 |  | 6 |  | 6 |  | 6 |  | 9
10 | [6 empty] | 15 |  |  |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 7 |  | 9 |  | 6 |  | 6 |  | 8 |  | 10 | 10 | 8 |  | 13 |  | 12 |  | 11 |  | 11 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 7 |  | 9 |  | 6 |  | 6 |  | 8 |  | 10
11 | [6 empty] | 19 |  |  |  | 6 |  | 6 |  | 13 |  | 13 |  | 6 |  | 6 |  | 5+1 |  | 19 |  | 12 | 6 | 12 | 6 | 16 |  | 11 | 11 | 17 |  | 12 | 6 | 12 | 6 | 19 |  | 19 |  | 6 |  | 6 |  | 13 |  | 13 |  | 6 |  | 6 |  | 19 |  | 19 |  | 12 | 6 | 12 | 6 | 16 |  | 11
12 | 6 |  | 6+2 |  | 8 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 5+1 |  | 6 |  | 6 |  | 6 |  | 6 |  | 12 | 12 | 6 |  | 8 |  | 8 |  | 10 |  | 10 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 12
13 | 6+2 |  | 6 |  | 6 |  | 14 |  | 6 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 7 |  | 8 |  | 6 |  | 6 |  | 8 |  | 13 | 13 | 8 |  | 6 |  | 6 |  | 10 |  | 10 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 8 |  | 13
14 | 6 |  | 6 |  | 6 |  | 6 |  | 5+1 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 14 | 14 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 14
15 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 15 | 15 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 15
16 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 16 | 16 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 16
17 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 5+1 |  | 6 |  | 6 |  | 6 |  | 6 |  | 17 | 17 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 17
18 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 18 | 18 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 18
19 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 9+1 |  | 6 |  | 6 |  | 6 |  | 6 |  | 19 | 19 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 10 |  | 6 |  | 6 |  | 6 |  | 6 |  | 19
20 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 20 | 20 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 20
21 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 21 | 21 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 21
22 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 22 | 22 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 22
23 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 23 | 23 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 23
24 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 24 | 24 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 24
25 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 25 | 25 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 25
26 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 26 | 26 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 26
27 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 5+1 |  | 6 |  | 6 |  | 6 |  | 6 |  | 27 | 27 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 27
28 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 28 | 28 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 28
29 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 29 | 29 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 29
30 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 30 | 30 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 30
31 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 31 | 31 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 31
32 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 32 | 32 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 32
33 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6(1) |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 33 | 33 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 33
34 | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 | [7 empty] | 6 |  |  |  | 6 |  |  |  | 34 | 34 | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 34
Dump | [18 empty] | 17 | 7 | 17 | 7 | [10 empty] | Dump | Dump | [18 empty] | 19 | 7 | 19 | 7 | [10 empty] | Dump
[34 empty] | IC to inst | 232 |  | 234 |  | 232 |  | 242 |  | 248 |  | 178 |  | 184 |  | 223 |  | 228 |  | 217 |  | 223 |  | 262 |  | 266 |  | 218 |  | 231 |  | 225 |  | 3643
[34 empty] | S to inst |  | 6 |  | 24 |  | 18 |  | 15 |  | 15 |  | 0 |  | 0 |  | 6 |  | 6 |  | 34 |  | 34 |  | 49 |  | 49 |  | 17 |  | 24 |  | 6 | 303
[37 empty] | 466 | 42 |  |  | 490 | 30 |  |  | 362 | 0 |  |  | 451 | 12 |  |  | 440 | 68 |  |  | 528 | 98 |  |  | 449 | 41 |  |  | 457 | 12
|  | finished |  |  |  | on work |  |  |  | to be done |  |  |  | 6 | No 240 V with comments | [6 empty] | D | Drawing
Note on H24: grishinv: 2007:No 240 V 31/01/08:Bernd->OK
Note on B18: grishinv: No 240V, no interconnection,no power
Note on B26: grishinv: No 240 V
Note on B28: grishinv: No 240 V
Note on H31: grishinv: 2007:Short FIP cable
Note on H26: grishinv: 2007:Short FIP cable
Note on J17: grishinv: 2007:No cover,no vent module
Note on J18: grishinv: 2007:No cover,no vent. Module, no PS
Note on J19: grishinv: 2007:No cover, no vent module 2008: 1 BLM(1521) on QBQL14R3 was dsimounted 24/01/08
Note on J20: grishinv: No cover
Note on L27: grishinv: 2007
Note on L30: grishinv: 2007
Note on L32: grishinv: 2007
Note on D24: grishinv: 2007
Note on L34: grishinv: 2007
Note on L36: grishinv: 2007
Note on J36: grishinv: 2007
Note on J37: grishinv: 2007
Note on P36: grishinv: 2007:Short FIP cable
Note on X24: grishinv: 2007:Short FIP cable 21/01/08: Andrea Musso ask to dismount QBQI->8L7,12L7,13L7,20L7,28L7
Note on V9: grishinv: 2007: yellow
Note on V10: grishinv: 2007:yellow
Note on Z17: grishinv: 2007: BL 240 V - no
Note on Z23: grishinv: 2007: BL 240 V - no
Note on Z28: grishinv: 2007: BL 240 V - no
Note on Z34: grishinv: 2007: BL 240 V - no
Note on Z36: grishinv: 2007: BL 240 V - no
Note on Z37: grishinv: 2007: BL 240 V - no
Note on Z38: grishinv: 2007: BL 240 V - no
Note on Z39: grishinv: 2007:BL 240 V-> empty cell
Note on AB36: grishinv: 2007:BL 240 V-> empty cell
Note on AB24: grishinv: 2007:BL 240 V-> empty cell
Note on AB17: grishinv: 2007:BL 240 V-> empty cell
Note on AB18: grishinv: 2007:BL 240 V-> empty cell
Note on AB29: grishinv: 2007:Short FIP cable
Note on AD31: grishinv: 2007:Short FIP cable
Note on O47: grishinv: No 240 V
Note on H27: grishinv: 30/01/08: Vladimir-> HV?
Note on P38: grishinv: 21/01/08:Sven de Man-> BLMQI.D33L5 est environ 10 sm plus bas que l'autre
Note on X32: grishinv: 21/01/08: Andrea Musso ask to dismount QBQI->8L7,12L7,13L7,20L7,28L7
Note on X17: grishinv: 21/01/08: Andrea Musso ask to dismount QBQI->8L7,12L7,13L7,20L7,28L7
Note on X16: grishinv: 21/01/08: Andrea Musso ask to dismount QBQI->8L7,12L7,13L7,20L7,28L7
Note on X12: grishinv: 21/01/08: Andrea Musso ask to dismount QBQI->8L7,12L7,13L7,20L7,28L7
Note on X22: grishinv: 24/01/08: J-P Tock ask to dismount QBQI->18L7