## HWC for BLM
Beam Loss Monitor HWC
Once completed. send this file Jacek.Szkutnik@cern.ch Empty fields will remain untouch in MTF DB Non empty fields will be updated (when allowed) on MTF DB -> Just fill modified fileds! DO NOT ALTER THIS TEMPLATE - You can just insert lines for new slots if necessary Remove given Examples!
71720057
Identification |  | 10-BLM channel check (leakage. bias current) | [7 empty] | [Patch_Input] |  | pA | pA | 20-BLM Acquisition Chain Desription | [5 empty] | [Loc=Ra_Cr_CFC_In] |  | [Cr_CFC_Out] | [Loc=Ra_Pa_In] | [Loc=Ra_Pa_Sl_Out] | [Loc=Ra_VME_Si_DAB_In] | [18 empty] | 30-BLM Acquisition Chain Test via test signal |  |  |  |  | pA | pA | 40-BLM HV modulation Test |  |  |  |  | V | Hz | ° |  | pA | 50-BLM Acquisition Chain Test via RA Source |  |  |  |  | pA | 60-BLM Interlock Test | [8 empty] | 70-BLM EMC Test |  |  |  |  | pA | pA | 80-BLM Beam Energy reception Test |  |  |  |  | EDMS Document Number
Official Slot Name |  | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Monitor Type | Monitor Identificator | HV Patch | BJBAP Input | Tunnel Mini Rack Id. | LC(offset) w/cable&M-r | Signal via source w/cable | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | BJBAP Cable Number | Analog Front End | BLECF Identificator | Opt Link Analog FE | Opt Link Patch Tunnel | Opt Link Patch Surface | Opt Link Digital Acq. | VME BLETC Id. | VME CPU Host Name | VME Crate Id. | VME Fantray Id. | VME Power Supply Id. | VME CPU Id. | VME BOBR Id. | VME BLECS Id. | VME BLETC Serial | VME BLECS Serial | Monitor Function | Monitor Status | VME Fantray Hostname | DAB card Id. | Mezzanine card Id. | CIBU Id. | FPGA firmware vers(BLETC) | FPGA firmware vers(BLECS) | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Test:100pA/84 sec run.sum | Test:10pA/84 sec run.sum | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Set voltage: peak-peak | Set frequency | Resulting phase | Resulting Gain | Current signal: peak-peak | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Signal Current | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Threshold/Ch Matrix Test | TTable User Beam Permit T | UBP Check BLETC to BLECS | UBP Check BLECS to CIBU | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Test EMC/40 µs run.sum | Test EMC/1.3 sec run.sum | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments
1 | BLMEI.A4L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A4L3 | BJBAP.A4L3_8 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302132 | UJ33=BY02_1_1_8 | HCBLECF001-CR000729 | 1_1_A1;1_1_A2 | UJ33=BY02_B_1;UJ33=BY02_B_2 | SR3=BY05_C_1_1;SR3=BY05_C_1_2 | SR3=BY02_1_4_1_1;SR3=BY02_1_4_1_2 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000286
2 | BLMEI.B4L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A4L3 | BJBAP.A4L3_7 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302132 | UJ33=BY02_1_1_7 | HCBLECF001-CR000729 | 1_1_A1;1_1_A2 | UJ33=BY02_B_1;UJ33=BY02_B_2 | SR3=BY05_C_1_1;SR3=BY05_C_1_2 | SR3=BY02_1_4_1_1;SR3=BY02_1_4_1_2 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000286
3 | BLMQI.A4L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A4L3 | BJBAP.A4L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302132 | UJ33=BY02_1_1_6 | HCBLECF001-CR000729 | 1_1_A1;1_1_A2 | UJ33=BY02_B_1;UJ33=BY02_B_2 | SR3=BY05_C_1_1;SR3=BY05_C_1_2 | SR3=BY02_1_4_1_1;SR3=BY02_1_4_1_2 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
4 | BLMQI.B4L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A4L3 | BJBAP.A4L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302132 | UJ33=BY02_1_1_5 | HCBLECF001-CR000729 | 1_1_A1;1_1_A2 | UJ33=BY02_B_1;UJ33=BY02_B_2 | SR3=BY05_C_1_1;SR3=BY05_C_1_2 | SR3=BY02_1_4_1_1;SR3=BY02_1_4_1_2 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
5 | BLMQI.C4L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A4L3 | BJBAP.A4L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302132 | UJ33=BY02_1_1_4 | HCBLECF001-CR000729 | 1_1_A1;1_1_A2 | UJ33=BY02_B_1;UJ33=BY02_B_2 | SR3=BY05_C_1_1;SR3=BY05_C_1_2 | SR3=BY02_1_4_1_1;SR3=BY02_1_4_1_2 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
6 | BLMQI.D4L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A4L3 | BJBAP.A4L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302132 | UJ33=BY02_1_1_3 | HCBLECF001-CR000729 | 1_1_A1;1_1_A2 | UJ33=BY02_B_1;UJ33=BY02_B_2 | SR3=BY05_C_1_1;SR3=BY05_C_1_2 | SR3=BY02_1_4_1_1;SR3=BY02_1_4_1_2 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
7 | BLMQI.E4L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A4L3 | BJBAP.A4L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302132 | UJ33=BY02_1_1_2 | HCBLECF001-CR000729 | 1_1_A1;1_1_A2 | UJ33=BY02_B_1;UJ33=BY02_B_2 | SR3=BY05_C_1_1;SR3=BY05_C_1_2 | SR3=BY02_1_4_1_1;SR3=BY02_1_4_1_2 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
8 | BLMQI.F4L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A4L3 | BJBAP.A4L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302132 | UJ33=BY02_1_1_1 | HCBLECF001-CR000729 | 1_1_A1;1_1_A2 | UJ33=BY02_B_1;UJ33=BY02_B_2 | SR3=BY05_C_1_1;SR3=BY05_C_1_2 | SR3=BY02_1_4_1_1;SR3=BY02_1_4_1_2 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
9 | BLMES.A4L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B4L3 | BJBAP.B4L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302133 | UJ33=BY02_1_2_2 | HCBLECF001-CR000711 | 1_2_A1;1_2_A2 | UJ33=BY02_B_3;UJ33=BY02_B_4 | SR3=BY05_C_1_3;SR3=BY05_C_1_4 | SR3=BY02_2_4_1_1;SR3=BY02_2_4_1_2 | BLETC 333 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501295 | MEZZ NO 390 | HCCIBUS-ID000286
10 | BLMES.B4L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B4L3 | BJBAP.B4L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302133 | UJ33=BY02_1_2_1 | HCBLECF001-CR000711 | 1_2_A1;1_2_A2 | UJ33=BY02_B_3;UJ33=BY02_B_4 | SR3=BY05_C_1_3;SR3=BY05_C_1_4 | SR3=BY02_2_4_1_1;SR3=BY02_2_4_1_2 | BLETC 333 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501295 | MEZZ NO 390 | HCCIBUS-ID000286
11 | BLMEI.A5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A5L3 | BJBAP.A5L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302134 | UJ33=BY02_1_3_6 | HCBLECF001-CR000602 | 1_3_A1;1_3_A2 | UJ33=BY02_B_5;UJ33=BY02_B_6 | SR3=BY05_C_1_5;SR3=BY05_C_1_6 | SR3=BY02_2_4_1_3;SR3=BY02_2_4_1_4 | BLETC 333 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501295 | MEZZ NO 390 | HCCIBUS-ID000286
12 | BLMEI.B5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A5L3 | BJBAP.A5L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302134 | UJ33=BY02_1_3_5 | HCBLECF001-CR000602 | 1_3_A1;1_3_A2 | UJ33=BY02_B_5;UJ33=BY02_B_6 | SR3=BY05_C_1_5;SR3=BY05_C_1_6 | SR3=BY02_2_4_1_3;SR3=BY02_2_4_1_4 | BLETC 333 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501295 | MEZZ NO 390 | HCCIBUS-ID000286
13 | BLMEI.C5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A5L3 | BJBAP.A5L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302134 | UJ33=BY02_1_3_4 | HCBLECF001-CR000602 | 1_3_A1;1_3_A2 | UJ33=BY02_B_5;UJ33=BY02_B_6 | SR3=BY05_C_1_5;SR3=BY05_C_1_6 | SR3=BY02_2_4_1_3;SR3=BY02_2_4_1_4 | BLETC 333 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501295 | MEZZ NO 390 | HCCIBUS-ID000286
14 | BLMEI.D5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A5L3 | BJBAP.A5L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302134 | UJ33=BY02_1_3_3 | HCBLECF001-CR000602 | 1_3_A1;1_3_A2 | UJ33=BY02_B_5;UJ33=BY02_B_6 | SR3=BY05_C_1_5;SR3=BY05_C_1_6 | SR3=BY02_2_4_1_3;SR3=BY02_2_4_1_4 | BLETC 333 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501295 | MEZZ NO 390 | HCCIBUS-ID000286
15 | BLMEI.E5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A5L3 | BJBAP.A5L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302134 | UJ33=BY02_1_3_2 | HCBLECF001-CR000602 | 1_3_A1;1_3_A2 | UJ33=BY02_B_5;UJ33=BY02_B_6 | SR3=BY05_C_1_5;SR3=BY05_C_1_6 | SR3=BY02_2_4_1_3;SR3=BY02_2_4_1_4 | BLETC 333 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501295 | MEZZ NO 390 | HCCIBUS-ID000286
16 | BLMEI.F5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A5L3 | BJBAP.A5L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302134 | UJ33=BY02_1_3_1 | HCBLECF001-CR000602 | 1_3_A1;1_3_A2 | UJ33=BY02_B_5;UJ33=BY02_B_6 | SR3=BY05_C_1_5;SR3=BY05_C_1_6 | SR3=BY02_2_4_1_3;SR3=BY02_2_4_1_4 | BLETC 333 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501295 | MEZZ NO 390 | HCCIBUS-ID000286
17 | BLMES.A5L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B5L3 | BJBAP.B5L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302135 | UJ33=BY02_1_4_6 | HCBLECF001-CR000575 | 1_4_A1;1_4_A2 | UJ33=BY02_B_7;UJ33=BY02_B_8 | SR3=BY05_C_1_7;SR3=BY05_C_1_8 | SR3=BY02_2_5_2_1;SR3=BY02_2_5_2_2 | BLETC 334 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501311 | MEZZ NO 391 | HCCIBUS-ID000286
18 | BLMES.B5L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B5L3 | BJBAP.B5L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302135 | UJ33=BY02_1_4_5 | HCBLECF001-CR000575 | 1_4_A1;1_4_A2 | UJ33=BY02_B_7;UJ33=BY02_B_8 | SR3=BY05_C_1_7;SR3=BY05_C_1_8 | SR3=BY02_2_5_2_1;SR3=BY02_2_5_2_2 | BLETC 334 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501311 | MEZZ NO 391 | HCCIBUS-ID000286
19 | BLMES.C5L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B5L3 | BJBAP.B5L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302135 | UJ33=BY02_1_4_4 | HCBLECF001-CR000575 | 1_4_A1;1_4_A2 | UJ33=BY02_B_7;UJ33=BY02_B_8 | SR3=BY05_C_1_7;SR3=BY05_C_1_8 | SR3=BY02_2_5_2_1;SR3=BY02_2_5_2_2 | BLETC 334 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501311 | MEZZ NO 391 | HCCIBUS-ID000286
20 | BLMES.D5L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B5L3 | BJBAP.B5L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302135 | UJ33=BY02_1_4_3 | HCBLECF001-CR000575 | 1_4_A1;1_4_A2 | UJ33=BY02_B_7;UJ33=BY02_B_8 | SR3=BY05_C_1_7;SR3=BY05_C_1_8 | SR3=BY02_2_5_2_1;SR3=BY02_2_5_2_2 | BLETC 334 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501311 | MEZZ NO 391 | HCCIBUS-ID000286
21 | BLMES.E5L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B5L3 | BJBAP.B5L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302135 | UJ33=BY02_1_4_2 | HCBLECF001-CR000575 | 1_4_A1;1_4_A2 | UJ33=BY02_B_7;UJ33=BY02_B_8 | SR3=BY05_C_1_7;SR3=BY05_C_1_8 | SR3=BY02_2_5_2_1;SR3=BY02_2_5_2_2 | BLETC 334 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501311 | MEZZ NO 391 | HCCIBUS-ID000286
22 | BLMES.F5L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B5L3 | BJBAP.B5L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1302135 | UJ33=BY02_1_4_1 | HCBLECF001-CR000575 | 1_4_A1;1_4_A2 | UJ33=BY02_B_7;UJ33=BY02_B_8 | SR3=BY05_C_1_7;SR3=BY05_C_1_8 | SR3=BY02_2_5_2_1;SR3=BY02_2_5_2_2 | BLETC 334 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501311 | MEZZ NO 391 | HCCIBUS-ID000286
23 | BLMEI.G5L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.C5L3 | BJBAP.C5L3_8 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307394 | UJ33=BY02_1_5_8 | HCBLECF001-CR000577 | 1_5_A1;1_5_A2 | UJ33=BY02_B_9;UJ33=BY02_B_10 | SR3=BY05_C_1_9;SR3=BY05_C_1_10 | SR3=BY02_1_4_1_3;SR3=BY02_1_4_1_4 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
24 | BLMEI.H5L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.C5L3 | BJBAP.C5L3_7 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307394 | UJ33=BY02_1_5_7 | HCBLECF001-CR000577 | 1_5_A1;1_5_A2 | UJ33=BY02_B_9;UJ33=BY02_B_10 | SR3=BY05_C_1_9;SR3=BY05_C_1_10 | SR3=BY02_1_4_1_3;SR3=BY02_1_4_1_4 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000286
25 | BLMQI.A5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C5L3 | BJBAP.C5L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307394 | UJ33=BY02_1_5_6 | HCBLECF001-CR000577 | 1_5_A1;1_5_A2 | UJ33=BY02_B_9;UJ33=BY02_B_10 | SR3=BY05_C_1_9;SR3=BY05_C_1_10 | SR3=BY02_1_4_1_3;SR3=BY02_1_4_1_4 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
26 | BLMQI.B5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C5L3 | BJBAP.C5L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307394 | UJ33=BY02_1_5_5 | HCBLECF001-CR000577 | 1_5_A1;1_5_A2 | UJ33=BY02_B_9;UJ33=BY02_B_10 | SR3=BY05_C_1_9;SR3=BY05_C_1_10 | SR3=BY02_1_4_1_3;SR3=BY02_1_4_1_4 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
27 | BLMQI.C5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C5L3 | BJBAP.C5L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307394 | UJ33=BY02_1_5_4 | HCBLECF001-CR000577 | 1_5_A1;1_5_A2 | UJ33=BY02_B_9;UJ33=BY02_B_10 | SR3=BY05_C_1_9;SR3=BY05_C_1_10 | SR3=BY02_1_4_1_3;SR3=BY02_1_4_1_4 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
28 | BLMQI.D5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C5L3 | BJBAP.C5L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307394 | UJ33=BY02_1_5_3 | HCBLECF001-CR000577 | 1_5_A1;1_5_A2 | UJ33=BY02_B_9;UJ33=BY02_B_10 | SR3=BY05_C_1_9;SR3=BY05_C_1_10 | SR3=BY02_1_4_1_3;SR3=BY02_1_4_1_4 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
29 | BLMQI.E5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C5L3 | BJBAP.C5L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307394 | UJ33=BY02_1_5_2 | HCBLECF001-CR000577 | 1_5_A1;1_5_A2 | UJ33=BY02_B_9;UJ33=BY02_B_10 | SR3=BY05_C_1_9;SR3=BY05_C_1_10 | SR3=BY02_1_4_1_3;SR3=BY02_1_4_1_4 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
30 | BLMQI.F5L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C5L3 | BJBAP.C5L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307394 | UJ33=BY02_1_5_1 | HCBLECF001-CR000577 | 1_5_A1;1_5_A2 | UJ33=BY02_B_9;UJ33=BY02_B_10 | SR3=BY05_C_1_9;SR3=BY05_C_1_10 | SR3=BY02_1_4_1_3;SR3=BY02_1_4_1_4 | BLETC 318 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06421128 | MEZZ NO 370 | HCCIBUS-ID000302
31 | BLMES.G5L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.D5L3 | BJBAP.D5L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307395 | UJ33=BY02_1_6_2 | HCBLECF001-CR000666 | 1_6_A1;1_6_A2 | UJ33=BY02_B_11;UJ33=BY02_B_12 | SR3=BY05_C_1_11;SR3=BY05_C_1_12 | SR3=BY02_2_5_2_3;SR3=BY02_2_5_2_4 | BLETC 334 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501311 | MEZZ NO 391 | HCCIBUS-ID000286
32 | BLMES.H5L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.D5L3 | BJBAP.D5L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307395 | UJ33=BY02_1_6_1 | HCBLECF001-CR000666 | 1_6_A1;1_6_A2 | UJ33=BY02_B_11;UJ33=BY02_B_12 | SR3=BY05_C_1_11;SR3=BY05_C_1_12 | SR3=BY02_2_5_2_3;SR3=BY02_2_5_2_4 | BLETC 334 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501311 | MEZZ NO 391 | HCCIBUS-ID000286
33 | BLMEI.A6L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A6L3 | BJBAP.A6L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301136 | UJ33=BY02_1_7_4 | HCBLECF001-CR000536 | 1_7_A1;1_7_A2 | UJ33=BY02_B_13;UJ33=BY02_B_14 | SR3=BY05_C_2_1;SR3=BY05_C_2_2 | SR3=BY02_2_6_3_1;SR3=BY02_2_6_3_2 | BLETC 335 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501309 | MEZZ NO 392 | HCCIBUS-ID000286
34 | BLMEI.B6L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A6L3 | BJBAP.A6L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301136 | UJ33=BY02_1_7_3 | HCBLECF001-CR000536 | 1_7_A1;1_7_A2 | UJ33=BY02_B_13;UJ33=BY02_B_14 | SR3=BY05_C_2_1;SR3=BY05_C_2_2 | SR3=BY02_2_6_3_1;SR3=BY02_2_6_3_2 | BLETC 335 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501309 | MEZZ NO 392 | HCCIBUS-ID000286
35 | BLMEI.C6L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A6L3 | BJBAP.A6L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301136 | UJ33=BY02_1_7_2 | HCBLECF001-CR000536 | 1_7_A1;1_7_A2 | UJ33=BY02_B_13;UJ33=BY02_B_14 | SR3=BY05_C_2_1;SR3=BY05_C_2_2 | SR3=BY02_2_6_3_1;SR3=BY02_2_6_3_2 | BLETC 335 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501309 | MEZZ NO 392 | HCCIBUS-ID000286
36 | BLMEI.D6L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A6L3 | BJBAP.A6L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301136 | UJ33=BY02_1_7_1 | HCBLECF001-CR000536 | 1_7_A1;1_7_A2 | UJ33=BY02_B_13;UJ33=BY02_B_14 | SR3=BY05_C_2_1;SR3=BY05_C_2_2 | SR3=BY02_2_6_3_1;SR3=BY02_2_6_3_2 | BLETC 335 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501309 | MEZZ NO 392 | HCCIBUS-ID000286
37 | BLMES.A6L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B6L3 | BJBAP.B6L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1310425 | UJ33=BY02_1_8_4 | HCBLECF001-CR000629 | 1_8_A1;1_8_A2 | UJ33=BY02_B_15;UJ33=BY02_B_16 | SR3=BY05_C_2_3;SR3=BY05_C_2_4 | SR3=BY02_2_6_3_3;SR3=BY02_2_6_3_4 | BLETC 335 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501309 | MEZZ NO 392 | HCCIBUS-ID000286
38 | BLMES.B6L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B6L3 | BJBAP.B6L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1310425 | UJ33=BY02_1_8_3 | HCBLECF001-CR000629 | 1_8_A1;1_8_A2 | UJ33=BY02_B_15;UJ33=BY02_B_16 | SR3=BY05_C_2_3;SR3=BY05_C_2_4 | SR3=BY02_2_6_3_3;SR3=BY02_2_6_3_4 | BLETC 335 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | M | 1 | CFVM-SR3-BLMC | BLM C06501309 | MEZZ NO 392 | HCCIBUS-ID000302
39 | BLMES.C6L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B6L3 | BJBAP.B6L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1310425 | UJ33=BY02_1_8_2 | HCBLECF001-CR000629 | 1_8_A1;1_8_A2 | UJ33=BY02_B_15;UJ33=BY02_B_16 | SR3=BY05_C_2_3;SR3=BY05_C_2_4 | SR3=BY02_2_6_3_3;SR3=BY02_2_6_3_4 | BLETC 335 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | M | 1 | CFVM-SR3-BLMC | BLM C06501309 | MEZZ NO 392 | HCCIBUS-ID000302
40 | BLMES.D6L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.B6L3 | BJBAP.B6L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1310425 | UJ33=BY02_1_8_1 | HCBLECF001-CR000629 | 1_8_A1;1_8_A2 | UJ33=BY02_B_15;UJ33=BY02_B_16 | SR3=BY05_C_2_3;SR3=BY05_C_2_4 | SR3=BY02_2_6_3_3;SR3=BY02_2_6_3_4 | BLETC 335 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | M | 1 | CFVM-SR3-BLMC | BLM C06501309 | MEZZ NO 392 | HCCIBUS-ID000302
41 | BLMQI.A6L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C6L3 | BJBAP.C6L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301137 | UJ33=BY02_1_9_6 | HCBLECF001-CR000211 | 1_9_A1;1_9_A2 | UJ33=BY02_B_17;UJ33=BY02_B_18 | SR3=BY05_C_2_5;SR3=BY05_C_2_6 | SR3=BY02_1_5_2_1;SR3=BY02_1_5_2_2 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
42 | BLMQI.B6L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C6L3 | BJBAP.C6L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301137 | UJ33=BY02_1_9_5 | HCBLECF001-CR000211 | 1_9_A1;1_9_A2 | UJ33=BY02_B_17;UJ33=BY02_B_18 | SR3=BY05_C_2_5;SR3=BY05_C_2_6 | SR3=BY02_1_5_2_1;SR3=BY02_1_5_2_2 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
43 | BLMQI.C6L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C6L3 | BJBAP.C6L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301137 | UJ33=BY02_1_9_4 | HCBLECF001-CR000211 | 1_9_A1;1_9_A2 | UJ33=BY02_B_17;UJ33=BY02_B_18 | SR3=BY05_C_2_5;SR3=BY05_C_2_6 | SR3=BY02_1_5_2_1;SR3=BY02_1_5_2_2 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
44 | BLMQI.D6L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C6L3 | BJBAP.C6L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301137 | UJ33=BY02_1_9_3 | HCBLECF001-CR000211 | 1_9_A1;1_9_A2 | UJ33=BY02_B_17;UJ33=BY02_B_18 | SR3=BY05_C_2_5;SR3=BY05_C_2_6 | SR3=BY02_1_5_2_1;SR3=BY02_1_5_2_2 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
45 | BLMQI.E6L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C6L3 | BJBAP.C6L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301137 | UJ33=BY02_1_9_2 | HCBLECF001-CR000211 | 1_9_A1;1_9_A2 | UJ33=BY02_B_17;UJ33=BY02_B_18 | SR3=BY05_C_2_5;SR3=BY05_C_2_6 | SR3=BY02_1_5_2_1;SR3=BY02_1_5_2_2 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
46 | BLMQI.A7L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.C6L3 | BJBAP.C6L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301137 | UJ33=BY02_1_9_1 | HCBLECF001-CR000211 | 1_9_A1;1_9_A2 | UJ33=BY02_B_17;UJ33=BY02_B_18 | SR3=BY05_C_2_5;SR3=BY05_C_2_6 | SR3=BY02_1_5_2_1;SR3=BY02_1_5_2_2 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
47 | BLMES.7L3 | In Progress | 2008-06-09 |  |  |  | SEM |  | BJBHT.A7L3 | BJBAP.A7L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301138 | UJ33=BY02_1_10_1 | HCBLECF001-CR000637 | 1_10_A1;1_10_A2 | UJ33=BY02_B_19;UJ33=BY02_B_20 | SR3=BY05_C_2_7;SR3=BY05_C_2_8 | SR3=BY02_2_7_4_1;SR3=BY02_2_7_4_2 | BLETC 336 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501293 | MEZZ NO 393 | HCCIBUS-ID000286
48 | BLMEI.7L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B7L3 | BJBAP.B7L3_7 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301139 | UJ33=BY02_2_1_7 | HCBLECF001-CR000576 | 2_1_A1;2_1_A2 | UJ33=BY02_B_21;UJ33=BY02_B_22 | SR3=BY05_C_2_9;SR3=BY05_C_2_10 | SR3=BY02_1_5_2_3;SR3=BY02_1_5_2_4 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000286
49 | BLMQI.B7L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B7L3 | BJBAP.B7L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301139 | UJ33=BY02_2_1_6 | HCBLECF001-CR000576 | 2_1_A1;2_1_A2 | UJ33=BY02_B_21;UJ33=BY02_B_22 | SR3=BY05_C_2_9;SR3=BY05_C_2_10 | SR3=BY02_1_5_2_3;SR3=BY02_1_5_2_4 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
50 | BLMQI.C7L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B7L3 | BJBAP.B7L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301139 | UJ33=BY02_2_1_5 | HCBLECF001-CR000576 | 2_1_A1;2_1_A2 | UJ33=BY02_B_21;UJ33=BY02_B_22 | SR3=BY05_C_2_9;SR3=BY05_C_2_10 | SR3=BY02_1_5_2_3;SR3=BY02_1_5_2_4 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
51 | BLMQI.D7L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B7L3 | BJBAP.B7L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301139 | UJ33=BY02_2_1_4 | HCBLECF001-CR000576 | 2_1_A1;2_1_A2 | UJ33=BY02_B_21;UJ33=BY02_B_22 | SR3=BY05_C_2_9;SR3=BY05_C_2_10 | SR3=BY02_1_5_2_3;SR3=BY02_1_5_2_4 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
52 | BLMQI.E7L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B7L3 | BJBAP.B7L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301139 | UJ33=BY02_2_1_3 | HCBLECF001-CR000576 | 2_1_A1;2_1_A2 | UJ33=BY02_B_21;UJ33=BY02_B_22 | SR3=BY05_C_2_9;SR3=BY05_C_2_10 | SR3=BY02_1_5_2_3;SR3=BY02_1_5_2_4 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
53 | BLMQI.F7L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B7L3 | BJBAP.B7L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301139 | UJ33=BY02_2_1_2 | HCBLECF001-CR000576 | 2_1_A1;2_1_A2 | UJ33=BY02_B_21;UJ33=BY02_B_22 | SR3=BY05_C_2_9;SR3=BY05_C_2_10 | SR3=BY02_1_5_2_3;SR3=BY02_1_5_2_4 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
54 | BLMQI.A8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B7L3 | BJBAP.B7L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301139 | UJ33=BY02_2_1_1 | HCBLECF001-CR000576 | 2_1_A1;2_1_A2 | UJ33=BY02_B_21;UJ33=BY02_B_22 | SR3=BY05_C_2_9;SR3=BY05_C_2_10 | SR3=BY02_1_5_2_3;SR3=BY02_1_5_2_4 | BLETC 319 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501238 | MEZZ NO 371 | HCCIBUS-ID000302
55 | BLMEI.A8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A8L3 | BJBAP.A8L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307397 | UJ33=BY02_2_2_6 | HCBLECF001-CR000574 | 2_2_A1;2_2_A2 | UJ33=BY02_B_23;UJ33=BY02_B_24 | SR3=BY05_C_2_11;SR3=BY05_C_2_12 | SR3=BY02_2_7_4_3;SR3=BY02_2_7_4_4 | BLETC 336 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501293 | MEZZ NO 393 | HCCIBUS-ID000286
56 | BLMEI.B8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A8L3 | BJBAP.A8L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307397 | UJ33=BY02_2_2_5 | HCBLECF001-CR000574 | 2_2_A1;2_2_A2 | UJ33=BY02_B_23;UJ33=BY02_B_24 | SR3=BY05_C_2_11;SR3=BY05_C_2_12 | SR3=BY02_2_7_4_3;SR3=BY02_2_7_4_4 | BLETC 336 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501293 | MEZZ NO 393 | HCCIBUS-ID000286
57 | BLMEI.C8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A8L3 | BJBAP.A8L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307397 | UJ33=BY02_2_2_4 | HCBLECF001-CR000574 | 2_2_A1;2_2_A2 | UJ33=BY02_B_23;UJ33=BY02_B_24 | SR3=BY05_C_2_11;SR3=BY05_C_2_12 | SR3=BY02_2_7_4_3;SR3=BY02_2_7_4_4 | BLETC 336 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501293 | MEZZ NO 393 | HCCIBUS-ID000286
58 | BLMEI.D8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A8L3 | BJBAP.A8L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307397 | UJ33=BY02_2_2_3 | HCBLECF001-CR000574 | 2_2_A1;2_2_A2 | UJ33=BY02_B_23;UJ33=BY02_B_24 | SR3=BY05_C_2_11;SR3=BY05_C_2_12 | SR3=BY02_2_7_4_3;SR3=BY02_2_7_4_4 | BLETC 336 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501293 | MEZZ NO 393 | HCCIBUS-ID000286
59 | BLMEI.E8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A8L3 | BJBAP.A8L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307397 | UJ33=BY02_2_2_2 | HCBLECF001-CR000574 | 2_2_A1;2_2_A2 | UJ33=BY02_B_23;UJ33=BY02_B_24 | SR3=BY05_C_2_11;SR3=BY05_C_2_12 | SR3=BY02_2_7_4_3;SR3=BY02_2_7_4_4 | BLETC 336 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501293 | MEZZ NO 393 | HCCIBUS-ID000286
60 | BLMEI.F8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A8L3 | BJBAP.A8L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307397 | UJ33=BY02_2_2_1 | HCBLECF001-CR000574 | 2_2_A1;2_2_A2 | UJ33=BY02_B_23;UJ33=BY02_B_24 | SR3=BY05_C_2_11;SR3=BY05_C_2_12 | SR3=BY02_2_7_4_3;SR3=BY02_2_7_4_4 | BLETC 336 | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC | BLM C06501293 | MEZZ NO 393 | HCCIBUS-ID000286
61 | BLMQI.B8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B8L3 | BJBAP.B8L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301140 | UJ33=BY02_2_3_6 | HCBLECF001-CR000672 | 2_3_A1;2_3_A2 | UJ33=BY02_C_1;UJ33=BY02_C_2 | SR3=BY05_C_3_1;SR3=BY05_C_3_2 | SR3=BY02_1_6_3_1;SR3=BY02_1_6_3_2 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
62 | BLMQI.C8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B8L3 | BJBAP.B8L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301140 | UJ33=BY02_2_3_5 | HCBLECF001-CR000672 | 2_3_A1;2_3_A2 | UJ33=BY02_C_1;UJ33=BY02_C_2 | SR3=BY05_C_3_1;SR3=BY05_C_3_2 | SR3=BY02_1_6_3_1;SR3=BY02_1_6_3_2 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
63 | BLMQI.D8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B8L3 | BJBAP.B8L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301140 | UJ33=BY02_2_3_4 | HCBLECF001-CR000672 | 2_3_A1;2_3_A2 | UJ33=BY02_C_1;UJ33=BY02_C_2 | SR3=BY05_C_3_1;SR3=BY05_C_3_2 | SR3=BY02_1_6_3_1;SR3=BY02_1_6_3_2 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
64 | BLMQI.E8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B8L3 | BJBAP.B8L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301140 | UJ33=BY02_2_3_3 | HCBLECF001-CR000672 | 2_3_A1;2_3_A2 | UJ33=BY02_C_1;UJ33=BY02_C_2 | SR3=BY05_C_3_1;SR3=BY05_C_3_2 | SR3=BY02_1_6_3_1;SR3=BY02_1_6_3_2 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
65 | BLMQI.F8L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B8L3 | BJBAP.B8L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301140 | UJ33=BY02_2_3_2 | HCBLECF001-CR000672 | 2_3_A1;2_3_A2 | UJ33=BY02_C_1;UJ33=BY02_C_2 | SR3=BY05_C_3_1;SR3=BY05_C_3_2 | SR3=BY02_1_6_3_1;SR3=BY02_1_6_3_2 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
66 | BLMQI.A9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B8L3 | BJBAP.B8L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301140 | UJ33=BY02_2_3_1 | HCBLECF001-CR000672 | 2_3_A1;2_3_A2 | UJ33=BY02_C_1;UJ33=BY02_C_2 | SR3=BY05_C_3_1;SR3=BY05_C_3_2 | SR3=BY02_1_6_3_1;SR3=BY02_1_6_3_2 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
67 | BLMEI.A9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A9L3 | BJBAP.A9L3_8 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1309798 | UJ33=BY02_2_4_8 | HCBLECF001-CR000609 | 2_4_A1;2_4_A2 | UJ33=BY02_C_3;UJ33=BY02_C_4 | SR3=BY05_C_3_3;SR3=BY05_C_3_4 | SR3=BY02_2_8_5_1;SR3=BY02_2_8_5_2 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
68 | BLMEI.B9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A9L3 | BJBAP.A9L3_108 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1309798 | UJ33=BY02_2_4_108 | HCBLECF001-CR000609 | 2_4_A1;2_4_A2 | UJ33=BY02_C_3;UJ33=BY02_C_4 | SR3=BY05_C_3_3;SR3=BY05_C_3_4 | SR3=BY02_2_8_5_1;SR3=BY02_2_8_5_2 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
69 | BLMEI.C9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A9L3 | BJBAP.A9L3_7 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1309798 | UJ33=BY02_2_4_7 | HCBLECF001-CR000609 | 2_4_A1;2_4_A2 | UJ33=BY02_C_3;UJ33=BY02_C_4 | SR3=BY05_C_3_3;SR3=BY05_C_3_4 | SR3=BY02_2_8_5_1;SR3=BY02_2_8_5_2 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
70 | BLMEI.D9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A9L3 | BJBAP.A9L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1309798 | UJ33=BY02_2_4_6 | HCBLECF001-CR000609 | 2_4_A1;2_4_A2 | UJ33=BY02_C_3;UJ33=BY02_C_4 | SR3=BY05_C_3_3;SR3=BY05_C_3_4 | SR3=BY02_2_8_5_1;SR3=BY02_2_8_5_2 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
71 | BLMEI.E9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A9L3 | BJBAP.A9L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1309798 | UJ33=BY02_2_4_5 | HCBLECF001-CR000609 | 2_4_A1;2_4_A2 | UJ33=BY02_C_3;UJ33=BY02_C_4 | SR3=BY05_C_3_3;SR3=BY05_C_3_4 | SR3=BY02_2_8_5_1;SR3=BY02_2_8_5_2 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
72 | BLMEI.F9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A9L3 | BJBAP.A9L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1309798 | UJ33=BY02_2_4_4 | HCBLECF001-CR000609 | 2_4_A1;2_4_A2 | UJ33=BY02_C_3;UJ33=BY02_C_4 | SR3=BY05_C_3_3;SR3=BY05_C_3_4 | SR3=BY02_2_8_5_1;SR3=BY02_2_8_5_2 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
73 | BLMEI.G9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A9L3 | BJBAP.A9L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1309798 | UJ33=BY02_2_4_3 | HCBLECF001-CR000609 | 2_4_A1;2_4_A2 | UJ33=BY02_C_3;UJ33=BY02_C_4 | SR3=BY05_C_3_3;SR3=BY05_C_3_4 | SR3=BY02_2_8_5_1;SR3=BY02_2_8_5_2 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
74 | BLMEI.H9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A9L3 | BJBAP.A9L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1309798 | UJ33=BY02_2_4_2 | HCBLECF001-CR000609 | 2_4_A1;2_4_A2 | UJ33=BY02_C_3;UJ33=BY02_C_4 | SR3=BY05_C_3_3;SR3=BY05_C_3_4 | SR3=BY02_2_8_5_1;SR3=BY02_2_8_5_2 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
75 | BLMEI.I9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A9L3 | BJBAP.A9L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1309798 | UJ33=BY02_2_4_1 | HCBLECF001-CR000609 | 2_4_A1;2_4_A2 | UJ33=BY02_C_3;UJ33=BY02_C_4 | SR3=BY05_C_3_3;SR3=BY05_C_3_4 | SR3=BY02_2_8_5_1;SR3=BY02_2_8_5_2 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
76 | BLMEI.J9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A9L3 | BJBAP.A9L3_101 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1309798 | UJ33=BY02_2_4_101 | HCBLECF001-CR000609 | 2_4_A1;2_4_A2 | UJ33=BY02_C_3;UJ33=BY02_C_4 | SR3=BY05_C_3_3;SR3=BY05_C_3_4 | SR3=BY02_2_8_5_1;SR3=BY02_2_8_5_2 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
77 | BLMEI.A10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_8 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_8 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000286
78 | BLMEI.B10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_108 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_108 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000286
79 | BLMEI.C10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_7 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_7 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000286
80 | BLMEI.D10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_107 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_107 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000286
81 | BLMQI.B9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_6 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000286
82 | BLMQI.C9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_5 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
83 | BLMQI.D9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_4 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
84 | BLMQI.E9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_3 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
85 | BLMQI.G9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_2 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
86 | BLMQI.F9L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_101 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_101 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M |  | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
87 | BLMQI.A10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B9L3 | BJBAP.B9L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301141 | UJ33=BY02_2_5_1 | HCBLECF001-CR000754 | 2_5_A1;2_5_A2 | UJ33=BY02_C_5;UJ33=BY02_C_6 | SR3=BY05_C_3_5;SR3=BY05_C_3_6 | SR3=BY02_1_6_3_3;SR3=BY02_1_6_3_4 | BLETC 320 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501292 | MEZZ NO 377 | HCCIBUS-ID000302
88 | BLMEI.E10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_8 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_8 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000286
89 | BLMEI.F10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_108 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_108 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000286
90 | BLMEI.G10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_7 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_7 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000286
91 | BLMEI.H10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_107 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_107 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000286
92 | BLMQI.B10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_6 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
93 | BLMQI.C10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_5 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
94 | BLMQI.D10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_4 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
95 | BLMQI.E10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_3 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
96 | BLMQI.G10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_2 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
97 | BLMQI.F10L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_101 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_101 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
98 | BLMQI.A11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A10L3 | BJBAP.A10L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301142 | UJ33=BY02_2_6_1 | HCBLECF001-CR000674 | 2_6_A1;2_6_A2 | UJ33=BY02_C_7;UJ33=BY02_C_8 | SR3=BY05_C_3_7;SR3=BY05_C_3_8 | SR3=BY02_1_7_4_1;SR3=BY02_1_7_4_2 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
99 | BLMEI.A11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_6 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
100 | BLMEI.B11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_106 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_106 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
101 | BLMEI.C11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_5 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
102 | BLMEI.D11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_105 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_105 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
103 | BLMEI.E11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_4 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
104 | BLMEI.F11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_104 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_104 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
105 | BLMEI.G11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_3 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
106 | BLMEI.H11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_103 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_103 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
107 | BLMEI.I11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_2 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
108 | BLMEI.J11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_102 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_102 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
109 | BLMEI.K11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_1 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
110 | BLMEI.L11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A11L3 | BJBAP.A11L3_101 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1307398 | UJ33=BY02_2_7_101 | HCBLECF001-CR000654 | 2_7_A1;2_7_A2 | UJ33=BY02_C_9;UJ33=BY02_C_10 | SR3=BY05_C_3_9;SR3=BY05_C_3_10 | SR3=BY02_2_8_5_3;SR3=BY02_2_8_5_4 |  | CFV-SR3-BLMC | 71720078 | SN: 71300220 | 71470078 | CH62402717 | 147 |  |  |  | U | 1 | CFVM-SR3-BLMC |  |  | HCCIBUS-ID000286
111 | BLMQI.G11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B11L3 | BJBAP.B11L3_7 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301143 | UJ33=BY02_2_8_7 | HCBLECF001-CR000657 | 2_8_A1;2_8_A2 | UJ33=BY02_C_11;UJ33=BY02_C_12 | SR3=BY05_C_3_11;SR3=BY05_C_3_12 | SR3=BY02_1_7_4_3;SR3=BY02_1_7_4_4 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
112 | BLMQI.B11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B11L3 | BJBAP.B11L3_6 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301143 | UJ33=BY02_2_8_6 | HCBLECF001-CR000657 | 2_8_A1;2_8_A2 | UJ33=BY02_C_11;UJ33=BY02_C_12 | SR3=BY05_C_3_11;SR3=BY05_C_3_12 | SR3=BY02_1_7_4_3;SR3=BY02_1_7_4_4 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
113 | BLMQI.C11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B11L3 | BJBAP.B11L3_5 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301143 | UJ33=BY02_2_8_5 | HCBLECF001-CR000657 | 2_8_A1;2_8_A2 | UJ33=BY02_C_11;UJ33=BY02_C_12 | SR3=BY05_C_3_11;SR3=BY05_C_3_12 | SR3=BY02_1_7_4_3;SR3=BY02_1_7_4_4 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
114 | BLMQI.D11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B11L3 | BJBAP.B11L3_4 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301143 | UJ33=BY02_2_8_4 | HCBLECF001-CR000657 | 2_8_A1;2_8_A2 | UJ33=BY02_C_11;UJ33=BY02_C_12 | SR3=BY05_C_3_11;SR3=BY05_C_3_12 | SR3=BY02_1_7_4_3;SR3=BY02_1_7_4_4 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
115 | BLMQI.E11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B11L3 | BJBAP.B11L3_3 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301143 | UJ33=BY02_2_8_3 | HCBLECF001-CR000657 | 2_8_A1;2_8_A2 | UJ33=BY02_C_11;UJ33=BY02_C_12 | SR3=BY05_C_3_11;SR3=BY05_C_3_12 | SR3=BY02_1_7_4_3;SR3=BY02_1_7_4_4 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
116 | BLMQI.F11L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B11L3 | BJBAP.B11L3_2 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301143 | UJ33=BY02_2_8_2 | HCBLECF001-CR000657 | 2_8_A1;2_8_A2 | UJ33=BY02_C_11;UJ33=BY02_C_12 | SR3=BY05_C_3_11;SR3=BY05_C_3_12 | SR3=BY02_1_7_4_3;SR3=BY02_1_7_4_4 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
117 | BLMQI.A12L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.B11L3 | BJBAP.B11L3_1 |  |  |  | In Progress | 2008-06-09 |  |  |  | 1301143 | UJ33=BY02_2_8_1 | HCBLECF001-CR000657 | 2_8_A1;2_8_A2 | UJ33=BY02_C_11;UJ33=BY02_C_12 | SR3=BY05_C_3_11;SR3=BY05_C_3_12 | SR3=BY02_1_7_4_3;SR3=BY02_1_7_4_4 | BLETC 321 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501220 | MEZZ NO 378 | HCCIBUS-ID000302
118 | BLMEI.A13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A12L3 |  | HCBYPLM001-CR000090 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A12L3_CFC_8 | HCBLECF001-CR000703 | CFC_A1;CFC_A2 | BYPLM.A12L3_7;BYPLM.A12L3_8 | SR3=BY05_F_1_7;SR3=BY05_F_1_8 | SR3=BY02_1_8_5_1;SR3=BY02_1_8_5_2 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000286
119 | BLMEI.B13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A12L3 |  | HCBYPLM001-CR000090 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A12L3_CFC_108 | HCBLECF001-CR000703 | CFC_A1;CFC_A2 | BYPLM.A12L3_7;BYPLM.A12L3_8 | SR3=BY05_F_1_7;SR3=BY05_F_1_8 | SR3=BY02_1_8_5_1;SR3=BY02_1_8_5_2 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000286
120 | BLMEI.C13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A12L3 |  | HCBYPLM001-CR000090 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A12L3_CFC_7 | HCBLECF001-CR000703 | CFC_A1;CFC_A2 | BYPLM.A12L3_7;BYPLM.A12L3_8 | SR3=BY05_F_1_7;SR3=BY05_F_1_8 | SR3=BY02_1_8_5_1;SR3=BY02_1_8_5_2 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000286
121 | BLMEI.D13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A12L3 |  | HCBYPLM001-CR000090 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A12L3_CFC_107 | HCBLECF001-CR000703 | CFC_A1;CFC_A2 | BYPLM.A12L3_7;BYPLM.A12L3_8 | SR3=BY05_F_1_7;SR3=BY05_F_1_8 | SR3=BY02_1_8_5_1;SR3=BY02_1_8_5_2 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000286
122 | BLMQI.B12L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A12L3 |  | HCBYPLM001-CR000090 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A12L3_CFC_6 | HCBLECF001-CR000703 | CFC_A1;CFC_A2 | BYPLM.A12L3_7;BYPLM.A12L3_8 | SR3=BY05_F_1_7;SR3=BY05_F_1_8 | SR3=BY02_1_8_5_1;SR3=BY02_1_8_5_2 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
123 | BLMQI.C12L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A12L3 |  | HCBYPLM001-CR000090 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A12L3_CFC_5 | HCBLECF001-CR000703 | CFC_A1;CFC_A2 | BYPLM.A12L3_7;BYPLM.A12L3_8 | SR3=BY05_F_1_7;SR3=BY05_F_1_8 | SR3=BY02_1_8_5_1;SR3=BY02_1_8_5_2 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
124 | BLMQI.D12L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A12L3 |  | HCBYPLM001-CR000090 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A12L3_CFC_4 | HCBLECF001-CR000703 | CFC_A1;CFC_A2 | BYPLM.A12L3_7;BYPLM.A12L3_8 | SR3=BY05_F_1_7;SR3=BY05_F_1_8 | SR3=BY02_1_8_5_1;SR3=BY02_1_8_5_2 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
125 | BLMQI.E12L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A12L3 |  | HCBYPLM001-CR000090 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A12L3_CFC_3 | HCBLECF001-CR000703 | CFC_A1;CFC_A2 | BYPLM.A12L3_7;BYPLM.A12L3_8 | SR3=BY05_F_1_7;SR3=BY05_F_1_8 | SR3=BY02_1_8_5_1;SR3=BY02_1_8_5_2 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
126 | BLMQI.F12L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A12L3 |  | HCBYPLM001-CR000090 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A12L3_CFC_2 | HCBLECF001-CR000703 | CFC_A1;CFC_A2 | BYPLM.A12L3_7;BYPLM.A12L3_8 | SR3=BY05_F_1_7;SR3=BY05_F_1_8 | SR3=BY02_1_8_5_1;SR3=BY02_1_8_5_2 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
127 | BLMQI.A13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A12L3 |  | HCBYPLM001-CR000090 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A12L3_CFC_1 | HCBLECF001-CR000703 | CFC_A1;CFC_A2 | BYPLM.A12L3_7;BYPLM.A12L3_8 | SR3=BY05_F_1_7;SR3=BY05_F_1_8 | SR3=BY02_1_8_5_1;SR3=BY02_1_8_5_2 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
128 | BLMEI.E13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A13L3 |  | HCBYPLM001-CR000089 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A13L3_CFC_8 | HCBLECF001-CR000600 | CFC_A1;CFC_A2 | BYPLM.A13L3_7;BYPLM.A13L3_8 | SR3=BY05_F_2_7;SR3=BY05_F_2_8 | SR3=BY02_1_8_5_3;SR3=BY02_1_8_5_4 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000286
129 | BLMEI.F13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A13L3 |  | HCBYPLM001-CR000089 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A13L3_CFC_108 | HCBLECF001-CR000600 | CFC_A1;CFC_A2 | BYPLM.A13L3_7;BYPLM.A13L3_8 | SR3=BY05_F_2_7;SR3=BY05_F_2_8 | SR3=BY02_1_8_5_3;SR3=BY02_1_8_5_4 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000286
130 | BLMEI.G13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A13L3 |  | HCBYPLM001-CR000089 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A13L3_CFC_7 | HCBLECF001-CR000600 | CFC_A1;CFC_A2 | BYPLM.A13L3_7;BYPLM.A13L3_8 | SR3=BY05_F_2_7;SR3=BY05_F_2_8 | SR3=BY02_1_8_5_3;SR3=BY02_1_8_5_4 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000286
131 | BLMEI.H13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A13L3 |  | HCBYPLM001-CR000089 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A13L3_CFC_107 | HCBLECF001-CR000600 | CFC_A1;CFC_A2 | BYPLM.A13L3_7;BYPLM.A13L3_8 | SR3=BY05_F_2_7;SR3=BY05_F_2_8 | SR3=BY02_1_8_5_3;SR3=BY02_1_8_5_4 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | U | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000286
132 | BLMQI.B13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A13L3 |  | HCBYPLM001-CR000089 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A13L3_CFC_6 | HCBLECF001-CR000600 | CFC_A1;CFC_A2 | BYPLM.A13L3_7;BYPLM.A13L3_8 | SR3=BY05_F_2_7;SR3=BY05_F_2_8 | SR3=BY02_1_8_5_3;SR3=BY02_1_8_5_4 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
133 | BLMQI.C13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A13L3 |  | HCBYPLM001-CR000089 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A13L3_CFC_5 | HCBLECF001-CR000600 | CFC_A1;CFC_A2 | BYPLM.A13L3_7;BYPLM.A13L3_8 | SR3=BY05_F_2_7;SR3=BY05_F_2_8 | SR3=BY02_1_8_5_3;SR3=BY02_1_8_5_4 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
134 | BLMQI.D13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A13L3 |  | HCBYPLM001-CR000089 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A13L3_CFC_4 | HCBLECF001-CR000600 | CFC_A1;CFC_A2 | BYPLM.A13L3_7;BYPLM.A13L3_8 | SR3=BY05_F_2_7;SR3=BY05_F_2_8 | SR3=BY02_1_8_5_3;SR3=BY02_1_8_5_4 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
135 | BLMQI.E13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A13L3 |  | HCBYPLM001-CR000089 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A13L3_CFC_3 | HCBLECF001-CR000600 | CFC_A1;CFC_A2 | BYPLM.A13L3_7;BYPLM.A13L3_8 | SR3=BY05_F_2_7;SR3=BY05_F_2_8 | SR3=BY02_1_8_5_3;SR3=BY02_1_8_5_4 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
136 | BLMQI.F13L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A13L3 |  | HCBYPLM001-CR000089 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A13L3_CFC_2 | HCBLECF001-CR000600 | CFC_A1;CFC_A2 | BYPLM.A13L3_7;BYPLM.A13L3_8 | SR3=BY05_F_2_7;SR3=BY05_F_2_8 | SR3=BY02_1_8_5_3;SR3=BY02_1_8_5_4 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302
137 | BLMQI.A14L3 | In Progress | 2008-06-09 |  |  |  | IC |  | BJBHT.A13L3 |  | HCBYPLM001-CR000089 |  |  | In Progress | 2008-06-09 |  |  |  |  | BYPLM.A13L3_CFC_1 | HCBLECF001-CR000600 | CFC_A1;CFC_A2 | BYPLM.A13L3_7;BYPLM.A13L3_8 | SR3=BY05_F_2_7;SR3=BY05_F_2_8 | SR3=BY02_1_8_5_3;SR3=BY02_1_8_5_4 | BLETC 322 | CFV-SR3-BLML | 71720067 | SN: 71300209 | 71470079 | CH62402724 | 146 |  |  |  | M | 1 | CFVM-SR3-BLML | BLM C06501297 | MEZZ NO 379 | HCCIBUS-ID000302