## HWC for BLM
Beam Loss Monitor HWC
Once completed. send this file Jacek.Szkutnik@cern.ch Empty fields will remain untouch in MTF DB Non empty fields will be updated (when allowed) on MTF DB -> Just fill modified fileds! DO NOT ALTER THIS TEMPLATE - You can just insert lines for new slots if necessary Remove given Examples!
Identification |  | 10-BLM channel check (leakage. bias current) | [7 empty] | [Patch_Input] |  | pA | pA | 20-BLM Acquisition Chain Desription | [5 empty] | [Loc=Ra_Cr_CFC_In] |  | [Cr_CFC_Out] | [Loc=Ra_Pa_In] | [Loc=Ra_Pa_Sl_Out] | [Loc=Ra_VME_Si_DAB_In] | [18 empty] | 30-BLM Acquisition Chain Test via test signal |  |  |  |  | pA | pA | 40-BLM HV modulation Test |  |  |  |  | V | Hz | ° |  | pA | 50-BLM Acquisition Chain Test via RA Source |  |  |  |  | pA | 60-BLM Interlock Test | [8 empty] | 70-BLM EMC Test |  |  |  |  | pA | pA | 80-BLM Beam Energy reception Test |  |  |  |  | EDMS Document Number
Official Slot Name |  | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Monitor Type | Monitor Identificator | HV Patch | BJBAP Input | Tunnel Mini Rack Id. | LC(offset) w/cable&M-r | Signal via source w/cable | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | BJBAP Cable Number | Analog Front End | BLECF Identificator | Opt Link Analog FE | Opt Link Patch Tunnel | Opt Link Patch Surface | Opt Link Digital Acq. | VME BLETC Id. | VME CPU Host Name | VME Crate Id. | VME Fantray Id. | VME Power Supply Id. | VME CPU Id. | VME BOBR Id. | VME BLECS Id. | VME BLETC Serial | VME BLECS Serial | Monitor Function | Monitor Status | VME Fantray Hostname | DAB card Id. | Mezzanine card Id. | CIBU Id. | FPGA firmware vers(BLETC) | FPGA firmware vers(BLECS) | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Test:100pA/84 sec run.sum | Test:10pA/84 sec run.sum | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Set voltage: peak-peak | Set frequency | Resulting phase | Resulting Gain | Current signal: peak-peak | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Signal Current | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Threshold/Ch Matrix Test | TTable User Beam Permit T | UBP Check BLETC to BLECS | UBP Check BLECS to CIBU | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Test EMC/40 µs run.sum | Test EMC/1.3 sec run.sum | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments
138 | BLMQI.B14R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001521 | BJBHT.A14R3 |  | HCBYPLM001-CR000093 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A14R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A14R3_7;BYPLM.A14R3_8 | SR3=BY05_F_10_7;SR3=BY05_F_10_8 | SR3=BY02_3_9_6_1;SR3=BY02_3_9_6_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
139 | BLMQI.C14R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001496 | BJBHT.A14R3 |  | HCBYPLM001-CR000093 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A14R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A14R3_7;BYPLM.A14R3_8 | SR3=BY05_F_10_7;SR3=BY05_F_10_8 | SR3=BY02_3_9_6_1;SR3=BY02_3_9_6_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
140 | BLMQI.D14R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001554 | BJBHT.A14R3 |  | HCBYPLM001-CR000093 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A14R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A14R3_7;BYPLM.A14R3_8 | SR3=BY05_F_10_7;SR3=BY05_F_10_8 | SR3=BY02_3_9_6_1;SR3=BY02_3_9_6_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
141 | BLMQI.E14R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001738 | BJBHT.A14R3 |  | HCBYPLM001-CR000093 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A14R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A14R3_7;BYPLM.A14R3_8 | SR3=BY05_F_10_7;SR3=BY05_F_10_8 | SR3=BY02_3_9_6_1;SR3=BY02_3_9_6_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
142 | BLMQI.F14R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001751 | BJBHT.A14R3 |  | HCBYPLM001-CR000093 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A14R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A14R3_7;BYPLM.A14R3_8 | SR3=BY05_F_10_7;SR3=BY05_F_10_8 | SR3=BY02_3_9_6_1;SR3=BY02_3_9_6_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
143 | BLMQI.A15R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001760 | BJBHT.A14R3 |  | HCBYPLM001-CR000093 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A14R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A14R3_7;BYPLM.A14R3_8 | SR3=BY05_F_10_7;SR3=BY05_F_10_8 | SR3=BY02_3_9_6_1;SR3=BY02_3_9_6_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
144 | BLMQI.B15R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001745 | BJBHT.A15R3 |  | HCBYPLM001-CR000094 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A15R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A15R3_7;BYPLM.A15R3_8 | SR3=BY05_F_11_7;SR3=BY05_F_11_8 | SR3=BY02_3_9_6_3;SR3=BY02_3_9_6_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
145 | BLMQI.C15R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001542 | BJBHT.A15R3 |  | HCBYPLM001-CR000094 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A15R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A15R3_7;BYPLM.A15R3_8 | SR3=BY05_F_11_7;SR3=BY05_F_11_8 | SR3=BY02_3_9_6_3;SR3=BY02_3_9_6_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
146 | BLMQI.D15R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001506 | BJBHT.A15R3 |  | HCBYPLM001-CR000094 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A15R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A15R3_7;BYPLM.A15R3_8 | SR3=BY05_F_11_7;SR3=BY05_F_11_8 | SR3=BY02_3_9_6_3;SR3=BY02_3_9_6_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
147 | BLMQI.E15R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001570 | BJBHT.A15R3 |  | HCBYPLM001-CR000094 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A15R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A15R3_7;BYPLM.A15R3_8 | SR3=BY05_F_11_7;SR3=BY05_F_11_8 | SR3=BY02_3_9_6_3;SR3=BY02_3_9_6_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
148 | BLMQI.F15R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001846 | BJBHT.A15R3 |  | HCBYPLM001-CR000094 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A15R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A15R3_7;BYPLM.A15R3_8 | SR3=BY05_F_11_7;SR3=BY05_F_11_8 | SR3=BY02_3_9_6_3;SR3=BY02_3_9_6_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
149 | BLMQI.A16R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001536 | BJBHT.A15R3 |  | HCBYPLM001-CR000094 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A15R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A15R3_7;BYPLM.A15R3_8 | SR3=BY05_F_11_7;SR3=BY05_F_11_8 | SR3=BY02_3_9_6_3;SR3=BY02_3_9_6_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
150 | BLMQI.B16R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001798 | BJBHT.A16R3 |  | HCBYPLM001-CR000095 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A16R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A16R3_7;BYPLM.A16R3_8 | SR3=BY05_F_12_7;SR3=BY05_F_12_8 | SR3=BY02_3_10_7_1;SR3=BY02_3_10_7_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
151 | BLMQI.C16R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001487 | BJBHT.A16R3 |  | HCBYPLM001-CR000095 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A16R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A16R3_7;BYPLM.A16R3_8 | SR3=BY05_F_12_7;SR3=BY05_F_12_8 | SR3=BY02_3_10_7_1;SR3=BY02_3_10_7_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
152 | BLMQI.D16R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001797 | BJBHT.A16R3 |  | HCBYPLM001-CR000095 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A16R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A16R3_7;BYPLM.A16R3_8 | SR3=BY05_F_12_7;SR3=BY05_F_12_8 | SR3=BY02_3_10_7_1;SR3=BY02_3_10_7_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
153 | BLMQI.E16R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001800 | BJBHT.A16R3 |  | HCBYPLM001-CR000095 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A16R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A16R3_7;BYPLM.A16R3_8 | SR3=BY05_F_12_7;SR3=BY05_F_12_8 | SR3=BY02_3_10_7_1;SR3=BY02_3_10_7_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
154 | BLMQI.F16R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001886 | BJBHT.A16R3 |  | HCBYPLM001-CR000095 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A16R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A16R3_7;BYPLM.A16R3_8 | SR3=BY05_F_12_7;SR3=BY05_F_12_8 | SR3=BY02_3_10_7_1;SR3=BY02_3_10_7_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
155 | BLMQI.A17R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001522 | BJBHT.A16R3 |  | HCBYPLM001-CR000095 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A16R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A16R3_7;BYPLM.A16R3_8 | SR3=BY05_F_12_7;SR3=BY05_F_12_8 | SR3=BY02_3_10_7_1;SR3=BY02_3_10_7_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
156 | BLMQI.B17R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001731 | BJBHT.A17R3 |  | HCBYPLM001-CR000096 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A17R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A17R3_7;BYPLM.A17R3_8 | SR3=BY05_G_7_7;SR3=BY05_G_7_8 | SR3=BY02_3_10_7_3;SR3=BY02_3_10_7_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
157 | BLMQI.C17R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001550 | BJBHT.A17R3 |  | HCBYPLM001-CR000096 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A17R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A17R3_7;BYPLM.A17R3_8 | SR3=BY05_G_7_7;SR3=BY05_G_7_8 | SR3=BY02_3_10_7_3;SR3=BY02_3_10_7_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
158 | BLMQI.D17R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001817 | BJBHT.A17R3 |  | HCBYPLM001-CR000096 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A17R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A17R3_7;BYPLM.A17R3_8 | SR3=BY05_G_7_7;SR3=BY05_G_7_8 | SR3=BY02_3_10_7_3;SR3=BY02_3_10_7_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
159 | BLMQI.E17R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001748 | BJBHT.A17R3 |  | HCBYPLM001-CR000096 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A17R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A17R3_7;BYPLM.A17R3_8 | SR3=BY05_G_7_7;SR3=BY05_G_7_8 | SR3=BY02_3_10_7_3;SR3=BY02_3_10_7_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
160 | BLMQI.F17R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001770 | BJBHT.A17R3 |  | HCBYPLM001-CR000096 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A17R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A17R3_7;BYPLM.A17R3_8 | SR3=BY05_G_7_7;SR3=BY05_G_7_8 | SR3=BY02_3_10_7_3;SR3=BY02_3_10_7_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
161 | BLMQI.A18R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001791 | BJBHT.A17R3 |  | HCBYPLM001-CR000096 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A17R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A17R3_7;BYPLM.A17R3_8 | SR3=BY05_G_7_7;SR3=BY05_G_7_8 | SR3=BY02_3_10_7_3;SR3=BY02_3_10_7_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
162 | BLMQI.B18R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001540 | BJBHT.A18R3 |  | HCBYPLM001-CR000097 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A18R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A18R3_7;BYPLM.A18R3_8 | SR3=BY05_G_8_7;SR3=BY05_G_8_8 | SR3=BY02_3_11_8_1;SR3=BY02_3_11_8_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
163 | BLMQI.C18R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001509 | BJBHT.A18R3 |  | HCBYPLM001-CR000097 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A18R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A18R3_7;BYPLM.A18R3_8 | SR3=BY05_G_8_7;SR3=BY05_G_8_8 | SR3=BY02_3_11_8_1;SR3=BY02_3_11_8_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
164 | BLMQI.D18R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001826 | BJBHT.A18R3 |  | HCBYPLM001-CR000097 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A18R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A18R3_7;BYPLM.A18R3_8 | SR3=BY05_G_8_7;SR3=BY05_G_8_8 | SR3=BY02_3_11_8_1;SR3=BY02_3_11_8_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
165 | BLMQI.E18R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001802 | BJBHT.A18R3 |  | HCBYPLM001-CR000097 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A18R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A18R3_7;BYPLM.A18R3_8 | SR3=BY05_G_8_7;SR3=BY05_G_8_8 | SR3=BY02_3_11_8_1;SR3=BY02_3_11_8_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
166 | BLMQI.F18R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001494 | BJBHT.A18R3 |  | HCBYPLM001-CR000097 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A18R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A18R3_7;BYPLM.A18R3_8 | SR3=BY05_G_8_7;SR3=BY05_G_8_8 | SR3=BY02_3_11_8_1;SR3=BY02_3_11_8_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
167 | BLMQI.A19R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001829 | BJBHT.A18R3 |  | HCBYPLM001-CR000097 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A18R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A18R3_7;BYPLM.A18R3_8 | SR3=BY05_G_8_7;SR3=BY05_G_8_8 | SR3=BY02_3_11_8_1;SR3=BY02_3_11_8_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
168 | BLMQI.B19R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001409 | BJBHT.A19R3 |  | HCBYPLM001-CR000098 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A19R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A19R3_7;BYPLM.A19R3_8 | SR3=BY05_G_9_7;SR3=BY05_G_9_8 | SR3=BY02_3_11_8_3;SR3=BY02_3_11_8_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
169 | BLMQI.C19R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001543 | BJBHT.A19R3 |  | HCBYPLM001-CR000098 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A19R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A19R3_7;BYPLM.A19R3_8 | SR3=BY05_G_9_7;SR3=BY05_G_9_8 | SR3=BY02_3_11_8_3;SR3=BY02_3_11_8_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
170 | BLMQI.D19R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001533 | BJBHT.A19R3 |  | HCBYPLM001-CR000098 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A19R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A19R3_7;BYPLM.A19R3_8 | SR3=BY05_G_9_7;SR3=BY05_G_9_8 | SR3=BY02_3_11_8_3;SR3=BY02_3_11_8_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
171 | BLMQI.E19R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001531 | BJBHT.A19R3 |  | HCBYPLM001-CR000098 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A19R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A19R3_7;BYPLM.A19R3_8 | SR3=BY05_G_9_7;SR3=BY05_G_9_8 | SR3=BY02_3_11_8_3;SR3=BY02_3_11_8_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
172 | BLMQI.F19R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001776 | BJBHT.A19R3 |  | HCBYPLM001-CR000098 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A19R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A19R3_7;BYPLM.A19R3_8 | SR3=BY05_G_9_7;SR3=BY05_G_9_8 | SR3=BY02_3_11_8_3;SR3=BY02_3_11_8_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
173 | BLMQI.A20R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001495 | BJBHT.A19R3 |  | HCBYPLM001-CR000098 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A19R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A19R3_7;BYPLM.A19R3_8 | SR3=BY05_G_9_7;SR3=BY05_G_9_8 | SR3=BY02_3_11_8_3;SR3=BY02_3_11_8_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
174 | BLMQI.B20R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001525 | BJBHT.A20R3 |  | HCBYPLM001-CR000099 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A20R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A20R3_7;BYPLM.A20R3_8 | SR3=BY05_G_10_7;SR3=BY05_G_10_8 | SR3=BY02_3_13_9_1;SR3=BY02_3_13_9_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
175 | BLMQI.C20R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001503 | BJBHT.A20R3 |  | HCBYPLM001-CR000099 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A20R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A20R3_7;BYPLM.A20R3_8 | SR3=BY05_G_10_7;SR3=BY05_G_10_8 | SR3=BY02_3_13_9_1;SR3=BY02_3_13_9_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
176 | BLMQI.D20R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001538 | BJBHT.A20R3 |  | HCBYPLM001-CR000099 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A20R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A20R3_7;BYPLM.A20R3_8 | SR3=BY05_G_10_7;SR3=BY05_G_10_8 | SR3=BY02_3_13_9_1;SR3=BY02_3_13_9_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
177 | BLMQI.E20R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001572 | BJBHT.A20R3 |  | HCBYPLM001-CR000099 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A20R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A20R3_7;BYPLM.A20R3_8 | SR3=BY05_G_10_7;SR3=BY05_G_10_8 | SR3=BY02_3_13_9_1;SR3=BY02_3_13_9_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
178 | BLMQI.F20R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001548 | BJBHT.A20R3 |  | HCBYPLM001-CR000099 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A20R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A20R3_7;BYPLM.A20R3_8 | SR3=BY05_G_10_7;SR3=BY05_G_10_8 | SR3=BY02_3_13_9_1;SR3=BY02_3_13_9_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
179 | BLMQI.A21R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001488 | BJBHT.A20R3 |  | HCBYPLM001-CR000099 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A20R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A20R3_7;BYPLM.A20R3_8 | SR3=BY05_G_10_7;SR3=BY05_G_10_8 | SR3=BY02_3_13_9_1;SR3=BY02_3_13_9_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
180 | BLMQI.B21R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001481 | BJBHT.A21R3 |  | HCBYPLM001-CR000100 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A21R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A21R3_7;BYPLM.A21R3_8 | SR3=BY05_G_11_7;SR3=BY05_G_11_8 | SR3=BY02_3_13_9_3;SR3=BY02_3_13_9_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
181 | BLMQI.C21R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001484 | BJBHT.A21R3 |  | HCBYPLM001-CR000100 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A21R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A21R3_7;BYPLM.A21R3_8 | SR3=BY05_G_11_7;SR3=BY05_G_11_8 | SR3=BY02_3_13_9_3;SR3=BY02_3_13_9_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
182 | BLMQI.D21R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001491 | BJBHT.A21R3 |  | HCBYPLM001-CR000100 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A21R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A21R3_7;BYPLM.A21R3_8 | SR3=BY05_G_11_7;SR3=BY05_G_11_8 | SR3=BY02_3_13_9_3;SR3=BY02_3_13_9_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
183 | BLMQI.E21R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001511 | BJBHT.A21R3 |  | HCBYPLM001-CR000100 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A21R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A21R3_7;BYPLM.A21R3_8 | SR3=BY05_G_11_7;SR3=BY05_G_11_8 | SR3=BY02_3_13_9_3;SR3=BY02_3_13_9_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
184 | BLMQI.F21R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001499 | BJBHT.A21R3 |  | HCBYPLM001-CR000100 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A21R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A21R3_7;BYPLM.A21R3_8 | SR3=BY05_G_11_7;SR3=BY05_G_11_8 | SR3=BY02_3_13_9_3;SR3=BY02_3_13_9_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
185 | BLMQI.A22R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001485 | BJBHT.A21R3 |  | HCBYPLM001-CR000100 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A21R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A21R3_7;BYPLM.A21R3_8 | SR3=BY05_G_11_7;SR3=BY05_G_11_8 | SR3=BY02_3_13_9_3;SR3=BY02_3_13_9_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
186 | BLMQI.B22R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001489 | BJBHT.A22R3 |  | HCBYPLM001-CR000101 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A22R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A22R3_7;BYPLM.A22R3_8 | SR3=BY05_G_12_7;SR3=BY05_G_12_8 | SR3=BY02_3_14_10_1;SR3=BY02_3_14_10_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
187 | BLMQI.C22R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001524 | BJBHT.A22R3 |  | HCBYPLM001-CR000101 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A22R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A22R3_7;BYPLM.A22R3_8 | SR3=BY05_G_12_7;SR3=BY05_G_12_8 | SR3=BY02_3_14_10_1;SR3=BY02_3_14_10_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
188 | BLMQI.D22R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001515 | BJBHT.A22R3 |  | HCBYPLM001-CR000101 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A22R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A22R3_7;BYPLM.A22R3_8 | SR3=BY05_G_12_7;SR3=BY05_G_12_8 | SR3=BY02_3_14_10_1;SR3=BY02_3_14_10_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
189 | BLMQI.E22R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001482 | BJBHT.A22R3 |  | HCBYPLM001-CR000101 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A22R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A22R3_7;BYPLM.A22R3_8 | SR3=BY05_G_12_7;SR3=BY05_G_12_8 | SR3=BY02_3_14_10_1;SR3=BY02_3_14_10_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
190 | BLMQI.F22R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001532 | BJBHT.A22R3 |  | HCBYPLM001-CR000101 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A22R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A22R3_7;BYPLM.A22R3_8 | SR3=BY05_G_12_7;SR3=BY05_G_12_8 | SR3=BY02_3_14_10_1;SR3=BY02_3_14_10_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
191 | BLMQI.A23R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001736 | BJBHT.A22R3 |  | HCBYPLM001-CR000101 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A22R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A22R3_7;BYPLM.A22R3_8 | SR3=BY05_G_12_7;SR3=BY05_G_12_8 | SR3=BY02_3_14_10_1;SR3=BY02_3_14_10_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
192 | BLMQI.B23R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001813 | BJBHT.A23R3 |  | HCBYPLM001-CR000102 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A23R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A23R3_7;BYPLM.A23R3_8 | SR3=BY05_H_7_7;SR3=BY05_H_7_8 | SR3=BY02_3_14_10_3;SR3=BY02_3_14_10_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
193 | BLMQI.C23R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001502 | BJBHT.A23R3 |  | HCBYPLM001-CR000102 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A23R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A23R3_7;BYPLM.A23R3_8 | SR3=BY05_H_7_7;SR3=BY05_H_7_8 | SR3=BY02_3_14_10_3;SR3=BY02_3_14_10_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
194 | BLMQI.D23R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001747 | BJBHT.A23R3 |  | HCBYPLM001-CR000102 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A23R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A23R3_7;BYPLM.A23R3_8 | SR3=BY05_H_7_7;SR3=BY05_H_7_8 | SR3=BY02_3_14_10_3;SR3=BY02_3_14_10_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
195 | BLMQI.E23R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001752 | BJBHT.A23R3 |  | HCBYPLM001-CR000102 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A23R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A23R3_7;BYPLM.A23R3_8 | SR3=BY05_H_7_7;SR3=BY05_H_7_8 | SR3=BY02_3_14_10_3;SR3=BY02_3_14_10_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
196 | BLMQI.F23R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001789 | BJBHT.A23R3 |  | HCBYPLM001-CR000102 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A23R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A23R3_7;BYPLM.A23R3_8 | SR3=BY05_H_7_7;SR3=BY05_H_7_8 | SR3=BY02_3_14_10_3;SR3=BY02_3_14_10_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
197 | BLMQI.A24R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001541 | BJBHT.A23R3 |  | HCBYPLM001-CR000102 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A23R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A23R3_7;BYPLM.A23R3_8 | SR3=BY05_H_7_7;SR3=BY05_H_7_8 | SR3=BY02_3_14_10_3;SR3=BY02_3_14_10_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
198 | BLMQI.B24R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001530 | BJBHT.A24R3 |  | HCBYPLM001-CR000103 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A24R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A24R3_7;BYPLM.A24R3_8 | SR3=BY05_H_8_7;SR3=BY05_H_8_8 | SR3=BY02_3_15_11_1;SR3=BY02_3_15_11_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
199 | BLMQI.C24R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001513 | BJBHT.A24R3 |  | HCBYPLM001-CR000103 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A24R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A24R3_7;BYPLM.A24R3_8 | SR3=BY05_H_8_7;SR3=BY05_H_8_8 | SR3=BY02_3_15_11_1;SR3=BY02_3_15_11_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
200 | BLMQI.D24R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001733 | BJBHT.A24R3 |  | HCBYPLM001-CR000103 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A24R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A24R3_7;BYPLM.A24R3_8 | SR3=BY05_H_8_7;SR3=BY05_H_8_8 | SR3=BY02_3_15_11_1;SR3=BY02_3_15_11_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
201 | BLMQI.E24R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001534 | BJBHT.A24R3 |  | HCBYPLM001-CR000103 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A24R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A24R3_7;BYPLM.A24R3_8 | SR3=BY05_H_8_7;SR3=BY05_H_8_8 | SR3=BY02_3_15_11_1;SR3=BY02_3_15_11_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
202 | BLMQI.F24R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001539 | BJBHT.A24R3 |  | HCBYPLM001-CR000103 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A24R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A24R3_7;BYPLM.A24R3_8 | SR3=BY05_H_8_7;SR3=BY05_H_8_8 | SR3=BY02_3_15_11_1;SR3=BY02_3_15_11_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
203 | BLMQI.A25R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001504 | BJBHT.A24R3 |  | HCBYPLM001-CR000103 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A24R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A24R3_7;BYPLM.A24R3_8 | SR3=BY05_H_8_7;SR3=BY05_H_8_8 | SR3=BY02_3_15_11_1;SR3=BY02_3_15_11_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
204 | BLMQI.B25R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001552 | BJBHT.A25R3 |  | HCBYPLM001-CR000104 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A25R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A25R3_7;BYPLM.A25R3_8 | SR3=BY05_H_9_7;SR3=BY05_H_9_8 | SR3=BY02_3_15_11_3;SR3=BY02_3_15_11_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
205 | BLMQI.C25R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500416 | BJBHT.A25R3 |  | HCBYPLM001-CR000104 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A25R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A25R3_7;BYPLM.A25R3_8 | SR3=BY05_H_9_7;SR3=BY05_H_9_8 | SR3=BY02_3_15_11_3;SR3=BY02_3_15_11_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
206 | BLMQI.D25R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500593 | BJBHT.A25R3 |  | HCBYPLM001-CR000104 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A25R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A25R3_7;BYPLM.A25R3_8 | SR3=BY05_H_9_7;SR3=BY05_H_9_8 | SR3=BY02_3_15_11_3;SR3=BY02_3_15_11_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
207 | BLMQI.E25R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001648 | BJBHT.A25R3 |  | HCBYPLM001-CR000104 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A25R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A25R3_7;BYPLM.A25R3_8 | SR3=BY05_H_9_7;SR3=BY05_H_9_8 | SR3=BY02_3_15_11_3;SR3=BY02_3_15_11_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
208 | BLMQI.F25R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500756 | BJBHT.A25R3 |  | HCBYPLM001-CR000104 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A25R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A25R3_7;BYPLM.A25R3_8 | SR3=BY05_H_9_7;SR3=BY05_H_9_8 | SR3=BY02_3_15_11_3;SR3=BY02_3_15_11_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
209 | BLMQI.A26R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001332 | BJBHT.A25R3 |  | HCBYPLM001-CR000104 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A25R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A25R3_7;BYPLM.A25R3_8 | SR3=BY05_H_9_7;SR3=BY05_H_9_8 | SR3=BY02_3_15_11_3;SR3=BY02_3_15_11_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
210 | BLMQI.B26R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001614 | BJBHT.A26R3 |  | HCBYPLM001-CR000105 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A26R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A26R3_7;BYPLM.A26R3_8 | SR3=BY05_H_10_7;SR3=BY05_H_10_8 | SR3=BY02_3_16_12_1;SR3=BY02_3_16_12_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
211 | BLMQI.C26R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500602 | BJBHT.A26R3 |  | HCBYPLM001-CR000105 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A26R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A26R3_7;BYPLM.A26R3_8 | SR3=BY05_H_10_7;SR3=BY05_H_10_8 | SR3=BY02_3_16_12_1;SR3=BY02_3_16_12_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
212 | BLMQI.D26R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500706 | BJBHT.A26R3 |  | HCBYPLM001-CR000105 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A26R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A26R3_7;BYPLM.A26R3_8 | SR3=BY05_H_10_7;SR3=BY05_H_10_8 | SR3=BY02_3_16_12_1;SR3=BY02_3_16_12_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
213 | BLMQI.E26R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001797 | BJBHT.A26R3 |  | HCBYPLM001-CR000105 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A26R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A26R3_7;BYPLM.A26R3_8 | SR3=BY05_H_10_7;SR3=BY05_H_10_8 | SR3=BY02_3_16_12_1;SR3=BY02_3_16_12_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
214 | BLMQI.F26R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500721 | BJBHT.A26R3 |  | HCBYPLM001-CR000105 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A26R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A26R3_7;BYPLM.A26R3_8 | SR3=BY05_H_10_7;SR3=BY05_H_10_8 | SR3=BY02_3_16_12_1;SR3=BY02_3_16_12_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
215 | BLMQI.A27R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500701 | BJBHT.A26R3 |  | HCBYPLM001-CR000105 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A26R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A26R3_7;BYPLM.A26R3_8 | SR3=BY05_H_10_7;SR3=BY05_H_10_8 | SR3=BY02_3_16_12_1;SR3=BY02_3_16_12_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
216 | BLMQI.B27R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500734 | BJBHT.A27R3 |  | HCBYPLM001-CR000106 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A27R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A27R3_7;BYPLM.A27R3_8 | SR3=BY05_H_11_7;SR3=BY05_H_11_8 | SR3=BY02_3_16_12_3;SR3=BY02_3_16_12_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
217 | BLMQI.C27R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500418 | BJBHT.A27R3 |  | HCBYPLM001-CR000106 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A27R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A27R3_7;BYPLM.A27R3_8 | SR3=BY05_H_11_7;SR3=BY05_H_11_8 | SR3=BY02_3_16_12_3;SR3=BY02_3_16_12_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
218 | BLMQI.D27R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500663 | BJBHT.A27R3 |  | HCBYPLM001-CR000106 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A27R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A27R3_7;BYPLM.A27R3_8 | SR3=BY05_H_11_7;SR3=BY05_H_11_8 | SR3=BY02_3_16_12_3;SR3=BY02_3_16_12_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
219 | BLMQI.E27R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500235 | BJBHT.A27R3 |  | HCBYPLM001-CR000106 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A27R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A27R3_7;BYPLM.A27R3_8 | SR3=BY05_H_11_7;SR3=BY05_H_11_8 | SR3=BY02_3_16_12_3;SR3=BY02_3_16_12_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
220 | BLMQI.F27R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500608 | BJBHT.A27R3 |  | HCBYPLM001-CR000106 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A27R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A27R3_7;BYPLM.A27R3_8 | SR3=BY05_H_11_7;SR3=BY05_H_11_8 | SR3=BY02_3_16_12_3;SR3=BY02_3_16_12_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
221 | BLMQI.A28R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500570 | BJBHT.A27R3 |  | HCBYPLM001-CR000106 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A27R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A27R3_7;BYPLM.A27R3_8 | SR3=BY05_H_11_7;SR3=BY05_H_11_8 | SR3=BY02_3_16_12_3;SR3=BY02_3_16_12_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
222 | BLMQI.B28R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500758 | BJBHT.A28R3 |  | HCBYPLM001-CR000107 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A28R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A28R3_7;BYPLM.A28R3_8 | SR3=BY05_H_12_7;SR3=BY05_H_12_8 | SR3=BY02_3_17_13_1;SR3=BY02_3_17_13_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
223 | BLMQI.C28R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500803 | BJBHT.A28R3 |  | HCBYPLM001-CR000107 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A28R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A28R3_7;BYPLM.A28R3_8 | SR3=BY05_H_12_7;SR3=BY05_H_12_8 | SR3=BY02_3_17_13_1;SR3=BY02_3_17_13_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
224 | BLMQI.D28R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500709 | BJBHT.A28R3 |  | HCBYPLM001-CR000107 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A28R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A28R3_7;BYPLM.A28R3_8 | SR3=BY05_H_12_7;SR3=BY05_H_12_8 | SR3=BY02_3_17_13_1;SR3=BY02_3_17_13_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
225 | BLMQI.E28R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500727 | BJBHT.A28R3 |  | HCBYPLM001-CR000107 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A28R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A28R3_7;BYPLM.A28R3_8 | SR3=BY05_H_12_7;SR3=BY05_H_12_8 | SR3=BY02_3_17_13_1;SR3=BY02_3_17_13_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
226 | BLMQI.F28R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500556 | BJBHT.A28R3 |  | HCBYPLM001-CR000107 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A28R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A28R3_7;BYPLM.A28R3_8 | SR3=BY05_H_12_7;SR3=BY05_H_12_8 | SR3=BY02_3_17_13_1;SR3=BY02_3_17_13_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
227 | BLMQI.A29R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500722 | BJBHT.A28R3 |  | HCBYPLM001-CR000107 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A28R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A28R3_7;BYPLM.A28R3_8 | SR3=BY05_H_12_7;SR3=BY05_H_12_8 | SR3=BY02_3_17_13_1;SR3=BY02_3_17_13_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
228 | BLMQI.B29R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500717 | BJBHT.A29R3 |  | HCBYPLM001-CR000108 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A29R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A29R3_7;BYPLM.A29R3_8 | SR3=BY05_I_7_7;SR3=BY05_I_7_8 | SR3=BY02_3_17_13_3;SR3=BY02_3_17_13_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
229 | BLMQI.C29R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500482 | BJBHT.A29R3 |  | HCBYPLM001-CR000108 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A29R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A29R3_7;BYPLM.A29R3_8 | SR3=BY05_I_7_7;SR3=BY05_I_7_8 | SR3=BY02_3_17_13_3;SR3=BY02_3_17_13_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
230 | BLMQI.D29R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001358 | BJBHT.A29R3 |  | HCBYPLM001-CR000108 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A29R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A29R3_7;BYPLM.A29R3_8 | SR3=BY05_I_7_7;SR3=BY05_I_7_8 | SR3=BY02_3_17_13_3;SR3=BY02_3_17_13_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
231 | BLMQI.E29R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500743 | BJBHT.A29R3 |  | HCBYPLM001-CR000108 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A29R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A29R3_7;BYPLM.A29R3_8 | SR3=BY05_I_7_7;SR3=BY05_I_7_8 | SR3=BY02_3_17_13_3;SR3=BY02_3_17_13_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
232 | BLMQI.F29R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500334 | BJBHT.A29R3 |  | HCBYPLM001-CR000108 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A29R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A29R3_7;BYPLM.A29R3_8 | SR3=BY05_I_7_7;SR3=BY05_I_7_8 | SR3=BY02_3_17_13_3;SR3=BY02_3_17_13_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
233 | BLMQI.A30R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500718 | BJBHT.A29R3 |  | HCBYPLM001-CR000108 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A29R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A29R3_7;BYPLM.A29R3_8 | SR3=BY05_I_7_7;SR3=BY05_I_7_8 | SR3=BY02_3_17_13_3;SR3=BY02_3_17_13_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
234 | BLMQI.B30R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500716 | BJBHT.A30R3 |  | HCBYPLM001-CR000109 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A30R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A30R3_7;BYPLM.A30R3_8 | SR3=BY05_I_8_7;SR3=BY05_I_8_8 | SR3=BY02_3_18_14_1;SR3=BY02_3_18_14_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
235 | BLMQI.C30R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500497 | BJBHT.A30R3 |  | HCBYPLM001-CR000109 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A30R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A30R3_7;BYPLM.A30R3_8 | SR3=BY05_I_8_7;SR3=BY05_I_8_8 | SR3=BY02_3_18_14_1;SR3=BY02_3_18_14_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
236 | BLMQI.D30R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500481 | BJBHT.A30R3 |  | HCBYPLM001-CR000109 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A30R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A30R3_7;BYPLM.A30R3_8 | SR3=BY05_I_8_7;SR3=BY05_I_8_8 | SR3=BY02_3_18_14_1;SR3=BY02_3_18_14_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
237 | BLMQI.E30R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500485 | BJBHT.A30R3 |  | HCBYPLM001-CR000109 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A30R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A30R3_7;BYPLM.A30R3_8 | SR3=BY05_I_8_7;SR3=BY05_I_8_8 | SR3=BY02_3_18_14_1;SR3=BY02_3_18_14_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
238 | BLMQI.F30R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500401 | BJBHT.A30R3 |  | HCBYPLM001-CR000109 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A30R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A30R3_7;BYPLM.A30R3_8 | SR3=BY05_I_8_7;SR3=BY05_I_8_8 | SR3=BY02_3_18_14_1;SR3=BY02_3_18_14_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
239 | BLMQI.A31R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500546 | BJBHT.A30R3 |  | HCBYPLM001-CR000109 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A30R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A30R3_7;BYPLM.A30R3_8 | SR3=BY05_I_8_7;SR3=BY05_I_8_8 | SR3=BY02_3_18_14_1;SR3=BY02_3_18_14_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
240 | BLMQI.B31R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500688 | BJBHT.A31R3 |  | HCBYPLM001-CR000110 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A31R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A31R3_7;BYPLM.A31R3_8 | SR3=BY05_I_9_7;SR3=BY05_I_9_8 | SR3=BY02_3_18_14_3;SR3=BY02_3_18_14_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
241 | BLMQI.C31R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500607 | BJBHT.A31R3 |  | HCBYPLM001-CR000110 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A31R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A31R3_7;BYPLM.A31R3_8 | SR3=BY05_I_9_7;SR3=BY05_I_9_8 | SR3=BY02_3_18_14_3;SR3=BY02_3_18_14_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
242 | BLMQI.D31R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500379 | BJBHT.A31R3 |  | HCBYPLM001-CR000110 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A31R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A31R3_7;BYPLM.A31R3_8 | SR3=BY05_I_9_7;SR3=BY05_I_9_8 | SR3=BY02_3_18_14_3;SR3=BY02_3_18_14_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
243 | BLMQI.E31R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500316 | BJBHT.A31R3 |  | HCBYPLM001-CR000110 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A31R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A31R3_7;BYPLM.A31R3_8 | SR3=BY05_I_9_7;SR3=BY05_I_9_8 | SR3=BY02_3_18_14_3;SR3=BY02_3_18_14_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
244 | BLMQI.F31R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500406 | BJBHT.A31R3 |  | HCBYPLM001-CR000110 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A31R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A31R3_7;BYPLM.A31R3_8 | SR3=BY05_I_9_7;SR3=BY05_I_9_8 | SR3=BY02_3_18_14_3;SR3=BY02_3_18_14_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
245 | BLMQI.A32R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500710 | BJBHT.A31R3 |  | HCBYPLM001-CR000110 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A31R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A31R3_7;BYPLM.A31R3_8 | SR3=BY05_I_9_7;SR3=BY05_I_9_8 | SR3=BY02_3_18_14_3;SR3=BY02_3_18_14_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
246 | BLMQI.B32R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500620 | BJBHT.A32R3 |  | HCBYPLM001-CR000111 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A32R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A32R3_7;BYPLM.A32R3_8 | SR3=BY05_I_10_7;SR3=BY05_I_10_8 | SR3=BY02_3_19_15_1;SR3=BY02_3_19_15_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
247 | BLMQI.C32R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500538 | BJBHT.A32R3 |  | HCBYPLM001-CR000111 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A32R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A32R3_7;BYPLM.A32R3_8 | SR3=BY05_I_10_7;SR3=BY05_I_10_8 | SR3=BY02_3_19_15_1;SR3=BY02_3_19_15_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
248 | BLMQI.D32R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500571 | BJBHT.A32R3 |  | HCBYPLM001-CR000111 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A32R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A32R3_7;BYPLM.A32R3_8 | SR3=BY05_I_10_7;SR3=BY05_I_10_8 | SR3=BY02_3_19_15_1;SR3=BY02_3_19_15_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
249 | BLMQI.E32R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500690 | BJBHT.A32R3 |  | HCBYPLM001-CR000111 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A32R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A32R3_7;BYPLM.A32R3_8 | SR3=BY05_I_10_7;SR3=BY05_I_10_8 | SR3=BY02_3_19_15_1;SR3=BY02_3_19_15_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
250 | BLMQI.F32R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500601 | BJBHT.A32R3 |  | HCBYPLM001-CR000111 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A32R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A32R3_7;BYPLM.A32R3_8 | SR3=BY05_I_10_7;SR3=BY05_I_10_8 | SR3=BY02_3_19_15_1;SR3=BY02_3_19_15_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
251 | BLMQI.A33R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500672 | BJBHT.A32R3 |  | HCBYPLM001-CR000111 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A32R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A32R3_7;BYPLM.A32R3_8 | SR3=BY05_I_10_7;SR3=BY05_I_10_8 | SR3=BY02_3_19_15_1;SR3=BY02_3_19_15_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
252 | BLMQI.B33R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500685 | BJBHT.A33R3 |  | HCBYPLM001-CR000112 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A33R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A33R3_7;BYPLM.A33R3_8 | SR3=BY05_I_11_7;SR3=BY05_I_11_8 | SR3=BY02_3_19_15_3;SR3=BY02_3_19_15_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
253 | BLMQI.C33R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500580 | BJBHT.A33R3 |  | HCBYPLM001-CR000112 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A33R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A33R3_7;BYPLM.A33R3_8 | SR3=BY05_I_11_7;SR3=BY05_I_11_8 | SR3=BY02_3_19_15_3;SR3=BY02_3_19_15_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
254 | BLMQI.D33R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001626 | BJBHT.A33R3 |  | HCBYPLM001-CR000112 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A33R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A33R3_7;BYPLM.A33R3_8 | SR3=BY05_I_11_7;SR3=BY05_I_11_8 | SR3=BY02_3_19_15_3;SR3=BY02_3_19_15_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
255 | BLMQI.E33R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001627 | BJBHT.A33R3 |  | HCBYPLM001-CR000112 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A33R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A33R3_7;BYPLM.A33R3_8 | SR3=BY05_I_11_7;SR3=BY05_I_11_8 | SR3=BY02_3_19_15_3;SR3=BY02_3_19_15_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
256 | BLMQI.F33R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001318 | BJBHT.A33R3 |  | HCBYPLM001-CR000112 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A33R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A33R3_7;BYPLM.A33R3_8 | SR3=BY05_I_11_7;SR3=BY05_I_11_8 | SR3=BY02_3_19_15_3;SR3=BY02_3_19_15_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
257 | BLMQI.A34R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001259 | BJBHT.A33R3 |  | HCBYPLM001-CR000112 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A33R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A33R3_7;BYPLM.A33R3_8 | SR3=BY05_I_11_7;SR3=BY05_I_11_8 | SR3=BY02_3_19_15_3;SR3=BY02_3_19_15_4 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
258 | BLMQI.B34R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001567 | BJBHT.A34R3 |  | HCBYPLM001-CR000113 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A34R3_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A34R3_7;BYPLM.A34R3_8 | SR3=BY05_I_12_7;SR3=BY05_I_12_8 | SR3=BY02_3_20_16_1;SR3=BY02_3_20_16_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
259 | BLMQI.C34R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500723 | BJBHT.A34R3 |  | HCBYPLM001-CR000113 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A34R3_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A34R3_7;BYPLM.A34R3_8 | SR3=BY05_I_12_7;SR3=BY05_I_12_8 | SR3=BY02_3_20_16_1;SR3=BY02_3_20_16_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
260 | BLMQI.D34R3 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001566 | BJBHT.A34R3 |  | HCBYPLM001-CR000113 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A34R3_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A34R3_7;BYPLM.A34R3_8 | SR3=BY05_I_12_7;SR3=BY05_I_12_8 | SR3=BY02_3_20_16_1;SR3=BY02_3_20_16_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
262 | BLMQI.D34L4 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-0500762 | BJBHT.A34R3 |  | HCBYPLM001-CR000113 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A34R3_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A34R3_7;BYPLM.A34R3_8 | SR3=BY05_I_12_7;SR3=BY05_I_12_8 | SR3=BY02_3_20_16_1;SR3=BY02_3_20_16_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
262 | BLMQI.C34L4 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001587 | BJBHT.A34R3 |  | HCBYPLM001-CR000113 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A34R3_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A34R3_7;BYPLM.A34R3_8 | SR3=BY05_I_12_7;SR3=BY05_I_12_8 | SR3=BY02_3_20_16_1;SR3=BY02_3_20_16_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302
263 | BLMQI.B34L4 | In Progress | 2008-04-29 |  |  |  | IC | HCBLM_I001-05001273 | BJBHT.A34R3 |  | HCBYPLM001-CR000113 |  |  | In Progress | 2008-04-29 |  |  |  |  | BYPLM.A34R3_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A34R3_7;BYPLM.A34R3_8 | SR3=BY05_I_12_7;SR3=BY05_I_12_8 | SR3=BY02_3_20_16_1;SR3=BY02_3_20_16_2 |  | CFV-SR3-BLMR | [8 empty] | M | 1 | CFVM-SR3-BLMR |  |  | HCCIBUS-ID000302