## HWC for BLM
Beam Loss Monitor HWC
Once completed. send this file Jacek.Szkutnik@cern.ch Empty fields will remain untouch in MTF DB Non empty fields will be updated (when allowed) on MTF DB -> Just fill modified fileds! DO NOT ALTER THIS TEMPLATE - You can just insert lines for new slots if necessary Remove given Examples!
Identification |  | 10-BLM channel check (leakage. bias current) | [7 empty] | [Patch_Input] |  | pA | pA | 20-BLM Acquisition Chain Desription | [5 empty] | [Loc=Ra_Cr_CFC_In] |  | [Cr_CFC_Out] | [Loc=Ra_Pa_In] | [Loc=Ra_Pa_Sl_Out] | [Loc=Ra_VME_Si_DAB_In] | [18 empty] | 30-BLM Acquisition Chain Test via test signal |  |  |  |  | pA | pA | 40-BLM HV modulation Test |  |  |  |  | V | Hz | ° |  | pA | 50-BLM Acquisition Chain Test via RA Source |  |  |  |  | pA | 60-BLM Interlock Test | [8 empty] | 70-BLM EMC Test |  |  |  |  | pA | pA | 80-BLM Beam Energy reception Test |  |  |  |  | EDMS Document Number
Official Slot Name |  | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Monitor Type | Monitor Identificator | HV Patch | BJBAP Input | Tunnel Mini Rack Id. | LC(offset) w/cable&M-r | Signal via source w/cable | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | BJBAP Cable Number | Analog Front End | BLECF Identificator | Opt Link Analog FE | Opt Link Patch Tunnel | Opt Link Patch Surface | Opt Link Digital Acq. | VME BLETC Id. | VME CPU Host Name | VME Crate Id. | VME Fantray Id. | VME Power Supply Id. | VME CPU Id. | VME BOBR Id. | VME BLECS Id. | VME BLETC Serial | VME BLECS Serial | Monitor Function | Monitor Status | VME Fantray Hostname | DAB card Id. | Mezzanine card Id. | CIBU Id. | FPGA firmware vers(BLETC) | FPGA firmware vers(BLECS) | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Test:100pA/84 sec run.sum | Test:10pA/84 sec run.sum | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Set voltage: peak-peak | Set frequency | Resulting phase | Resulting Gain | Current signal: peak-peak | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Signal Current | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Threshold/Ch Matrix Test | TTable User Beam Permit T | UBP Check BLETC to BLECS | UBP Check BLECS to CIBU | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Test EMC/40 µs run.sum | Test EMC/1.3 sec run.sum | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments
133 | BLMQI.B26L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500759 | BJBHT.A26L4 |  | HCBYPLM001-CR000121 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A26L4_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A26L4_7;BYPLM.A26L4_8 | SX4=BY05_H_4_7;SX4=BY05_H_4_8 | SX4=BY02_1_15_11_3;SX4=BY02_1_15_11_4 | BLETC 010 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351007 | MEZZ NO 232 | HCCIBUS-ID000122
134 | BLMQI.C26L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500733 | BJBHT.A26L4 |  | HCBYPLM001-CR000121 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A26L4_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A26L4_7;BYPLM.A26L4_8 | SX4=BY05_H_4_7;SX4=BY05_H_4_8 | SX4=BY02_1_15_11_3;SX4=BY02_1_15_11_4 | BLETC 010 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351007 | MEZZ NO 232 | HCCIBUS-ID000122
135 | BLMQI.D26L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500754 | BJBHT.A26L4 |  | HCBYPLM001-CR000121 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A26L4_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A26L4_7;BYPLM.A26L4_8 | SX4=BY05_H_4_7;SX4=BY05_H_4_8 | SX4=BY02_1_15_11_3;SX4=BY02_1_15_11_4 | BLETC 010 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351007 | MEZZ NO 232 | HCCIBUS-ID000122
136 | BLMQI.E26L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500725 | BJBHT.A26L4 |  | HCBYPLM001-CR000121 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A26L4_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A26L4_7;BYPLM.A26L4_8 | SX4=BY05_H_4_7;SX4=BY05_H_4_8 | SX4=BY02_1_15_11_3;SX4=BY02_1_15_11_4 | BLETC 010 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351007 | MEZZ NO 232 | HCCIBUS-ID000122
137 | BLMQI.F26L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500788 | BJBHT.A26L4 |  | HCBYPLM001-CR000121 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A26L4_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A26L4_7;BYPLM.A26L4_8 | SX4=BY05_H_4_7;SX4=BY05_H_4_8 | SX4=BY02_1_15_11_3;SX4=BY02_1_15_11_4 | BLETC 010 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351007 | MEZZ NO 232 | HCCIBUS-ID000122
138 | BLMQI.A27L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500732 | BJBHT.A26L4 |  | HCBYPLM001-CR000121 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A26L4_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A26L4_7;BYPLM.A26L4_8 | SX4=BY05_H_4_7;SX4=BY05_H_4_8 | SX4=BY02_1_15_11_3;SX4=BY02_1_15_11_4 | BLETC 010 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351007 | MEZZ NO 232 | HCCIBUS-ID000122
139 | BLMQI.B27L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500636 | BJBHT.A27L4 |  | HCBYPLM001-CR000120 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A27L4_CFC_6 |  | CFC_A1;CFC_A2 | BYPLM.A27L4_7;BYPLM.A27L4_8 | SX4=BY05_H_5_7;SX4=BY05_H_5_8 | SX4=BY02_1_16_12_1;SX4=BY02_1_16_12_2 | BLETC 011 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351000 | MEZZ NO 331 | HCCIBUS-ID000122
140 | BLMQI.C27L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500589 | BJBHT.A27L4 |  | HCBYPLM001-CR000120 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A27L4_CFC_5 |  | CFC_A1;CFC_A2 | BYPLM.A27L4_7;BYPLM.A27L4_8 | SX4=BY05_H_5_7;SX4=BY05_H_5_8 | SX4=BY02_1_16_12_1;SX4=BY02_1_16_12_2 | BLETC 011 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351000 | MEZZ NO 331 | HCCIBUS-ID000122
141 | BLMQI.D27L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500720 | BJBHT.A27L4 |  | HCBYPLM001-CR000120 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A27L4_CFC_4 |  | CFC_A1;CFC_A2 | BYPLM.A27L4_7;BYPLM.A27L4_8 | SX4=BY05_H_5_7;SX4=BY05_H_5_8 | SX4=BY02_1_16_12_1;SX4=BY02_1_16_12_2 | BLETC 011 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351000 | MEZZ NO 331 | HCCIBUS-ID000122
142 | BLMQI.E27L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-050073 | BJBHT.A27L4 |  | HCBYPLM001-CR000120 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A27L4_CFC_3 |  | CFC_A1;CFC_A2 | BYPLM.A27L4_7;BYPLM.A27L4_8 | SX4=BY05_H_5_7;SX4=BY05_H_5_8 | SX4=BY02_1_16_12_1;SX4=BY02_1_16_12_2 | BLETC 011 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351000 | MEZZ NO 331 | HCCIBUS-ID000122
143 | BLMQI.F27L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500705 | BJBHT.A27L4 |  | HCBYPLM001-CR000120 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A27L4_CFC_2 |  | CFC_A1;CFC_A2 | BYPLM.A27L4_7;BYPLM.A27L4_8 | SX4=BY05_H_5_7;SX4=BY05_H_5_8 | SX4=BY02_1_16_12_1;SX4=BY02_1_16_12_2 | BLETC 011 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351000 | MEZZ NO 331 | HCCIBUS-ID000122
144 | BLMQI.A28L4 | In Progress | 2008-05-09 |  |  |  | IC | HCBLM_I001-0500799 | BJBHT.A27L4 |  | HCBYPLM001-CR000120 |  |  | In Progress | 2008-05-09 |  |  |  |  | BYPLM.A27L4_CFC_1 |  | CFC_A1;CFC_A2 | BYPLM.A27L4_7;BYPLM.A27L4_8 | SX4=BY05_H_5_7;SX4=BY05_H_5_8 | SX4=BY02_1_16_12_1;SX4=BY02_1_16_12_2 | BLETC 011 | CFV-SX4-BLML | 71720039 | SN: 71300141 | 71470037 | CH51702097 | 043 |  |  |  | M | 1 | CFVM-SX4-BLML | BLM C06351000 | MEZZ NO 331 | HCCIBUS-ID000122