## HWC for BLM
Beam Loss Monitor HWC
Once completed. send this file Jacek.Szkutnik@cern.ch Empty fields will remain untouch in MTF DB Non empty fields will be updated (when allowed) on MTF DB -> Just fill modified fileds! DO NOT ALTER THIS TEMPLATE - You can just insert lines for new slots if necessary Remove given Examples!
Identification |  | 10-BLM channel check (leakage. bias current) | [7 empty] | [Patch_Input] |  | pA | pA | 20-BLM Acquisition Chain Desription | [5 empty] | [Loc=Ra_Cr_CFC_In] |  | [Cr_CFC_Out] | [Loc=Ra_Pa_In] | [Loc=Ra_Pa_Sl_Out] | [Loc=Ra_VME_Si_DAB_In] | [18 empty] | 30-BLM Acquisition Chain Test via test signal |  |  |  |  | pA | pA | 40-BLM HV modulation Test |  |  |  |  | V | Hz | ° |  | pA | 50-BLM Acquisition Chain Test via RA Source |  |  |  |  | pA | 60-BLM Interlock Test | [8 empty] | 70-BLM EMC Test |  |  |  |  | pA | pA | 80-BLM Beam Energy reception Test |  |  |  |  | EDMS Document Number
Official Slot Name |  | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Monitor Type | Monitor Identificator | HV Patch | BJBAP Input | Tunnel Mini Rack Id. | LC(offset) w/cable&M-r | Signal via source w/cable | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | BJBAP Cable Number | Analog Front End | BLECF Identificator | Opt Link Analog FE | Opt Link Patch Tunnel | Opt Link Patch Surface | Opt Link Digital Acq. | VME BLETC Id. | VME CPU Host Name | VME Crate Id. | VME Fantray Id. | VME Power Supply Id. | VME CPU Id. | VME BOBR Id. | VME BLECS Id. | VME BLETC Serial | VME BLECS Serial | Monitor Function | Monitor Status | VME Fantray Hostname | DAB card Id. | Mezzanine card Id. | CIBU Id. | FPGA firmware vers(BLETC) | FPGA firmware vers(BLECS) | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Test:100pA/84 sec run.sum | Test:10pA/84 sec run.sum | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Set voltage: peak-peak | Set frequency | Resulting phase | Resulting Gain | Current signal: peak-peak | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Signal Current | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Threshold/Ch Matrix Test | TTable User Beam Permit T | UBP Check BLETC to BLECS | UBP Check BLECS to CIBU | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments | Test EMC/40 µs run.sum | Test EMC/1.3 sec run.sum | Result | Start date YYYY-MM-DD | End date YYYY-MM-DD | Executed by | Comments
| BLMQI.A2R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A2R5 | BJBAP.A2R5_1 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508830 | RR57=BY02_1_3_1 |  | 1_3_A1;1_3_A2 | RR57=BY02_A_5;RR57=BY02_A_6 | SR5=BY05_C_12_5;SR5=BY05_C_12_6 | SR5=BY02_2_14_10_1;SR5=BY02_2_14_10_2 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.B2R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A2R5 | BJBAP.A2R5_2 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508830 | RR57=BY02_1_3_2 |  | 1_3_A1;1_3_A2 | RR57=BY02_A_5;RR57=BY02_A_6 | SR5=BY05_C_12_5;SR5=BY05_C_12_6 | SR5=BY02_2_14_10_1;SR5=BY02_2_14_10_2 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.C2R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A2R5 | BJBAP.A2R5_3 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508830 | RR57=BY02_1_3_3 |  | 1_3_A1;1_3_A2 | RR57=BY02_A_5;RR57=BY02_A_6 | SR5=BY05_C_12_5;SR5=BY05_C_12_6 | SR5=BY02_2_14_10_1;SR5=BY02_2_14_10_2 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.D2R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A2R5 | BJBAP.A2R5_4 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508830 | RR57=BY02_1_3_4 |  | 1_3_A1;1_3_A2 | RR57=BY02_A_5;RR57=BY02_A_6 | SR5=BY05_C_12_5;SR5=BY05_C_12_6 | SR5=BY02_2_14_10_1;SR5=BY02_2_14_10_2 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.E2R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A2R5 | BJBAP.A2R5_5 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508830 | RR57=BY02_1_3_5 |  | 1_3_A1;1_3_A2 | RR57=BY02_A_5;RR57=BY02_A_6 | SR5=BY05_C_12_5;SR5=BY05_C_12_6 | SR5=BY02_2_14_10_1;SR5=BY02_2_14_10_2 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.F2R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A2R5 | BJBAP.A2R5_6 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508830 | RR57=BY02_1_3_6 |  | 1_3_A1;1_3_A2 | RR57=BY02_A_5;RR57=BY02_A_6 | SR5=BY05_C_12_5;SR5=BY05_C_12_6 | SR5=BY02_2_14_10_1;SR5=BY02_2_14_10_2 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.G2R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A2R5 | BJBAP.A2R5_7 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508830 | RR57=BY02_1_3_7 |  | 1_3_A1;1_3_A2 | RR57=BY02_A_5;RR57=BY02_A_6 | SR5=BY05_C_12_5;SR5=BY05_C_12_6 | SR5=BY02_2_14_10_1;SR5=BY02_2_14_10_2 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.H2R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A2R5 | BJBAP.A2R5_8 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508830 | RR57=BY02_1_3_8 |  | 1_3_A1;1_3_A2 | RR57=BY02_A_5;RR57=BY02_A_6 | SR5=BY05_C_12_5;SR5=BY05_C_12_6 | SR5=BY02_2_14_10_1;SR5=BY02_2_14_10_2 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.A3R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A3R5 | BJBAP.A3R5_1 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508831 | RR57=BY02_1_4_1 |  | 1_4_A1;1_4_A2 | RR57=BY02_A_7;RR57=BY02_A_8 | SR5=BY05_C_12_7;SR5=BY05_C_12_8 | SR5=BY02_2_14_10_3;SR5=BY02_2_14_10_4 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.B3R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A3R5 | BJBAP.A3R5_2 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508831 | RR57=BY02_1_4_2 |  | 1_4_A1;1_4_A2 | RR57=BY02_A_7;RR57=BY02_A_8 | SR5=BY05_C_12_7;SR5=BY05_C_12_8 | SR5=BY02_2_14_10_3;SR5=BY02_2_14_10_4 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.C3R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A3R5 | BJBAP.A3R5_3 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508831 | RR57=BY02_1_4_3 |  | 1_4_A1;1_4_A2 | RR57=BY02_A_7;RR57=BY02_A_8 | SR5=BY05_C_12_7;SR5=BY05_C_12_8 | SR5=BY02_2_14_10_3;SR5=BY02_2_14_10_4 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.D3R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A3R5 | BJBAP.A3R5_4 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508831 | RR57=BY02_1_4_4 |  | 1_4_A1;1_4_A2 | RR57=BY02_A_7;RR57=BY02_A_8 | SR5=BY05_C_12_7;SR5=BY05_C_12_8 | SR5=BY02_2_14_10_3;SR5=BY02_2_14_10_4 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237
| BLMQI.A4R5 | In Progress | 2008-04-24 |  |  |  | IC |  | BJBHT.A3R5 | BJBAP.A3R5_5 |  |  |  | In Progress | 2008-04-24 |  |  |  | 1508831 | RR57=BY02_1_4_5 |  | 1_4_A1;1_4_A2 | RR57=BY02_A_7;RR57=BY02_A_8 | SR5=BY05_C_12_7;SR5=BY05_C_12_8 | SR5=BY02_2_14_10_3;SR5=BY02_2_14_10_4 | BLETC 313 | CFV-SR5-BLMC | 71720041 | SN: 71300132 | 71470035 | CH51702099 |  |  |  |  | U | 1 | CFVM-SR5-BLMC | BLM C06501249 | MEZZ NO 356 | HCCIBUS-ID000237