## Slide 1: LS1 BLM planning
20/01/2014

## Slide 2: Surface racks
P1, P2, P5, P6, P7, P8 : done
(not complete: new air deflector, …)
Pt3 : end of January, February
Pt4 : February, March
Cards

## Slide 3: Tunnel racks and HV divider
Arc: All backplanes was exchange
Arc: all CFC cards removed
LSS: HV divider installation:
~60% HV dividers was installed
except Pt6 , where 3 HV dividers was installed
LSS: CFC cards removed

## Slide 4: BLM re-installation
New cables for dipole-dipole (DD) BLM installation
was done in All Arc with the connectors, except sector 6-7 and L6 (no HV connectors)
L6 – BLMs re-installed in cells 7-21 with new DD support (except cell 8)
R6 – BLMs re-installed in cells 7 -13 with new DD support ( except cell 8)
R5 – BLMs re-installed in cells 7 – 11, we are planning this week to install all BLMs in R5 and to put the new cables in DS
LSS: Pt3 re-installed
DD supports:
Germany: received long 100 supports, expect: Monday - 300 ones
CERN: received brides and int supports for DD – 300 pcs( for 150 DD), 21.01 – 150, next delivery – middle of February
Connectors : 14.01 and 21.01
New installations (collimators, AFP, TOTEM, Alice – 2 old + new?)

## Slide 5: Divers
Labels
Databases ( ~840 new expert names)
Test (electrical, battery)
Rad Source test
- source