## Slide 1: LS1@LHC BLM planning
03/02/2014

## Slide 2: Surface racks
P1, P2, P5, P6, P7, P8 (1/2) : done
Pt3 : February
Pt4 : February, March (Bernd’s request)
From: Christos Zamantzas Sent: 31 January 2014 14:35 To: Slava Grishin; Seghaier Ben Amor Cc: Ewald Effinger Subject: Rack configuration
Hi Slava,
Here is the latest version of the rack configuration in the LHC.
We have agreed with Ewald to change the position if the “Left” crates, because it will allow us to reuse many of the fibres.
Regards,
Christos

## Slide 3: Tunnel racks and HV divider
HV divider installation:
~60% HV dividers was installed in 6 LSS, but rest of cases are special :
R5 – presentation of special cases R6 – not installed . presentation
Schedule for installation, including P6 and P7 and special cases in rest of Points( wall, not enough space, not easy accessible)
New cables
L5: restoration of racks after He spill test, after Feb 7th
Racks – CFC cards and take in to account the problems ( ventilator…)

## Slide 4: BLM re-installation (not yet approved, Marzia)
1)Sector 6-7:
Weeks 5, 7, 8 ( week 6 – no access)
24.02 – Walkway reinstallation
2)Sector 5-6:
Week 6 (and this sector will be done)
17.02 – Walkway reinstallation
3)Sector 7-8:
From 24.02, Weeks 9,10,11
17.03 – Walkway reinstallation
4)Sector 8-1:
From 17.03, Weeks 12,13,14 and w15 up to 10.04 (+ 2 working days -exchange of persons of installation team)
14.04 – Walkway reinstallation
5)Sector 1-2:
From 11.04, Weeks 16,17,18 and w19 up to May 7th (April 18,21 and May 1st – holiday at CERN)
08.05 – Walkway reinstallation
6)Sector 2-3:
From May 8, Weeks 20,21,22 (May 29th – holiday at CERN)
02.06 – Walkway reinstallation
7)Sector 3-4:
From 02.06, Weeks 23,24,25 + up to 24.06 (June 9 – holiday at CERN)
24.06 – Walkway reinstallation
8)Sector 4-5:
From 24.06, Weeks 26,27,28
15.07 – Walkway reinstallation

## Slide 5: BLM re-installation
According to LS1 schedule and constrains for ARC+DS
Sector 6-7:
R6 – done from Q7-Q34 with connectors, except QBBI.8R6
L7 – will work weeks 7 and 8
Sector 5-6:
R5 – done with connectors, except for 3 open ICs
L6 – will be done on this week
LSS:
LSS: Pt3 re-installed
LSS: R5 - prepared but not installed 4 and 5 cells
Schedule for LSS re-installation and new installation (Slava)

## Slide 6: Divers
Slot Labels
Databases ( ~840 new expert names)
Test (electrical, battery)
Rad Source test ( 2 sources)
Label for new “short” cable (BJBDV - BJBAP)
ECR LHC-BLM-EC-0003 (BJBDV)
LIC’s after GIF for installation – this week or middle of March