## Slide 1: LS1@LHC BLM planning
03/03/2014

## Slide 2: Surface racks
P1 -/+, P2 -/+, P5 -/+: to change the configuration:
Next week P1,P2,P5 – configuration will be correct
P6 + , P7 +, P8 +, P3 + : OK
Pt4 : March (Bernd’s request)
Rack configuration:
R L
I C
- ground metallic bar: >5 fixation – OK (P3)

## Slide 3: Tunnel racks and HV divider
HV divider installation:
Installed in all “standard” locations in all Points, except L6
In “special cases” – not installed, but long cables was ordered ( Remo)
L5: restoration of racks after He spill test
Racks – CFC cards : ready for installation ( Ion or Russian team)

## Slide 4: From version 3.0 to 3.1
Schematic view of version 3.1, now includes
  DFBA repairs at P6 and P8
  CSCM in sectors 67 and 81
  a margin of 2 weeks after flushing for N.C. solving
  The sector test from P2 to P3
Under discussion

## Slide 5: BLM re-installation and RSM
New planning for Installation and Rad Source Measurements
(pdf files from 27 February)
Current status of DS+ARC installation:
Sector 6-7 - done
Sector 5-6 - done
Sector 7-8 – in work
last, this and next weeks, but it’ll be no access during 3 days on the next week
List what we need to be work before RSM:
Installation, surface rack, tunnel rack, DB, …
Request to move the source on surface?
LSS installation
New request:
2 IC shifted + new 4 ICs new installation
Request for ion losses control – new ICs installation in Q10 -Q12 location in P1,P2,P5
Alice – new 3 ICs installation

## Slide 6: BLM re-installation
03/03/2014 |  |  |  |  |  |  |  |  |  |  | LHC Beam Loss installation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cell | R 1 |  | L 2 |  | R 2 |  | L 3 |  | R 3 |  | L 4 |  | R 4 |  | L 5 |  | R 5 |  | L 6 |  | R 6 |  | L 7 |  | R 7 |  | L 8 |  | R 8 |  | L 1 |  | 
 | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | IC | S | 
1 | 5 | 1 | 5 | 1 | 5 | 1 |  |  |  |  |  |  |  |  | 6 | 1 | 6 | 1 |  |  |  |  |  |  |  |  | 5 | 1 | 5 | 1 | 5 | 1 | 1
2 | 8 |  | 8 |  | 8 |  |  |  |  |  |  |  |  |  | 6 |  | 6 |  |  |  |  |  |  |  |  |  | 8 |  | 8 |  | 8 |  | 2
3 | 5 |  | 5 |  | 5 |  |  |  |  |  |  |  |  |  | 6 |  | 6 |  |  |  |  |  |  |  |  |  | 5 |  | 5 |  | 5 |  | 3
4 | 10 | 4 | 15 | 5 | 13 | 3 | 8 | 2 | 8 | 2 | 2 |  | 2 |  | 11 | 4 | 12 | 4 | 31 | 24 | 31 | 24 | 18 | 12 | 18 | 12 | 13 | 3 | 15 | 5 | 10 | 4 | 4
5 | 7 | 1 | 6 |  | 6 |  | 14 | 8 | 14 | 8 | 8 |  | 8 |  | 7 | 1 | 7 | 1 | 11 | 3 | 11 | 3 | 20 | 14 | 20 | 14 | 6 |  | 6 |  | 7 | 1 | 5
6 | 6 |  | 12 | 6 | 7 | 1 | 10 | 4 | 10 | 4 | 6 |  | 6 |  | 8 |  | 7 |  |  |  |  |  | 27 | 21 | 27 | 21 | 7 | 1 | 12 | 6 | 6 |  | 6
7 | 8 |  | 6 |  | 6 |  | 12 | 1 | 7 | 1 | 6 |  | 6 |  | 6 |  | 6 |  |  |  |  |  | 8 | 2 | 8 | 2 | 6 |  | 6 |  | 8 |  | 7
8 | 12 |  | 12 | 6 | 12 | 6 | 7 |  | 12 |  | 6 |  | 6 |  | 12 |  | 12 |  | 6 |  | 6 |  | 9 |  | 9 |  | 12 | 6 | 12 | 6 | 12 |  | 8
9 | 6 |  | 6 |  | 6 |  | 21 |  | 21 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 15 |  | 16 |  | 6 |  | 6 |  | 6 |  | 9
10 | 8 |  | 13 |  | 12 |  | 11 |  | 11 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 7 |  | 9 |  | 6 |  | 6 |  | 8 |  | 10
11 | 16 |  | 12 | 6 | 12 | 6 | 19 |  | 19 |  | 6 |  | 6 |  | 13 |  | 15 |  | 6 |  | 6 |  | 19 |  | 19 |  | 12 | 6 | 12 | 6 | 16 |  | 11
12 | 6 |  | 8 |  | 8 |  | 10 |  | 10 |  | 6 |  | 6 |  | 6 |  | 4+2 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 12
13 | 8 |  | 6 |  | 6 |  | 10 |  | 10 |  | 6 |  | 6 |  | 8 |  | 8 |  | 6 |  | 6 |  | 8 |  | 6 |  | 6 |  | 6 |  | 8 |  | 13
14 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 14
15 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 15
16 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 16
17 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 17
18 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 18
19 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 9 |  | 6 |  | 6 |  | 6 |  | 6 |  | 19
20 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 20
21 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 21
22 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 22
23 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 23
24 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 24
25 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 25
26 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 26
27 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 27
28 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 28
29 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 29
30 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 30
31 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 31
32 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 32
33 | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 33
34 | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 6 |  |  |  | 34
Dump |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 19 | 7 | 19 | 7 |  |  |  |  |  |  |  |  |  |  | Dump
IC inst | 231 |  | 234 |  | 232 |  | 242 |  | 248 |  | 178 |  | 184 |  | 223 |  | 225 |  | 217 |  | 223 |  | 260 |  | 264 |  | 218 |  | 231 |  | 225 |  | 3635
SEM inst |  | 6 |  | 24 |  | 17 |  | 15 |  | 15 |  | 0 |  | 0 |  | 6 |  | 6 |  | 34 |  | 34 |  | 49 |  | 49 |  | 17 |  | 24 |  | 6 | 302
IC to inst | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6 |  | 0 |  | 0 |  | 7 |  | 5 |  | 0 |  | 0 |  | 0 |  | 18
SEM to in |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6 |  | 0 |  | 0 |  | 0 |  | 7 |  | 5 |  | 0 |  | 0 |  | 0 | 18
 |  | finished |  |  |  |  |  |  |  | Sem, IC monitors not installed |  |  |  |  |  |  |  |  | LIC |  | HV divider |  |  |  | Card_CFC |  |  |  |  |  |  |  | 

## Slide 7: General Information ( old?)
Beam Vacuum Pumping in the LSS and Arcs before the start of the cool-down
  All activities on the stand alone need to be completed before
Start week 13 for the sector 67

## Slide 8: GLOBAL OVERVIEW: P test & cool down(old?)

## Slide 9: Divers
Databases: changes on this week sector 5-6, 6-7, R7
Slot Labels ( after changes of expert names)
Rad Source test ( 2 sources )
ECR for HV divider is released
Label for new “short” cable (BJBDV - BJBAP)
Amendment for 1 month* 4 persons prolongation – signed at CERN
ECR for LICs
LIC’s after GIF for installation – middle of March (?)