## Slide 1: LS1@LHC BLM planning
10/03/2014

## Slide 2: Surface racks
11/03, Tuesday Seghair and Russian team will check, correct, install the all in P1,P2,P5 surface racks
P1 -/+, P2 -/+, P5 -/+: to change the configuration:
P6 + , P7 +, P8 +, P3 + : OK
Pt4 : March (Bernd’s request)
Rack configuration:
R L
I C
- ground metallic bar: >5 fixation – OK (P3)

## Slide 3: Tunnel racks and HV divider
HV divider installation:
Installed in all “standard” locations in all Points, except L6
In “special cases” – not installed,
but long cables was ordered ( Remo) - ?
L5: restoration of racks after He spill test
Racks – CFC cards : ready for installation ( Ion or Russian team)

## Slide 4: BLM re-installation
Current status of DS+ARC installation:
Sector 6-7 - done
Sector 5-6 – done
Sector 7-8 – R7 – done
L8 – 4 working days to finish
- All SEMs was dismounted in L8 ( to exchange for LIC)
- BLMQI.01L8.B1E30)MQXA(BPMSW) with support was dismonted for LHCb counter installation, and to install in new, shifted place
But no access in sector 7-8 10-11-12/03 and 17-18/03
Remarks:
a) good collaboration with QPS team on DS of L8 to put down the common longest cable trays
b) BLM team works with walkways
List what we need to be work before RSM:
Installation, surface rack, tunnel rack, DB, …
Request to move the source on surface?
LSS installation
New installation:

## Slide 5: Divers
Databases:
cryoBLM-BJBAP box and expert names and DCUM are in Layout(MTF)
Slot Labels ( after changes of expert names)
Rad Source test ( 2 sources )
ECR for HV divider is released
Label for new “short” cable (BJBDV - BJBAP)
Amendment for 1 month* 4 persons prolongation – signed at CERN
ECR for LICs
LIC’s tests and shrinking at GIF:
- shrinking – 12.03
- irradiation on front irradiator – 17-18/03