## Slide 1: LS1 BLM@LHC status
17/03/2014

## Slide 2: Surface racks
P2 -/+, to change the configuration
P1, P3, P5, P6 , P7, P8 : OK (Seghaier and Steve)
Pt4 for dismounting , March 17th :
4 extensions (P4) and 1 door from P3 with ventilators
all BL equipment to Seghaier for cleaning
Rack configuration:
R L
I C

## Slide 3: BLM re-installation
Current status of DS+ARC installation:
Sector 6-7 - done
Sector 5-6 – done
Sector 7-8:
R7 – done
L8 – Arc done, LSS needs 2 more days( 19-20 of March), no access to sector 17-18.03
All SEMs was dismounted in L8 ( to exchange for LIC)
Barbara’s request to dismount SEMs in P6 ( mail form 13.03.2014)
- BLMQI.01L8.B1E30)MQXA(BPMSW) - change of expert name ( Christos question from 10.03) with support was dismounted for LHCb counter installation, and to install in new, shifted place
Sector 8-1 - start
DS of R8: Friday, March 21st QPS and BLM team will put down the common longest cable trays
List what we need to be work before RSM:
Installation, surface rack, tunnel rack, DB, …
Request to move the source on surface – OK:
From: Abderrahim Errahhaoui
Sent: 11 March 2014 19:34
In this case, I suggest that you transport the trolley (with the radioactive sources) in the Type A package.
For that, you have to fill in the internal transport request in EDH and please indicate “Radioactive” as danger and “Type A package*” required in the comments.
LSS installation
New installation

## Slide 4: General Information
Beam Vacuum schedule is really tight and just fit with the deadline
LSS 6
LSS 7
LSS 8R
LSS 1L
LSS 8L
LSS 5R
LSS 4
LSS 2R
LSS 3
LSS 1R
LSS 2L
Provisional deadline
This hole of activities appeared because of delay of equipment in surface.
The schedule already shifted by 1 month !
No margin left to fit the deadline
On a critical path

## Slide 5: Divers
Slot Labels ( after changes of expert names)
Label for new “short” cable (BJBDV - BJBAP), ECR for HV divider is released
Coating of rest of supports and brides to outside of CERN, schedule?
Plastic boxes and old supports from tunnel to ?
Order the additional materials for installation: cables, metallic strips
1000 m(HV) and 3000 m(BNC) cables; 35 bobins (*45 m in each) of metallic strips.
Rad Source test ( 2 sources ) ready to end of July
ECR for LICs and Removal the all SEMs(?)
LIC’s tests and shrinking at GIF: from 14:00 at 17-18/03
GIF and GIF++ status:
GIF will operate up to Middle of August, 2013 (FIC tests in July, 2013)
GIF++ will operate from Middle of January, 2014 (IC tests in February,2014)
FIC production contract was signed:
Materials to send: resistors ?
List of materials, cost and amount of IC new production ( Q4,2013-Q1,2014)

## Slide 6: Tunnel racks and HV divider
HV divider installation:
Installed in all “standard” locations in all Points, except L6
In “special cases” – not installed,
but long cables was ordered ( Remo) - ?
L5: restoration of racks after He spill test
Racks – CFC cards : ready for installation ( Ion or Russian team)