## Slide 1: From: Bernd Dehning Sent: 04 July 2014 17:27 Subject: meeting LHC BLM, 07.07.2014 in room 865 1-B03
07/07/2014
* status, all
* AccTest framework
* preparation for source measurements

## Slide 2
ARC
Sector 4-5:
DS’s done, up to 30R4 done
After He spill test - the mini-racks under the quads 12,13,14 L5, but not in 11L5
Sector 1-2
Mirko Pojer: Urgent to remove cable trays on
QBQI.31R1; QBBI.B31R1; QBBI.A31R1; QQBI.29R1; QBQI.29R1; QBQI.34R1
LSS
3 weeks 11.07 – 04.08 re- and new installation, but at least 2 days out as 28.07 – whole day training and August 1st with sources
Drawings, ECR…
Patrick Fassnacht: the BLMs in the region of the ALFA RP at point 1 (A7L(R)1 and B7L(R)1). We have moved one of the stations by 4m…
Stefano Redaelli : ”I would prefer if there was a visual inspection rather than relying on
the database values, unless the BLM team is sure that these monitors were not moved.
…not dismount the monitors in baking locations of A4R5 vacuum sub sector?
LHC matters
Slava

## Slide 3: AccTest framework
BLMEI.C5R6 | BLMEI.05R6.B2I10_MKD.M5R6.B2 | 16861.260184
BLMES.C5R6 | BLMES.05R6.B2I10_MKD.M5R6.B2 | 16861.260184
BLMQI.B5R6 | BLMQI.05R6.B2I30_MQY | 16864.93
BLMQI.C5R6 | BLMQI.05R6.B1E10_MQY | 16868.898
BLMQI.D5R6 | BLMQI.05R6.B2I20_MQY | 16869.502
BLMQI.E5R6 | BLMQI.05R6.B1E20_MQY | 16870.702
BLMQI.F5R6 | BLMQI.05R6.B2I10_MQY | 16872.529
BLMQI.G5R6 | BLMQI.05R6.B1E30_MQY | 16875.684
BLMEI.8R6 | BLMEI.05R6.B1E10_DFBLB | 16932.407
BLMQI.A8R6 | BLMQI.08R6.B2I30_MQML | 16961.327
1. The measurement follows to DCUM ( team in tunnel)
2. AccTest framework Data: expert name, DCUM, time, signal
3. AccTest framework Storage: measurement DB -> Logging DB, no link to MTF-Layout
4. AccTest framework Picture : as in timber, but no online analysis (noise, signal, stdev)
5. Possibility to get “automatically” ( except team in tunnel) measurements!

## Slide 4: RSM- 2014
Arc and LSS:
Sector 6-7 : 04.08 – 15.08
Sector 3-4 : 18.08 – 29.08
Sector 1-2 : 01.09 – 15.09
Sector 8-1 : 16.09 – 29.09
Sector 7-8 : 29.09 – 10.10
Sector 4-5 : 13.10 – 24.10
Sector 5-6 : 27.10 – 07.11
Sector 2-3 : 10.11 - 21.11
the load the sources to chariots at August 1st + Internal transport type A for transfer to P6 and P7 + to lower of chariots to parking place at P6 and P7
the Safety manual, training and availability@Point of tractors, radiation training to controlled area
Another jobs…

## Slide 5: Sector 6-7
BLMs (including LICs) from 4R6(MSD) to 4L7 (TCSM) : ARC and LSS
HV dividers
CFC cards
Check of the installation, the “space” location and pictures of monitors, mini-racks, B%boxes
Database (Layout, MTF, LSA) for ARC and LSS , synchronized and uploading to the electronic
Labels of monitors, HV divider, B%boxes ( BJLAP – BJLHT for LIC for example)
Bar code reader
Surface electronics at P6 and P7
Measurement DB
Ready for reparation