## BLM&BPM Installation
22/3/2004 |  |  | LHC installation planning (Beam Loss and BPM)
SECTOR |  | 7 - 8 |  |  |  |  | 8 - 1 |  |  |  |  | 4 - 5 |  |  |  |  | 3 - 4 |  |  |  |  | 5 - 6 |  |  |  |  | 6 - 7 |  |  |  |  | 2 - 3 |  |  |  |  | 1 - 2 | [5 empty] | Work Performed by | Installation Step | Description
2004 | Apr | [41 empty] | BL Section | 1 | Check and number location
| May | [41 empty] | 2 Persons |  | 1 week per sector (70 quads)
Jun
| Jul | [41 empty] | External (BDI-BL) | 2 | Support installation
| Aug | [41 empty] | 2 Persons | 3 | Chamber installation
| Sep | [42 empty] | 4 | Mini-rack installation
| Oct | [43 empty] | 4 quads per day Þ 16 chambers
| Nov | [43 empty] | 70 quads Þ 420 chambres Þ 17.5 days (4 weeks)
Dec
2005 | Jan | [41 empty] | TS-EL | 5 | BLM Cable installation
| Feb | [41 empty] | J-C. Guillaume | 6 | BLM cable connection to the chambers
| Mar | [41 empty] | 2 Persons |  | 4 quads per day Þ 24 cables
| Apr | [43 empty] | 70 quads Þ 1680 cables Þ 17.5 days (4 weeks)
May
| Jun | [41 empty] | TS-EL | 7 | Installation of fibre-optic patch panel
| Jul | [41 empty] | L. de Jonge | 8 | Fibre-optic termination and test
| Aug |  | 1 | 1 | 4 |  |  | 1 | 1 | 4 | [32 empty] | 2 Persons |  | X quads per day Þ X patch panels & X terminations
| Sep |  | 4 | 2 | 2 | 2 |  | 4 | 2 | 2 | 2 | [33 empty] | 70 quads Þ 70 patch-panels & XX terminations Þ XX days (X weeks)
Oct
| Nov | [41 empty] | External (BDI-EM) | 9 | Install chassis under quadrupole
| Dec | [41 empty] | 2 Persons | 10 | Connect BPM cables
2006 | Jan | [11 empty] | 1 | 1 | 4 | [28 empty] | 11 | Connect fibre-optic cables
| Feb | [11 empty] | 4 | 2 | 2 | 2 | [28 empty] | 8 quads per day Þ 8 chassis, 64 coax cables, 64 optical patch cords
| Mar | [16 empty] | 1 | 1 | 4 | [24 empty] | 70 quads Þ 9 days (2 weeks)
| Apr | [16 empty] | 4 | 2 | 2 | 2
| May | [41 empty] | EM Section | 12 | Test of chassis using local WorldFIP link
| Jun | [41 empty] | 2/3 Persons | 13 | Check of fibre-optic connection to the surface
| Jul | [6 empty] | BEAM | [35 empty] | 14 | Test of chassis using full WorldFIP link
| Aug | [21 empty] | 1 | 1 | 4 | [19 empty] | 8 quads per day
| Sep | [21 empty] | 4 | 2 | 2 | 2 |  | 1 | 1 | 4 | [14 empty] | 70 quads Þ 9 days (2 weeks)
| Oct | [26 empty] | 4 | 2 | 2 | 2
| Nov | [31 empty] | 1 | 1 | 4 | [7 empty] | BL Section | 15 | High Voltage cables test (CBH50)
| Dec | [31 empty] | 4 | 2 | 2 | 2 | [6 empty] | 2/3 Persons | 16 | Analog cables test (CB50) (with picometer and current source)
2007 | Jan | [36 empty] | 1 | 1 | 4 |  |  |  | 17 | Cables connection on the chassis
| Feb | [36 empty] | 4 | 2 | 2 | 2 |  |  | 18 | CFC installation and test
| Mar | [42 empty] | 19 | Optical fibres installation
| Apr | Final test | [9 empty] | Final test | [10 empty] | Final test | [9 empty] | Final test | [10 empty] | 20 | Test from surface
| May | [43 empty] | 8 quads per day Þ 8 CFC, 8 Alim, 18 optical patch cords
| Jun | [43 empty] | 70 quads Þ 9 days (2 weeks)
| Jul | [41 empty] | EM Section | 21 | Surface installation
| Aug |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | 2 Persons
| Sep | [41 empty] | BL Section
| Oct | [41 empty] | 2 Persons |  | 1 week per Point
Nov
Dec
Total
Weeks | EXT-BDI |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  | 48
Weeks | EXT-TS/EL |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  | 32
Weeks | BL |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  | 24
Weeks | EM |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  | 24
General Interconnections Works
Work | EXT-BDI |  |  | Steps 2 - 4 | [9 empty] | Steps 9 - 11 | [21 empty] | 192 |  |  |  | Man Weeks
Work | EXT-TS/EL |  |  | Steps 5 - 8 | [31 empty] | 128 |  |  |  | Man Weeks
Work | BL |  |  | Step 1 | [9 empty] | Step 15 - 20 | [9 empty] | Step 21 | [11 empty] | 144 |  |  |  | Man Weeks
Work | EM | [12 empty] | Step 12-14 | [9 empty] | Step 21 | [11 empty] | 96 |  |  |  | Man Weeks