## Tunnel Inst 2006
17.03.06 | [14 empty] | Beam Loss LHC installation planning
based on chamonix planning 2006
SECTOR |  |  |  | 7 - 8 |  | 8 - 1 |  |  | 3 - 4 |  |  | 4 - 5 |  |  |  | 5 - 6 |  |  | 6 - 7 |  |  | 2 - 3 |  |  | 1 - 2 | [5 empty] | hours
number of channels | [26 empty] | BL section | 1 | Check location
right ¦ left |  | 292 |  | 234 | 260 | 230 |  | 226 |  | 180 | 186 |  | 232 | 238 |  |  | 224 | 230 |  | 286 | 242 |  | 220 | 230 |  | 256 |  |  | 1 week/sector, 70 quad, 2 persons
total ¦ days | 3766 | 526 |  | 21.9167 | 490 | 20.4167 |  | 406 |  | 16.9167 | 418 |  | 17.4167 | 462 |  |  | 19.25 | 516 |  | 21.5 | 462 |  | 19.25 | 486 |  | 20.25 |  |  | 8 weeks / LHC 16 man weeks
Jul
[27 empty] | External BI | 2 | Supports chambers installation |  | 0.5
| Aug | [26 empty] | 3 | Chambers installation |  | 0.5
[28 empty] | 4 | Mounting of crate and fan unit ( BPM BLM) under quad |  | 0.2
( bicycle in the tunnel)
[30 empty] | sum | 1.2
Sep
[28 empty] | 5 | Cupper cables installation |  | 0.4
| Oct | [26 empty] | 6 | Cupper cables connection on the chambers (signal) |  | 0.2
[28 empty] | 7 | Cupper cables connection on the chambers (high voltage) |  | 0.2
[30 empty] | sum | 0.8
Nov
|  | BEAM |  |  | BEAM | [22 empty] | 9 | High Voltage cables test (CBH50) |  | 0.1
[28 empty] | 10 | Analog cables test (CB50) (with picometer and current source) |  | 0.4
| Dec | [26 empty] | 11 | Cables connection on the chassis |  | 0
[28 empty] | 12 | CFC installation and test |  | 0.1
[28 empty] | 13 | Optical fibres installation |  | 0.1
[28 empty] | 14 | Test of whole system (CFC + TC) |  | 0.3
2007 | Jan | [28 empty] | sum | 1
Feb
1 day for 4 quadrupole,
6 chambers/quad, 24 chambers, 13 cable/quad, 52 cables
Mar
70 quad, 910 cables, 17.5 days, 4 weeks
35 weeks/LHC, 70 man weeks
Apr
[27 empty] | External EL | 8 | Fiber patch pannel installation
[27 empty] | BL section | 15 | Surface installation
May
Jun
Jul
Aug
Sep
Works | BI / BL |  | Works 1 |  |  |  | Works 15
| BI / EXT |  | Works 2 - 4 |  |  |  | Works 5 - 7 |  |  |  | Works 9 - 14
| TS/EL EXT |  | Works 8

## Tunnel inst details 2005
[6 empty] | 18/2/2005 | [16 empty] | Beam Loss LHC installation planning
|  |  |  | 2006 | [47 empty] | 2007
|  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  |  | Total | Man
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | weeks | weeks | weeks
Interconnection closure |  |  | 1 - 2 | Feb 2: 10
Works 1 | persons | 2 | [57 empty] | 1 | 8 | 16 | BDI / BL | bar: Dec 2 to Feb 3
Works 2-4 | persons | 4 |  | Feb 2: 4 | 4 | 35 | 140 | BDI Ext
Works 5-6 | persons | 2 |  | Feb 2: 5 | 5 | 43 | 86 | TS Ext
Works 7 | persons | 2 |  | Feb 2: 2 | 2 | 19 | 38 | EL Ext
Works 8-13 | persons | 4 |  | Feb 2: 3 | 3 | 27 | 108 | BDI / BL
Works 14 | persons | 2 | [57 empty] | 1 | 8 | 16 | BDI / BL | bar: Dec 1
Interconnection closure |  |  | 2 - 3 | Feb 2: 10 | 10
Works 1 | [59 empty] | 1 | bar: Dec 2 to Feb 3
Works 2-4 |  |  |  | Feb 2: 4 | 4 |  | 140 | BDI/ BL
Works 5-6 |  |  |  | Feb 2: 5 | 5
Works 7 |  |  |  | Feb 2: 2 | 2 |  | 140 | BDI Ext
Works 8-13 |  |  |  | Feb 2: 3 | 3
Works 14 | [59 empty] | 1 |  | 124 | TS/EL Ext | bar: Dec 1
Interconnection closure |  |  | 3 - 4 | Aug 2: 8 | 8
Works 1 | [59 empty] | 1 | bar: Jun 4 to Aug 3
Works 2-4 |  |  |  | Aug 2: 4 | 4
Works 5-6 |  |  |  | Aug 2: 5 | 5
Works 7 |  |  |  | Aug 2: 2 | 2
Works 8-13 |  |  |  | Aug 2: 3 | 3
Works 14 | [59 empty] | 1 | bar: Jun 3
Interconnection closure |  |  | 4 - 5 | Jun 2: 8 | 8
Works 1 | [59 empty] | 1 | bar: Apr 4 to Jun 3
Works 2-4 |  |  |  | Jun 2: 4 | 4
Works 5-6 |  |  |  | Jun 2: 5 | 5
Works 7 |  |  |  | Jun 2: 2 | 2
Works 8-13 |  |  |  | Jun 2: 3 | 3
Works 14 | [59 empty] | 1 | bar: Apr 3
Interconnection closure |  |  | 5 - 6 | Aug 4: 8 | 8
Works 1 | [59 empty] | 1 | bar: Jul 2 to Sep 1
Works 2-4 |  |  |  | Aug 4: 5; Sep 2: Dump | 5
Works 5-6 |  |  |  | Aug 4: 6 | 6
Works 7 |  |  |  | Aug 4: 3 | 3
Works 8-13 |  |  |  | Aug 4: 4 | 4
Works 14 | [59 empty] | 1 | bar: Jul 1
Interconnection closure |  |  | 6-7 | Nov 1: 8 | 8
Works 1 | [59 empty] | 1 | bar: Sep 3 to Nov 2
Works 2-4 |  |  |  | Nov 1: 5; Nov 3: Coll | 5
Works 5-6 |  |  |  | Nov 1: 6; Nov 3: Dump | 6
Works 7 |  |  |  | Nov 1: 3 | 3
Works 8-13 |  |  |  | Nov 1: 4 | 4
Works 14 | [59 empty] | 1 | bar: Sep 2
Interconnection closure |  |  | 7 - 8 | Apr 2: 8 | 8
Works 1 | [59 empty] | 1 | bar: Feb 4 to Apr 3
Works 2-4 |  |  |  | Apr 2: 5; May 2: Coll | 5
Works 5-6 |  |  |  | Apr 2: 6 | 6
Works 7 |  |  |  | Apr 2: 3 | 3
Works 8-13 |  |  |  | Apr 2: 4 | 4
Works 14 | [59 empty] | 1 | bar: Feb 3
Interconnection closure |  |  | 8 - 1 | Mar 4: 8 | 8
Works 1 | [59 empty] | 1 | bar: Feb 2 to Apr 1; Sep 4 to Oct 3
Works 2-4 |  |  |  | Mar 4: 4; Oct 1: Beam | 4
Works 5-6 |  |  |  | Mar 4: 5 | 5
Works 7 |  |  |  | Mar 4: 2 | 2
Works 8-13 |  |  |  | Mar 4: 3 | 3
Works 14 | [59 empty] | 1 | bar: Feb 1; Sep 4 to Oct 3

## Tunnel Inst 2004
23/3/2004 | [5 empty] | Beam Loss LHC installation planning
SECTOR |  |  |  | 7- 8 |  |  | 8 -1 |  |  |  | 4 - 5 |  |  | 3- 4 |  |  | 5- 6 |  |  | 6- 7 |  |  | 2- 3 |  |  | 1- 2
2004 | Apr
May
Jun
Jul
Aug
Sep
| Oct | [28 empty] | 1 | Check location
| Nov | [29 empty] | 1 week / sector 70 quad, 2 persons
| Dec | [27 empty] | BL section |  | 8 weeks / LHC 16 man weeks
2005 | Jan
| Feb | [28 empty] | 2 | Supports installation
| Mar | [28 empty] | 3 | Chambers installation
| Apr | [28 empty] | 4 | Mini rack installation ( BPM BLM) under quad
| May | [29 empty] | ( electrical car in the tunnel)
| Jun | [29 empty] | ( transport of materials from lab to SR to Tunnel)
| Jul | [29 empty] | 1/2 day/ 2 quadrupole 16 chambers 2 persons
| Aug |  | 1 |  | 1 | 1 |  | 1 | [22 empty] | 70 quad 420 chambres 17.5 days 4 weeks
| Sep |  | 4 | 4 | 2 | 4 | 4 | 2 | [20 empty] | External |  | 35 weeks/LHC 70 man weeks
Oct
Nov
| Dec | [28 empty] | 5 | Cupper cables installation
2006 | Jan | [8 empty] | 1 |  | 1 | [17 empty] | 6 | Fiber patch pannel installation
| Feb | [8 empty] | 4 | 4 | 2 | [17 empty] | 7 | Micro fip installation
| Mar | [11 empty] | 1 |  | 1 | [14 empty] | 8 | Cupper cables connection on the chambers
| Apr | [11 empty] | 4 | 4 | 2 | [15 empty] | 1/2 day/ 2 quadrupole 24 cables 2 persons
| May | [29 empty] | 70 quad 1680 cables 17.5 days 4 weeks
| Jun | [27 empty] | External |  | 35 weeks/LHC 70 man weeks
| Jul |  |  |  |  | BEAM
| Aug | [14 empty] | 1 |  | 1 | [11 empty] | 9 | Chassis installation (under quadrupole) with BPM
| Sep | [14 empty] | 4 | 4 | 2 | 1 |  | 1 | [8 empty] | 10 | High Voltage cables test (CBH50)
| Oct | [14 empty] | 1 | 1 | 1 | 4 | 4 | 2 | 1 |  | 1 | [5 empty] | 11 | Analog cables test (CB50) (with picometer and current source)
| Nov | [14 empty] | (Dump) |  |  | 1 | 1 | 1 | 4 | 4 | 2 | [5 empty] | 12 | Cables connection on the chassis
| Dec | [17 empty] | (Collim.) |  |  | 1 | 1 | 1 | [5 empty] | 13 | CFC installation and test
2007 | Jan | [20 empty] | (Collim.) |  |  | 1 |  | 1 |  |  | 14 | Optical fibres installation
| Feb | [23 empty] | 4 | 4 | 2 |  |  | 15 | Test from surface
| Mar | [29 empty] | 1 day 8 quad 8CFC, 8 Alim, 18 otical cords, 3- 4 persons
| Apr | Final test | [6 empty] | Final test | [6 empty] | Final test | [5 empty] | Final test | [8 empty] | 70 quad 9 days 2 weeks/ sector 3- 4 persons
| May | [27 empty] | BL section |  | 19 weeks/LHC 57 or 72 man weeks
Jun
Jul
| Aug |  | BEAM |  |  | BEAM |  |  |  | BEAM |  |  | BEAM |  |  | BEAM |  |  | BEAM |  |  | BEAM |  |  | BEAM |  |  |  |  | 16 | Surface installation
| Sep | [29 empty] | 1 week / point 2 persons
| Oct | [27 empty] | BL section |  | 8 weeks / LHC 16 man weeks
Nov
Dec
Total
Weeks | EXT |  | 8 |  |  | 8 |  |  |  | 8 |  |  | 8 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 8 |  |  | 70
Weeks | BL |  | 4 |  |  | 4 |  |  |  | 4 |  |  | 4 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 4 |  |  | 35
Generals Interconnections Works
Works | EXT |  |  | Works 2 - 4 | [6 empty] | Works 5 - 8 | [10 empty] | 140 man weeks
Works | BL |  |  | Works 1 | [6 empty] | Works 9 - 15 | [5 empty] | Works 16 |  |  |  |  | 89 or 104 man weeks

## BLM&BPM Installation 2004
22/3/2004 |  |  | LHC installation planning (Beam Loss and BPM)
SECTOR |  | 7 - 8 |  |  |  |  | 8 - 1 |  |  |  |  | 4 - 5 |  |  |  |  | 3 - 4 |  |  |  |  | 5 - 6 |  |  |  |  | 6 - 7 |  |  |  |  | 2 - 3 |  |  |  |  | 1 - 2 | [5 empty] | Work Performed by | Installation Step | Description
2004 | Apr | [41 empty] | BL Section | 1 | Check and number location
| May | [41 empty] | 2 Persons |  | 1 week per sector (70 quads)
Jun
| Jul | [41 empty] | External (BDI-BL) | 2 | Support installation
| Aug | [41 empty] | 2 Persons | 3 | Chamber installation
| Sep | [42 empty] | 4 | Mini-rack installation
| Oct | [43 empty] | 4 quads per day Þ 16 chambers
| Nov | [43 empty] | 70 quads Þ 420 chambres Þ 17.5 days (4 weeks)
Dec
2005 | Jan | [41 empty] | TS-EL | 5 | BLM Cable installation
| Feb | [41 empty] | J-C. Guillaume | 6 | BLM cable connection to the chambers
| Mar | [41 empty] | 2 Persons |  | 4 quads per day Þ 24 cables
| Apr | [43 empty] | 70 quads Þ 1680 cables Þ 17.5 days (4 weeks)
May
| Jun | [41 empty] | TS-EL | 7 | Installation of fibre-optic patch panel
| Jul | [41 empty] | L. de Jonge | 8 | Fibre-optic termination and test
| Aug |  | 1 | 1 | 4 |  |  | 1 | 1 | 4 | [32 empty] | 2 Persons |  | X quads per day Þ X patch panels & X terminations
| Sep |  | 4 | 2 | 2 | 2 |  | 4 | 2 | 2 | 2 | [33 empty] | 70 quads Þ 70 patch-panels & XX terminations Þ XX days (X weeks)
Oct
| Nov | [41 empty] | External (BDI-EM) | 9 | Install chassis under quadrupole
| Dec | [41 empty] | 2 Persons | 10 | Connect BPM cables
2006 | Jan | [11 empty] | 1 | 1 | 4 | [28 empty] | 11 | Connect fibre-optic cables
| Feb | [11 empty] | 4 | 2 | 2 | 2 | [28 empty] | 8 quads per day Þ 8 chassis, 64 coax cables, 64 optical patch cords
| Mar | [16 empty] | 1 | 1 | 4 | [24 empty] | 70 quads Þ 9 days (2 weeks)
| Apr | [16 empty] | 4 | 2 | 2 | 2
| May | [41 empty] | EM Section | 12 | Test of chassis using local WorldFIP link
| Jun | [41 empty] | 2/3 Persons | 13 | Check of fibre-optic connection to the surface
| Jul | [6 empty] | BEAM | [35 empty] | 14 | Test of chassis using full WorldFIP link
| Aug | [21 empty] | 1 | 1 | 5 | [19 empty] | 8 quads per day
| Sep | [21 empty] | 5 | 2 | 2 | 3 |  | 1 | 1 | 5 | [14 empty] | 70 quads Þ 9 days (2 weeks)
| Oct | [26 empty] | 5 | 2 | 2 | 3
| Nov | [31 empty] | 1 | 1 | 5 | [7 empty] | BL Section | 15 | High Voltage cables test (CBH50)
| Dec | [31 empty] | 5 | 2 | 2 | 3 | [6 empty] | 2/3 Persons | 16 | Analog cables test (CB50) (with picometer and current source)
2007 | Jan | [36 empty] | 1 | 1 | 4 |  |  |  | 17 | Cables connection on the chassis
| Feb | [36 empty] | 4 | 2 | 2 | 2 |  |  | 18 | CFC installation and test
| Mar | [42 empty] | 19 | Optical fibres installation
| Apr | Final test | [9 empty] | Final test | [10 empty] | Final test | [9 empty] | Final test | [10 empty] | 20 | Test from surface
| May | [43 empty] | 8 quads per day Þ 8 CFC, 8 Alim, 18 optical patch cords
| Jun | [43 empty] | 70 quads Þ 9 days (2 weeks)
| Jul | [41 empty] | EM Section | 21 | Surface installation
| Aug |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | 2 Persons
| Sep | [41 empty] | BL Section
| Oct | [41 empty] | 2 Persons |  | 1 week per Point
Nov
Dec
Total
Weeks | EXT-BDI |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 7 |  |  |  |  | 7 |  |  |  |  | 6 |  |  |  | 51
Weeks | EXT-TS/EL |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 5 |  |  |  |  | 5 |  |  |  |  | 4 |  |  |  | 35
Weeks | BL |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 5 |  |  |  |  | 5 |  |  |  |  | 4 |  |  |  | 35
Weeks | EM |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  | 24
General Interconnections Works
Work | EXT-BDI |  |  | Steps 2 - 4 | [9 empty] | Steps 9 - 11 | [21 empty] | 204 |  |  |  | Man Weeks
Work | EXT-TS/EL |  |  | Steps 5 - 8 | [31 empty] | 140 |  |  |  | Man Weeks
Work | BL |  |  | Step 1 | [9 empty] | Step 15 - 20 | [9 empty] | Step 21 | [11 empty] | 210 |  |  |  | Man Weeks
Work | EM | [12 empty] | Step 12-14 | [9 empty] | Step 21 | [11 empty] | 96 |  |  |  | Man Weeks

## General old 2004
2004-02-16 |  |  |  | Planning Beam Loss monitors
|  | 2004 |  |  |  | 2005 |  |  |  | 2006 |  |  |  | 2007
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
7--8
Front end electronics, Power supply developpement | bar: Q1 to 2004 Q3; 2006 Q2
Front end electronics, Power supply production | bar: 2004 Q4 to 2005 Q4; 2006 Q2; 2007 Q3
Front end electronics, Power supply tests | bar: 2005 Q2 to 2006 Q2; 2007 Q3
[10 empty] | S |  |  |  |  | C
Digital elctronics developpement | bar: Q1 to 2004 Q4; 2006 Q2
Digital elctronics pruduction | bar: 2004 Q1 to 2006 Q2
Digital elctronics tests | bar: 2005 Q2 to 2006 Q3
[10 empty] | B |  |  |  |  | B
Ionisation chamber, SEM developpement | bar: Q1 to 2004 Q3; 2006 Q2; 2007 Q3
Ionisation chamber, SEM production | bar: 2004 Q4 to 2006 Q2; 2007 Q3
Ionisation chamber, SEM test | bar: 2005 Q2 to 2006 Q3
Installation of fibres | bar: Q1 to 2005 Q4; 2006 Q2
Installation of cupper cables (BJBAP, BJBHT, NG18, CBH50) | bar: Q1 to 2005 Q4; 2006 Q2
Check of cupper cable (NG18, CBH50) | bar: Q1 to 2005 Q4; 2006 Q2
Production, test CBH50, CB50 cables (short cables) | bar: 2004 Q1 to 2005 Q4; 2006 Q2
Installation of chambers | bar: 2005 Q3 to 2006 Q1
Installation of short cables | bar: 2005 Q3 to 2006 Q1
Installation of crates in the tunnel | bar: 2005 Q3 to 2006 Q1
Post-installation check of cabling | bar: 2005 Q3 to 2006 Q1
Installation of crates in the surface | bar: 2005 Q4 to 2006 Q1
Test of each channel from surface | bar: 2005 Q4 to 2006 Q1
Developpement | bar: Q1 to 2004 Q3
Production, Tests | bar: 2004 Q4 to 2006 Q3
Installation | bar: 2005 Q3 to 2006 Q1