## Sheet1
				21.05.2014

				2013		2014	2015

BGI	64876	Exploitation LHC	LHC BGI	64	92	0
	64040	LIU-SPS Wirescanner & BGI Upgrades	wirescanner BGI	90	155	70			in jens listing 70 in BI LIU 100 k (in 50k in Brennan LIU 28.02.2014)
	64030	LIU-PS Beam Instrumentation	new BGI	116	69	200	60		in jens list missing (2014 money spend by Thibaut 71k)
	code missing	Consolidation LHC				100	100		request done but status not clear

	to be ordered SPS and LHC	Pump 1				16
		Camara + electroncs 1				35
		MCP 3				16
		new MCP 1				4
		HV card production	code to be defined
		joints				10
		new SPS detector				40
		operate systems				20
				sum		141

	to be ordered PS	feasibility				60			requested but not allocated
		Vac + elec + cables				100	100		„
		Magnets power	clarification for PC needed, Mariusz			100	100		„

## LIU agreement SPS BGV 06.03.14
Produce New Fast SPS Wirescanners	LIU-SPS 6	bernd.dehning@cern.ch		01/01/14	12/31/17
Design, manufacture and installation	64040	650000	CHF
Mechanical design	0	100	%	01/01/14	12/31/14
Mechanical production (1 spare scanner)	0	100	%	01/01/15	12/31/16
Mechanical installation	0	4	U	01/01/17	12/31/17
Electronics design	0	100	%	01/01/15	12/31/15
Electronics production and installation	0	100	%	01/01/16	12/31/16
Upgrade SPS BGI	LIU-SPS 6	mariusz.sapinski@cern.ch		01/01/14	12/31/15
Design, manufacture and installation	64040	100000	CHF
Mechanical optics design and production	0	2	U	01/01/14	12/31/15
Electronics design, purchase and installation	0	2	U	01/01/14	12/31/15
Upgrade ionisation chamber BLMs	LIU-SPS 6	christos.zamantzas@cern.ch		01/01/15	12/31/19
Design, manufacture and installation	64041	955000	CHF
Electronics design	0	100	%	01/01/15	12/31/16
Electronics production and installation	0	100	%	01/01/15	12/31/17
Installation & Additional cabling	0	100	%	01/01/18	12/31/19
Provide electronics for fast BLMs	LIU-SPS 6	christos.zamantzas@cern.ch		01/01/14	12/31/14
Design, manufacture and installation	64041	50000	CHF
Electronics design	0	100	%	01/01/14	06/30/14
Electronics production, purchase and installation	0	2	U	07/01/14	12/31/14