## budget list
				13.08.2014

				2013	Spend 2013	2014	2015	2016	2017	2018	2019	sum

BLM	64020	LIU-PSB BLM Upgrades		90	367
	64041	LIU-SPS BLM Upgrade (diamond acquistion)		50		50					see other worksheet
	64041	LIU-SPS BLM					xx	xx	xx	xx	xx	955		see other worksheet, includes 40 k for chamber production

	64720	Consolidation - PS BLM systems	Originally 320 in 2013	125	154	320					150 k transfered to SEM, 180 k foreseen for 2014 + 150k = 320k, in ACC-CON 250 k foreseen for 2014
	64734	Beam Loss Monitors LINAC4		45	73					55 k subratcted last year by Rhodri left 45 k

	64726	HL-LHC LHC BLM rad hard electronics		4	5.4	152	100					mail Rhodri,18.03.2014
	64727	LHC BLM dismantling for interconnect work		433	651	240					Foreseen for 2014 240k (mail 23.08.13), at 01.02.14 budget pipeline 221k (IHEP team end of August, Slava end of June)

	64274	ExploitationBeam Beam loss & wire scanners PS		37	31	294					25 k mail Rhodri 02.05.2014 (in addtion he put the 250 k for the ionisation chambers on the code), allocated on code (CET) 294 24.04.2014
	64374	ExploitationBeam loss & wire scanners SPS		37	38	52					114 % used 21.05.14
	64874	ExploitationBeam Beam Loss Monitors LHC		368	252	278					CET 24.02.2014

	no code yet	consolidation request VFC				150	150

	64061	HL-LHC BLM				100

				64061 mail 22.05.14 To your question, / Any idea how much more you need on 64061 (HL-LHC: BLM upgrades) this year – 40kCHF now allocated? / The code is with the 40 k at 104 %, some money is needed for the preparation of the new IRRAD area, 20 k, for the contract with St-Petersburg 20 k and for a LASER to test the CVDs during irradiation. 20 k. 60 k in total.

## code 64727
	code	budget	64727

budget	foreseen for 2014	240

	in pipeling 04.02.	221

	Slava end 2014, 6 month (5.2k/month)	31.2

unforeseen	IHEP Sep. 4 persons 5.85 k/monnth	23.4

unforeseen	IHEP Oct + Nov 2 persons 5.85 k/monnth	23.4

unforeseen	hardware	30

	Total	-89

## consolisdation_budget requests
CET Totals by Cost Centre

Last CET Data Extraction: 15 Apr 2014, bookclosed for November (Stores: March).

Date: 15 Apr 2014
Query: Organic Unit BE-BI and Category of Accounts Materiel and Time Period This Year + Carry Over and Type (Rec. / Non-Rec.) Recurrent

		Budget Code Description	Charged to Budget Code (CHF)	Carry Over (CHF)	Annual Commitment (CHF)	Annual Open Commitment (CHF)	Payment Budget (CHF)	Pipeline (CHF)	Commitments incl. Pipeline (CHF)	Balance (Excluding Pipeline) (CHF)	Percentage Budget Used (Excluding Pipeline)	New request
	64274	Beam loss & wire scanners PS	21541.38	19009.2	71178.5	49637.12	294000		71178.5	222821.5	24	250 k are reserved for the production of the ionisation chambers, request Jonthan + update, missing 90 k
	64374	Beam loss & wire scanners SPS	31773.3	15424.4	48938.8	17165.5	52000	1510	50448.8	3061.2	94	SPS replacement of BLM power supplyes + cable replacement, missing 30 k
	64874	Beam Loss Monitors LHC	81329.7	53918.14	125443.77	44114.07	330000	30640	156083.77	204556.23	38	OK
	64875	Wire scanners LHC	5882.44	223.22	10732.79	4850.35	18000		10732.79	7267.21	60	likely more needed for repair, missing 25 k
	64876	Ionisation Gas Monitors LHC	6759.85	3379.96	20791.14	14031.29	50000		20791.14	29208.86	42	OK
	Total of Recurrent:		870210.21	320538.64	2145923.27	1275713.06	3541000	366768.79	2512692.06	1395076.73	61
Grand Total:			870210.21	320538.64	2145923.27	1275713.06	3541000	366768.79	2512692.06	1395076.73	61

All figures shown are in Swiss Francs (CHF).

## LIU agreement SPS 06.03.14
Produce New Fast SPS Wirescanners	LIU-SPS 6	bernd.dehning@cern.ch		01/01/14	12/31/17			Mallika 06.03.2014
Design, manufacture and installation	64040	650000	CHF
Mechanical design	0	100	%	01/01/14	12/31/14
Mechanical production (1 spare scanner)	0	100	%	01/01/15	12/31/16
Mechanical installation	0	4	U	01/01/17	12/31/17
Electronics design	0	100	%	01/01/15	12/31/15
Electronics production and installation	0	100	%	01/01/16	12/31/16
Upgrade SPS BGI	LIU-SPS 6	mariusz.sapinski@cern.ch		01/01/14	12/31/15
Design, manufacture and installation	64040	100000	CHF
Mechanical optics design and production	0	2	U	01/01/14	12/31/15
Electronics design, purchase and installation	0	2	U	01/01/14	12/31/15
Upgrade ionisation chamber BLMs	LIU-SPS 6	christos.zamantzas@cern.ch		01/01/15	12/31/19
Design, manufacture and installation	64041	955000	CHF
Electronics design	0	100	%	01/01/15	12/31/16
Electronics production and installation	0	100	%	01/01/15	12/31/17
Installation & Additional cabling	0	100	%	01/01/18	12/31/19
Provide electronics for fast BLMs	LIU-SPS 6	christos.zamantzas@cern.ch		01/01/14	12/31/14
Design, manufacture and installation	64041	50000	CHF
Electronics design	0	100	%	01/01/14	06/30/14
Electronics production, purchase and installation	0	2	U	07/01/14	12/31/14