## BLM System
Sub-System | needed for installation | spare (10%) | total needed quantity | production loss | pieces per card | to be ordered | lost units while tests | Status | in stock | ordred | delivered | checked by | quantity difference | Unit Price | Total Price [CHF] | delivery schedule | comments | DAI | Price/Card
|  | 0.1 |  | 0.055 |  | 749.683
CFC | 646 | 64.6 | 710.6 | 39.083 |  | 750 | [9 empty] | F82/Mar90/May73/Jul68/Au80/O86Dec163
Printed Circuit | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Partial | 0 | 50 | 50 |  | -700 | 37 | 27750 |  | https://edms.cern.ch/item/EDA-00593/0
APW 951-263903D (case) | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Ordered |  | 750 |  |  | -750 | 34.07 | 25552.5 |  | http://www.apw.com/raptor/pdf/pdf1-846.pdf
Card mount bracket | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Ordered |  | 1500 |  |  | -1500 | 1.525 | 2287.5
Flat Alloy Bar | 62.016 | 6.2016 | 68m |  | 0.096 | 75 m |  | Ordered |  | 75m |  |  |  | 0.907 | 68.025
Mechanical treatment alloy bar | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Ordered |  |  |  |  | -750 | 3.1 | 2325
AXN350038S (GOH connector) | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Ordered | 0 | 1500 | 1500 |  | 0 | 5 | 7500 |  | http://www.naisweb.com/e/connecte/con_eng/pdf/con_eng_np3.pdf
CERN CHIPIDEA LVDS_RX | 3876 | 387.6 | 4263.6 | 234.498 | 6 | 4500 |  | TID launched |  |  | 4650 |  | 150 | 5.5 | 24750
CERN CHIPIDEA AD41240_V2 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | TID launched |  |  | 1550 |  | 50 | 18.75 | 28125 |  | http://proj-kchip.web.cern.ch/proj-Kchip/preshower/doc/AD41240%20Manual%20v0.2.pdf
A54SX72A2PQ208I | 646 | 64.6 | 710.6 | 39.083 | 1 | 768 |  | Inquiry |  | 768 | 161 |  | -607 | 75.64 | 58091.52 |  | http://www.actel.com/documents/SXA_DS.pdf
OPA627AU / OPA637AU | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Inquiry |  | 6000 | 6000 |  | 0 | 19.67 | 118020 |  | http://focus.ti.com/lit/ds/symlink/opa627.pdf
NE521DN | 2584 | 258.4 | 2842.4 | 156.332 | 4 | 3000 |  | Ordered | 0 | 3000 | 3000 |  | 0 | 2.8044 | 8413.2 | 2005-12-16 | http://www.semiconductors.philips.com/acrobat_download/datasheets/NE521_2.pdf
74HCT123D | 2584 | 258.4 | 2842.4 | 156.332 | 4 | 3000 |  | Complete | 3000 | 3000 | 3000 | Ewald | 0 | 0.10906 | 327.18 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/74HC_HCT123_3.pdf
THS4141CD | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Ordered | 0 | 6000 | 0 |  | -6000 | 4.27 | 25620 | week 51 05 | http://focus.ti.com/lit/ds/symlink/ths4141.pdf
AD5346 | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Ordered | 0 | 750 | 750 |  | 0 | 5.116 | 3837 | 2005-12-12 | http://www.analog.com/UploadedFiles/Data_Sheets/4283875071479AD5346_7_8_0.pdf
TL072CD | 1938 | 193.8 | 2131.8 | 117.249 | 3 | 2250 |  | Ordered | 0 | 2500 | 2500 |  | 250 | 0.0976 | 219.6 | 2005-12-12 | http://focus.ti.com/lit/ds/symlink/tl072.pdf
LMV393M | 5814 | 581.4 | 6395.4 | 351.747 | 9 | 6750 |  | Ordered | 855 | 6805 | 6805 |  | 55 | 0.49493 | 3340.7788 | 2005-01-10 | http://cache.national.com/ds/LM/LMV331.pdf
LM4140-2.5V | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Ordered | 0 | 750 | 750 |  | 0 | 2.644 | 1983 | 2005-01-31 | http://cache.national.com/ds/LM/LM4140.pdf
X357, CFPS-72B (40MHz) | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Ordered | 250 |  | 750 |  | 0 | 1.244 | 933 |  | http://www.cmac.com/mt/databook/oscillators/semtech/cfps-72.pdf
SST176 | 10336 | 1033.6 | 11369.6 | 625.328 | 16 | 12000 |  | Ordered | 3000 | 12000 | 3000 |  | -9000 | 0.20215 | 2425.8462 |  | http://www.vishay.com/docs/70257/70257.pdf
BAV99LT1 | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete | 6000 | 6000 | 6000 | Ewald | 0 | 0.011685 | 70.11 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/BAV99_4.pdf
BAV199 | 16150 | 1615 | 17765 | 977.075 | 25 | 18750 |  | Complete | 21000 | 21000 | 21000 | Ewald | 2250 | 0.043624 | 817.95 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/BAV199_4.pdf
EPCOS SMD-NTC resistor B57621C103K62 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1500 | 1500 | 1500 | Ewald | 0 | 0.38867 | 583 |  | http://www.epcos.com/inf/50/db/ntc_02/00600061.pdf
High ohmic resistor CHS 1206 10G 5 500 | 10336 | 1033.6 | 11369.6 | 625.328 | 16 | 12000 |  | Ordered | 1900 | 10100 | 0 |  | -12000 | 2.08 | 24960 | 2006-01-17 | http://www.willow.co.uk/CHS.pdf
1/4W 10% SMD Trimmer 11 Turns 1k | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Ordered | 0 | 6000 | 250 |  | -5750 | 1.5285 | 9171 | 2006-01-02 | http://www.vishay.com/docs/51009/tsm4.pdf
1/4W 10% SMD Trimmer 11 Turns 5k | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Ordered | 0 | 6000 | 0 |  | -6000 | 1.5285 | 9171 | 2006-01-02 | http://www.vishay.com/docs/51009/tsm4.pdf
100uF 10V SMD | 5814 | 581.4 | 6395.4 | 351.747 | 9 | 6750 |  | Complete | 7000 |  | 7000 | Ewald | 250 | 0.27986 | 1889.0357 |  | http://www.kemet.com/kemet/web/homepage/kechome.nsf/vapubfilesname/F3102T495.pdf/$file/F3102T495.pdf
10uF SMD 1206 | 31654 | 3165.4 | 34819.4 | 1915.067 | 49 | 36750 |  | Complete | 38000 | 38000 | 38000 | Ewald | 1250 | 0.091737 | 3371.3289 |  | http://www.murata.com/catalog/c02e11.pdf#page=14
100nF SMD 0402 | 31008 | 3100.8 | 34108.8 | 1875.984 | 48 | 36000 |  | Ordered | 0 | 40000 | 40000 |  | 4000 | 0.006232 | 224.352 | week 50 05 | http://www.farnell.com/datasheets/57604.pdf
100nF SMD 0805 | 78166 | 7816.6 | 85982.6 | 4729.043 | 121 | 90750 |  | Complete | 92000 |  | 92000 | Ewald | 1250 | 0.006232 | 565.554
10pF SMD 0805 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 4000 |  | 4000 | Ewald | 2500 | 0.006232 | 9.348
E-2000 Adapter for Front panel | [5 empty] | 1500 |  | Complete |  | 1500 | 1500 |  | 0 | 9.1 | 13650
Screw fixing clip E-2000 | [5 empty] | 1500 |  | Complete |  | 1500 | 1500 |  | 0 | 0.4 | 600
0.01uF C1206 | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete |  |  | 8000 |  | 2000 | 1.4 | 8400
100pF C0805 | 1938 | 193.8 | 2131.8 | 117.249 | 3 | 2250 |  | Complete |  |  | 4000 |  | 1750 | 2.4 | 5400
100pF C1206 | 12920 | 1292 | 14212 | 781.66 | 20 | 15000 |  | Complete |  |  | 16000 |  | 1000 | 3.4 | 51000
10pF C1206 | 12920 | 1292 | 14212 | 781.66 | 20 | 15000 |  | Complete |  |  | 16000 |  | 1000 | 4.4 | 66000
33pF C1206 | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete |  |  | 4000 |  | 3250 | 5.4 | 4050
470pF C1206 | 1938 | 193.8 | 2131.8 | 117.249 | 3 | 2250 |  | Complete |  |  | 4000 |  | 1750 | 6.4 | 14400
4.7nF C1206 | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete |  |  | 8000 |  | 2000 | 7.4 | 44400
| 0 | 0 | 0 | 0 |  | 0 | [6 empty] | 0 | 8.4 | 0
0
standard material | [12 empty] | 0
100nF | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [6 empty] | -750 | 0.02 | 15 |  | 10.03.04.500.2
10nF | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [6 empty] | -6000 | 0.02 | 120 |  | 10.03.04.400.5
10pF | 16796 | 1679.6 | 18475.6 | 1016.158 | 26 | 19500 | [6 empty] | -19500 | 0.02 | 390 |  | 10.03.04.100.4
33pF | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [6 empty] | -6000 | 0.02 | 120 |  | 10.03.04.133.5
100pF | 15504 | 1550.4 | 17054.4 | 937.992 | 24 | 18000 | [6 empty] | -18000 | 0.03 | 540 |  | 10.03.04.200.1
470pF | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [6 empty] | -6000 | 0.02 | 120 |  | 10.03.04.247.6
4.7nF | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [6 empty] | -6000 | 0.02 | 120 |  | 10.03.04.347.3
DIN 41612-TYPE C | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  |  |  |  | 750 |  | 0 | 1.7 | 1275 |  | 09.61.33.215.0
100 | 3876 | 387.6 | 4263.6 | 234.498 | 6 | 4500 | [6 empty] | -4500 | 0.02 | 90 |  | 11.24.05.200.9
10K | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  |  |  |  | 10000 |  | 4000 | 0.02 | 120 |  | 11.24.05.400.3
9.1K | 1938 | 193.8 | 2131.8 | 117.249 | 3 | 2250 |  |  |  |  | 5000 |  | 2750 | 0.02 | 45 |  | 11.24.05.391.7
3.3K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  |  |  |  | 15000 |  | 14250 | 0.02 | 15 |  | 11.24.05.333.7
1.6K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [6 empty] | -750 | 0.02 | 15 |  | 11.24.05.316.8
51 | 16150 | 1615 | 17765 | 977.075 | 25 | 18750 |  |  |  |  | 5000 |  | -13750 | 0.02 | 375 |  | 11.24.05.151.1
6.8K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [6 empty] | -750 | 0.02 | 15 |  | 11.24.05.368.6
39K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  |  |  |  | 5000 |  | 4250 | 0.02 | 15 |  | 11.24.05.439.8
6.2K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [6 empty] | -750 | 0.02 | 15 |  | 11.24.05.362.2
11K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  |  |  |  | 5000 |  | 4250 | 0.02 | 15 |  | 11.24.05.411.0
2.7K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [6 empty] | -750 | 0.02 | 15 |  | 11.24.05.327.5
2.4K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [6 empty] | -750 | 0.02 | 15 |  | 11.24.05.324.8
00 | 3230 | 323 | 3553 | 195.415 | 5 | 3750 |  |  |  |  | 15000 |  | 11250 | 0.02 | 75 |  | 11.24.05.000.5
3.6K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [6 empty] | -750 | 0.02 | 15 |  | 11.24.05.336.4
22K | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  |  |  |  | 5000 |  | 3500 | 0.02 | 30 |  | 11.24.05.422.7
240 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 | [6 empty] | -1500 | 0.02 | 30 |  | 11.24.05.224.1
1.2K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [6 empty] | -750 | 0.02 | 15 |  | 11.24.05.312.2
2K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [6 empty] | -750 | 0.02 | 15 |  | 11.24.05.320.2
390 | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  |  |  |  | 5000 |  | -1000 | 0.02 | 120 |  | 11.24.05.239.4
2.2K | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  |  |  |  | 10000 |  | 4000 | 0.02 | 120 |  | 11.24.05.322.0
1.5K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  |  |  |  | 5000 |  | 4250 | 0.02 | 15 |  | 11.24.05.315.9
12K | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  |  |  |  | 5000 |  | 3500 | 0.02 | 30 |  | 11.24.05.412.9
470 | 31654 | 3165.4 | 34819.4 | 1915.067 | 49 | 36750 |  |  |  |  | 10000 |  | -26750 | 0.02 | 735 |  | 11.24.05.247.4
5.1K | 10336 | 1033.6 | 11369.6 | 625.328 | 16 | 12000 |  |  |  |  | 10000 |  | -2000 | 0.02 | 240 |  | 11.24.05.351.5
5.6K | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [6 empty] | -6000 | 0.02 | 120 |  | 11.24.05.356.0
100K | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  |  |  |  | 10000 |  | 4000 | 0.02 | 120 |  | 11.24.05.500.0
1K | 31008 | 3100.8 | 34108.8 | 1875.984 | 48 | 36000 |  |  |  |  | 15000 |  | -21000 | 0.02 | 720 |  | 11.24.05.300.6
0 Ohm (0805) | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  |  |  |  | 1000 |  | 250 | 0.01262 | 9.465
24k | [10 empty] | 5000
56k | [10 empty] | 5000
150k | [10 empty] | 5000
4.7k | [10 empty] | 5000
390k | [10 empty] | 5000
130k | [10 empty] | 5000
75k | [10 empty] | 5000
3k | [10 empty] | 5000
1M | [10 empty] | 5000
510k 1206 | [10 empty] | 15000 |  | 15000
Jumper | [10 empty] | 800
0
GOH | 1292 | 129.2 | 1421.2 | 113.696 |  | 1534.896 |  |  |  | 1525 |  |  | -9.896 |  |  |  | http://cms-tk-opto.web.cern.ch/cms-tk-opto/ecal/components/goh.html
GOL (order) | 1292 | 129.2 | 1421.2 |  |  | 1525 |  | Completed |  | 1580 | 1580 |  | 55 |  |  |  | http://proj-gol.web.cern.ch/proj-gol/
LASER+E2000 APC | 1292 | 129.2 | 1421.2 |  |  | 1525 |  |  |  | 1580 | 1580 | Claudine | 55 | 134.5 | 212510 |  | http://cms-tk-opto.web.cern.ch/cms-tk-opto/tk/components/laserpill.html
GOH | 1292 | 129.2 | 1421.2 |  |  | 1525 |  |  |  | 1580 |  |  | -1525 |  |  | J300/Mar400/May400/Julrest
CRT4T | 1292 | 129.2 | 1421.2 |  |  | 1525 |  | TID launched |  | 75, 1505 | 75 |  | -1450 |  |  | total mid feb 06
0
TC | 331 | 33.1 | 364.1 | [13 empty] | EDA-00998
STRATIX EP1S40F780C7 | 331 | 33.1 | 364.1 |  | 1 | 364.1 |  | Completed |  | 360 |  |  | -364.1 | 483 | 212133.6 |  | http://altera.com/products/devices/stratix/stx-index.jsp
AS7C33512PFS32A-166TQC | 993 | 99.3 | 1092.3 |  | 3 | 1092.3 |  | Completed |  | 1122 |  |  | -1092.3 | 6.6 | 9034.344 |  | http://www.alsc.com/pdf/sram.pdf/fs/as7c331mpfs32a-36a_v2.3.pdf
PMC Connector (Socket: 71439-1164 (SMT 64WAY 11/12MM HIGH)) | 662 | 66.2 | 728.2 | 14.564 | 2 | 742.764 |  | Completed |  | 840 |  |  | -742.764 | 2.87 | 2410.8 |  | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/MX71439.pdf
Front Pannel / Handles(x2) / Fixation Bracket | 331 | 33.1 | 364.1 |  | 1 | 364.1 |  | Completed |  |  |  |  | -364.1
Front Pannel - Machining & Engraving | 331 | 33.1 | 364.1 |  | 1 | 364.1 | [6 empty] | -364.1
E-2000 Mating Adapter | 662 | 66.2 | 728.2 |  | 2 | 728.2 |  | Offer |  |  |  |  | -728.2
E-2000 Sleeve for Front Panel | 1324 | 132.4 | 1456.4 |  | 4 | 1456.4 |  | Offer |  |  |  |  | -1456.4
0
TC mezzanine | 331 | 33.1 | 364.1 | [13 empty] | EDA-00780
TLK1501IRCP/R | 1324 | 132.4 | 1456.4 | 29.128 | 4 | 1485.528 |  | Completed | 0 | 1440 | 1440 |  | -45.528 | 7 | 15664.32 | 2005-01-06 | http://focus.ti.com/docs/prod/folders/print/tlk1501.html | 2025559 | 43.512
Photodiodes (Neoptek NTPPT-3EPNH Pigtailed 1.25Gbps InGaAs PIN/TIA Receiver) | 1324 | 132.4 | 1456.4 | 29.128 | 4 | 1485.528 |  | Ordered | 0 | 1490 | 200 |  | -1285.528 | 69.331 | 102993.1418 | Jan: 200, Mar: 700, Mai: rest | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/TXP0036.pdf |  | 276.4917
Crystal Osc. (C-Mac 40.00 MHz IQXO-73B) | 331 | 33.1 | 364.1 | 7.282 | 1 | 371.382 |  | Completed | 0 | 400 | 400 |  | 28.618 | 0.8 | 498 |  | http://www.cmac.com/mt/databook/oscillators/smd/spxo/iqxo_70.html | 2028759 | 1.245
PMC Connector (Header: 71436-2164 (SMT 64WAY 10MM HIGH)) | 662 | 66.2 | 728.2 | 14.564 | 2 | 742.764 |  | Completed |  | 760 | 760 |  | 17.236 | 2.99 | 2272.4 |  | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/MX71436.pdf | 1904928 | 5.98
Voltage Regulator (MIC39300-2.5WU) | 331 | 33.1 | 364.1 |  | 1 | 364.1 |  | Completed | 160 | 410 | 410 |  | 45.9 | $2.22 | 1165 |  | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/mic39300.pdf | 2025637 | 2.8415
NV-Memory (ST M25P-AVMN6P) | 331 | 33.1 | 364.1 |  | 1 | 364.1 |  | Completed | 0 | 364 | 364 |  | -0.1 | 1.15 | 650 |  |  | 2025559 | 1.7857
RF Choke (B82412A1102K) | 662 | 66.2 | 728.2 | 14.564 | 2 | 742.764 |  | Completed |  | 800 | 800 |  | 57.236 | 0.9 | 677 |  |  | 2011788 | 1.6925
E-2000 Adapter Compact APC Front Panel | 662 | 66.2 | 728.2 |  | 2 | 730 |  | Ordered |  | 730 |  |  | -730 | 20.6 | 15038 |  |  | 2048849 | 41.2
Fixing clip for FP special 2.5mm thickness | 1324 | 132.4 | 1456.4 |  | 4 | 1460 |  | Ordered |  | 1460 |  |  | -1460 | 0.45 | 657 |  |  | 2048849 | 1.8
Reset Button (B3F-3100 OMRON) | 331 | 33.1 | 364.1 |  | 1 | 364.1 |  |  |  | 400 |  |  | -364.1 | 1.17 | 468 |  |  |  | 1.17
Connector standard 10 pins 2.54mm | 662 | 66 | 728 | 2 | 2 | 730 | [6 empty] | -730
JTAG Connector for PCB mounting | 662 | 66.2 | 728.2 |  | 2 | 728.2 | [6 empty] | -728.2
Connector Front-panel 26pin SCSI | 331 | 33.1 | 364.1 |  | 1 | 364.1 | [6 empty] | -364.1 | 9 | 3276.9
Male Connector Frondpanel | 20 | 0 | 20 |  |  | 20 | [6 empty] | -20
Standard Components
50V SMD Ceramic Capacitor 10nF | 5296 | 529.6 | 5825.6 | 116.512 | 16 | 5942.112 | [6 empty] | -5942.112
25V 10% SMD Ceramic Capacitor 100nF | 12909 | 1290.9 | 14199.9 | 283.998 | 39 | 14483.898 | [6 empty] | -14483.898 |  |  |  | FARNELL (VITRAMON), 894-904, C0805
35V SMD Tantalum Electrolytic Capacitor 100uF | 662 | 66.2 | 728.2 | 14.564 | 2 | 742.764 | [6 empty] | -742.764 |  |  |  | SIEMENS, Type B
1/8W 5% SMD Resistor 200 | 3972 | 397.2 | 4369.2 | 87.384 | 12 | 4456.584 | [6 empty] | -4456.584 |  |  |  | R0805
1/8W 5% SMD Resistor 10K | 1655 | 165.5 | 1820.5 | 36.41 | 5 | 1856.91 | [6 empty] | -1856.91 |  |  |  | R0805
1/8W 5% SMD Resistor 51 | 5296 | 529.6 | 5825.6 | 116.512 | 16 | 5942.112 | [6 empty] | -5942.112 |  |  |  | R0805
1/8W 5% SMD Resistor 820 | 1324 | 132.4 | 1456.4 | 29.128 | 4 | 1485.528 | [6 empty] | -1485.528 |  |  |  | R0805
1/8W 5% SMD Resistor 100K | 331 | 33.1 | 364.1 | 7.282 | 1 | 371.382 | [6 empty] | -371.382 |  |  |  | R0805
SMD Jumper | 3310 | 331 | 3641 | 72.82 | 10 | 3713.82 | [6 empty] | -3713.82 |  |  |  | R0805
|  |  | Components per Card |  | 132 | [6 empty] | Price per Card |  |  | 393.7373 |  |  |  | 334.2063
COM | 30
Total |  |  | 574048.2 | 29363.849 |  | 606927.64 |  |  |  | 193814 |  |  |  | 1015.579 | 1186003.5368
Note on A104: czam: Price increase (from BPM's DAB64x) FPGA: SFr. 432.32/card <---- (212,134 SFr / 360 pcs - 188,328 SFr / 1200 pcs) SRAM: SFr. 9.75/card <---- 3 * (9,034 SFr / 1122 pcs - 19,008 SFr / 3960 pcs) FPanel: E-2000: Total:
Note on A115: czam: will be changed with a similar one.
Note on A118: czam: probably need to change this to MIC39301-2.5WU (5 pins w/ enable)
Note on A123: czam: BUTTON B3F-3100 OMRON SFr. 1.17 Best.-Nr.: 959704 Hersteller: OMRON Herstellerbez.: B3F-3100 Produktdetails PCB DUAL-IN-LINE-DRUCKTASTER; RoHS -konform:JA; Schaltfunktionstyp:SPNO; Spannung, Kontakt max. DC:24V; Temperatur, Betriebs- max.:70°C; Temperatur, Betriebs- min.:-25°C; Länge/Höhe, Außen-:7.4mm; Breite/Weite:7.3mm; Tiefe, Aussen:7.15mm; Haltbarkeit, elektrisch:10000000; Haltbarkeit, mechanisch:10000000; Spannungsfestigkeit, VDC:500V; Strom, Kontakt bei Kontaktspannung, DC, max.:50mA; Strom, Last, min.:1mA; Widerstand, Isolations-:100MR; Widerstand, Kontakt-:100mR
Note on A126: czam: new: FARNELL Part ID: 854025 Price: €9.39 FICHE FEMELLE SCSI 26 VOIES; Nombre de voies:26 ---------------------------------------------------------------- old: Code Commande : 965637 Fabricant HARTING Ref. Fabricant : 6011 026 5140 Description : SUB-D FEMELLE IEEE1284-C 26P http://www.farnell.com/datasheets/41215.pdf http://www.farnell.com/datasheets/21667.pdf
Note on A127: czam: not necessary for production FARNELL Part ID: 487703 Price: €5.18 FICHE SCSI-2 26 VOIES; Conforme RoHS:NON; Nombre de voies:26; Approuvé:EIA RS232, IPI, HIPPI, SCSI-2; Diamctre, câble max.:0.91mm; Diamctre, câble min.:0.74mm; Inflammabilité:UL94V-0; Maticre:Plastique noir; Maticre, con
Note on D149: czam: Total Number of components needed
Note on E98: czam: Production Loss = 8%
Note on E107: czam: production loss: 2%
Note on E114: czam: production loss: 2%
Note on E115: czam: production loss: 2%
Note on E117: czam: production loss: 2%
Note on E120: czam: production loss: 2%
Note on G149: czam: Total Number of components to be ordered
Note on I108: czam: Joint order with the BPM by Jose
Note on I110: czam: Requested 10/11/2005 by Diamond SA
Note on I111: czam: requested 10/11/2005 by Diamond SA
Note on K99: effinger: original 1505 ordered new TID for 75 pcs launched at 31.10.05
Note on K100: dehning: first order 1460 second 120, out 22.09.05
Note on K106: czam: 17 Packages of 66 pcs
Note on L100: dehning: first 1410 second 170
Note on O100: dehning: ST price
Note on O105: czam: ordered 24.05.05 Price given by EBV unit price $483 Total price $173,880
Note on O106: czam: ordered 31.03.05 unit price $6.60 Total price $7,405.20 MSC SUISSE SA, Avenue Nestle 14, 1820 MONTREUX (MSC-02, MA01)
Note on O107: czam: ordered 22.06.05 EME AG , Lohwisstrasse, 50, 8123 EBMATINGEN (EMEG50, MA01)
Note on O114: czam: Price for one piece. Offer has NOT been requested.
Note on O115: dehning: aproximate price 53 br. Pounds
Note on O116: czam: ordered: 23.11.2005 SPOERLE ELECTRONIC DISTRIBUTION INTERNATIONAL, Case Postale, 1442 MONTAGNY (SPOE01, MA01)
Note on O117: czam: ordered 22.06.05 EME AG , Lohwisstrasse, 50, 8123 EBMATINGEN (EMEG50, MA01)
Note on O118: czam: PRICE FROM ELECTRONITEL SA, C.P. 142, 1752 VILLARS-SUR-GLANE 1 (ELEC10, MA01)
Note on O120: czam: price from FARNELL Zurich 6% deduction not calculated.
Note on O123: czam: Price Farnell Suisse expected to change
Note on O126: czam: price from Farnell Final expected to change http://fr.farnell.com/jsp/endecaSearch/partDetail.jsp?SKU=965637&N=0
Note on P105: dehning: dollar 1.22 (24.05.05)
Note on P114: czam: Unit : €7.00 Total €10,080.00 10,080 * 1.554 = 15664.32
Note on P115: czam: Final Price
Note on P119: czam: €418.60 * 1.554 = 650
Note on P120: czam: https://edh.cern.ch/Document/DAI/2011788 ordered: 03/11/2005 FARNELL ZH
Note on P140: czam: relative price (calculated including spare parts)
Note on U140: czam: Accurate price for components in one card

## CFC EDA-00593-V3
C.F.C EDA-00593-V3
Nom du client: GF.Ferioli / E.Effinger
Date: 4/05/2005 | [8 empty] | 1.58
Materiel non standart
QTY | SCEM / Art. No. |  |  | Valeur | Remarques | Prix (EURO) | Prix (CH) PC | Prix par unité | QTY for 10 | QYT 750 | total price
1 | N.S | Cablage |  |  |  | 1.58 | 100 | 100 | 10 | 750 | 75000
1 | N:S | Circuit imprimé |  |  |  |  | 80 | 80 | 10 | 750 | 60000
2 | N.S | GOH |  |  |  |  | 200 | 400 | 20 | 1500 | 300000
1 | Radiospares 121-2118 | EMI-RFI Box 75*50*25mm |  | PFL3 | Box1 | 9.13 | 14.4254 | 14.4254 | 10 | 750 | 10819.05 |  | n.c.
1 | APW 951-263903D | Case |  |  | price for more than 500pcs | 22.52 | 35.5816 | 35.5816 | 10 | 750 | 26686.2
1 | DIPTRONICS | SMT Push Button | SW4PSMD_DTSL6 | DTSL-61R-B | PB1 |  |  |  | 10 | 750 | 0
9 | Radiospares 262-4759 | 10V SMD Tantalum Electrolytic Capacitor | SMD | 100uF 10V | C1->C4,C10,C44,C87->C89 | 2.032 | 3.2106 | 28.895 | 90 | 6750 | 21671.28
48 | FARNELL 301-9482 | 16V SMD Ceramic Capacitor; 2238 787 19849 PHYCOMP | SMD 0402 | 100nF | C220->C243,C250->C273 |  | 0.069 | 3.312 | 480 | 36000 | 2484
49 | Radiospares 367-3279 | 10V SMD Ceramic Capacitor | SMD 1206 | 10uF | C45,C47,C49,C53,C119,C122->C123,C126->C127,C130->C131,C134,C139,C142,C145,C148,C182,C185,C188,C191,C194,C197,C207,C209->C210,C213,C215->C216,C218->C219,C244->C249,C275,C277,C279,C281,C284,C286,C290->C291,C293,C299,C302,C308,C311 |  | 0.564 | 27.636 | 490 | 36750 | 20727
121 |  | 25V 10% SMD Ceramic Capacitor | SMD 0805 | 100nF | C5->C9,C46,C48,C50,C52,C54,C90->C118,C120->C121,C124->C125,C128->C129,C132->C133,C135->C138,C140->C141,C143->C144,C146->C147,C162->C165,C167->C170,C172->C175,C177->C181,C183->C184,C186->C187,C189->C190,C192->C193,C195->C196,C198->C206,C208,C211->C212,C214,C217,C274,C276,C278,C280,C282->C283,C285,C288,C292,C295->C298,C300->C301,C303->C307,C309->C310,C312 |  |  | 0 | 1210 | 90750 | 0
2 |  | 50V SMD Multilayer Chip Ceramic Capacitor | SMD 0805 | 100pF | C51,C287 |  | 0 | 0 | 20 | 1500 | 0
2 | NAIS A.C.G. AXN350038S | SM50 Contact Narrow-pitch NAIS AXN350038S |  | AXN350038S | J1->J2 |  | 5 | 10 | 20 | 1500 | 7500
8 |  | Dual Series Rectifier Diode | SOT23 | BAV99LT1 | D2,D4 D6,D8 D10,D12 D14,D16 | 0.02 | 0.0316 | 0.2528 | 80 | 6000 | 189.6
25 | Spoerle No. 110542 | Low-leakage Double Diode | SOT23 | BAV199W | D1,D3 D5,D7 D9,D11 D13,D15 D17->D33 | 0.039 | 0.06162 | 1.5405 | 250 | 18750 | 1155.375
8 | Radiospares 318-1297 | Dual General Purpose, Low Voltage, TinyPack Comparator | SO08 | LMV393M | IC12->IC15 IC20,IC25 IC30,IC35 | 0.7 | 1.106 | 8.848 | 80 | 6000 | 6636
1 | A54SX72A2PQ208I | SX-A FPGA | PQ208 | 54SX72A | IC1 | 62$ | 75.64 | 75.64 | 10 | 750 | 56730
6 | CERN CHIPIDEA LVDS_RX | LVDS driver | LPCC32_050 | LVDS_RX | IC4->IC9 |  | 10 | 60 | 60 | 4500 | 45000
1 | Spoerle AD5346BRU | 2.5V to 5.5V Parallel Interface Octal Voltage Output 8 Bit DACs | TSSOP-38 | AD5346 | IC2 | 7.41 | 11.7078 | 11.7078 | 10 | 750 | 8780.85
2 | CERN CHIPIDEA AD41240_V2 | A quad 12 bit-40 Ms/s 450 mW CMOS A/D Converter | BGA144M12_100 | AD41240_V2 | IC10->IC11 | 8.85 | 18.75 | 37.5 | 20 | 1500 | 28125
3 | Farnell 401134 | Voltage-Feedback Operational Amplifier | SOIC8 | TL072CD | IC3 IC16->IC17 | 0.49 | 0.7742 | 2.3226 | 30 | 2250 | 1741.95
8 | Spoerle No. 442433 | Precision Voltage feedback operational amplifier | SO08 | OPA627AU | IC38->IC45 | 12.45 | 19.671 | 157.368 | 80 | 6000 | 118026
4 | Chipbrocker NE521D | High Speed Dual Differencial Comparator | SO14 | NE521DN | IC22,IC27,IC32,IC37 | 1.11 | 1.7538 | 7.0152 | 40 | 3000 | 5261.4
4 | Radiospares 436-7644 | Dual Retriggerable Monostable Multivibrator | SO14 | 74HCT123D | IC21,IC26,IC31,IC36 | 0.24 | 0.3792 | 1.5168 | 40 | 3000 | 1137.6
8 | Far. 8453276 or Spoerle ??? | High Speed Fully Differential I/O Amplifiers | SOIC8S_127 | THS4141CD | IC18->IC19,IC23->IC24,IC28->IC29,IC33->IC34 | 4.75 | 7.505 | 60.04 | 80 | 6000 | 45030
1 | Radiospares 471-4337 | Voltage source | so08 | LM4041-2.5V |  | 2.41 | 3.8078 | 3.8078 | 10 | 750 | 2855.85
8 | Farnell 3065297 | 1/4W 10% SMD Miniature Trimmer 11 Turns Cermet Sealed | SMD | 1K | P1,P3, P5, P7, P9, P11, P13, P15 | 1.84 | 2.9072 | 23.2576 | 80 | 6000 | 17443.2
8 | Farnell 3065297 | 1/4W 10% SMD Miniature Trimmer 11 Turns Cermet Sealed | SMD | 5K | P1,P3, P5, P7, P9, P11, P13, P15 | 1.84 | 2.9072 | 23.2576 | 80 | 6000 | 17443.2 |  | will be added in V4
1 | Spoerle 040929 | Quarz 40MHz | SMD | X357, CFPS-72B | QZ1 |  | 0.08 | 0.08 | 10 | 750 | 60
2 | Radiospares 191-2342 | EPCOS SMD-NTC resistor B57621C103K62 | SMD | 10k | R113, R134 | 0.474 | 0.74892 | 1.4978 | 20 | 1500 | 1123.38
16 | Dynatime SA | High ohmic resistor CHS 1206 10G 5 500 | SMD | 10G | R1->R8 |  | 2.08 | 33.28 | 160 | 12000 | 24960 |  | 8 pcs more will be added in V4
16 | Spoerle 132075 | P-Channel JFET | SOT23 | SST176 | IC46->IC59 T13->T14 | 0.2 | 0.316 | 5.056 | 160 | 12000 | 3792
Materiel standart
1 | 10.03.04.500.2 | 50V SMD Ceramic Capacitor | SMD | 100nF | C11 |  | 0.02 | 0.02 | 10 | 750 | 15 | 1
8 | 10.03.04.400.5 | 50V SMD Ceramic Capacitor | SMD | 10nF | C150->C151,C153->C154,C156->C157,C159->C160 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 2
26 | 10.03.04.100.4 | 50V SMD Ceramic Capacitor | SMD | 10pF | C20->C43,C289,C294 |  | 0.02 | 0.52 | 260 | 19500 | 390 | 3
8 | 10.03.04.133.5 | 50V SMD Ceramic Capacitor | SMD | 33pF | C56,C60,C64,C67,C72,C76,C80,C84 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 4
24 | 10.03.04.200.1 | 50V SMD Ceramic Capacitor | SMD | 100pF | C12->C19,C55,C59,C63,C68,C71,C75,C79,C83,C149,C152,C155,C158,C161,C166,C171,C176 |  | 0.03 | 0.72 | 240 | 18000 | 540 | 5
8 | 10.03.04.247.6 | 50V SMD Ceramic Capacitor | SMD | 470pF | C57,C61,C65,C69,C73,C77,C81,C85 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 6
8 | 10.03.04.347.3 | 50V SMD Ceramic Capacitor | SMD | 4.7nF | C58,C62,C66,C70,C74,C78,C82,C86 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 7
1 | 09.61.33.215.0 | 96 Pins Right Angle PCB Connector |  | DIN 41612-TYPE C | J3 |  | 1.7 | 1.7 | 10 | 750 | 1275 | 8
6 | 11.24.05.200.9 | 1/4W 1% SMD Resistor | SMD | 100 | R11,R20,R25,R28,R230,R234 |  | 0.02 | 0.12 | 60 | 4500 | 90 | 9
8 | 11.24.05.400.3 | 1/4W 1% SMD Resistor | SMD | 10K | R110->R111,R121,R126,R130->R131,R136,R139 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 10
3 | 11.24.05.391.7 | 1/4W 1% SMD Resistor | SMD | 9.1K | R112,R132,R137 |  | 0.02 | 0.06 | 30 | 2250 | 45 | 11
18 |  | Specified On Test (S.O.T) SMD Resistor | SMD | oo | R164->R165,R169->R170,R174->R175,R179->R180,R184->R185,R189->R190,R194->R195,R199->R200 |  | 0 | 0 | 180 | 13500 | 0 | 12
1 | 11.24.05.333.7 | 1/4W 1% SMD Resistor | SMD | 3.3K | R115 |  | 0.02 | 0.02 | 10 | 750 | 15 | 13
1 | 11.24.05.316.8 | 1/4W 1% SMD Resistor | SMD | 1.6K | R116 |  | 0.02 | 0.02 | 10 | 750 | 15 | 14
25 | 11.24.05.151.1 | 1/4W 1% SMD Resistor | SMD | 51 | R12->R13,R21->R24,R26->R27,R30->R45,R158 |  | 0.02 | 0.5 | 250 | 18750 | 375 | 15
1 | 11.24.05.368.6 | 1/4W 1% SMD Resistor | SMD | 6.8K | R120 |  | 0.02 | 0.02 | 10 | 750 | 15 | 16
1 | 11.24.05.439.8 | 1/4W 1% SMD Resistor | SMD | 39K | R125 |  | 0.02 | 0.02 | 10 | 750 | 15 | 17
1 | 11.24.05.362.2 | 1/4W 1% SMD Resistor | SMD | 6.2K | R129 |  | 0.02 | 0.02 | 10 | 750 | 15 | 18
1 | 11.24.05.411.0 | 1/4W 1% SMD Resistor | SMD | 11K | R140 |  | 0.02 | 0.02 | 10 | 750 | 15 | 19
1 | 11.24.05.327.5 | 1/4W 1% SMD Resistor | SMD | 2.7K | R143 |  | 0.02 | 0.02 | 10 | 750 | 15 | 20
1 | 11.24.05.324.8 | 1/4W 1% SMD Resistor | SMD | 2.4K | R144 |  | 0.02 | 0.02 | 10 | 750 | 15 | 21
5 | 11.24.05.000.5 | SMD Jumper | SMD | 00 | R146,R225->R226,R233,R236 |  | 0.02 | 0.1 | 50 | 3750 | 75 | 22
1 | 11.24.05.336.4 | 1/4W 1% SMD Resistor | SMD | 3.6K | R147 |  | 0.02 | 0.02 | 10 | 750 | 15 | 23
2 | 11.24.05.422.7 | 1/4W 1% SMD Resistor | SMD | 22K | R148,R232 |  | 0.02 | 0.04 | 20 | 1500 | 30 | 24
2 | 11.24.05.224.1 | 1/4W 1% SMD Resistor | SMD | 240 | R150,R153 |  | 0.02 | 0.04 | 20 | 1500 | 30 | 25
1 | 11.24.05.312.2 | 1/4W 1% SMD Resistor | SMD | 1.2K | R159 |  | 0.02 | 0.02 | 10 | 750 | 15 | 26
1 | 11.24.05.320.2 | 1/4W 1% SMD Resistor | SMD | 2K | R160 |  | 0.02 | 0.02 | 10 | 750 | 15 | 27
8 | 11.24.05.239.4 | 1/4W 1% SMD Resistor | SMD | 390 | R163,R168,R173,R178,R183,R188,R193,R198 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 28
8 | 11.24.05.322.0 | 1/4W 1% SMD Resistor | SMD | 2.2K | R166,R171,R176,R181,R186,R191,R196,R201 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 29
1 | 11.24.05.315.9 | 1/4W 1% SMD Resistor | SMD | 1.5K | R235 |  | 0.02 | 0.02 | 10 | 750 | 15 | 30
2 | 11.24.05.412.9 | 1/4W 1% SMD Resistor | SMD | 12K | R29,R219 |  | 0.02 | 0.04 | 20 | 1500 | 30 | 31
49 | 11.24.05.247.4 | 1/4W 1% SMD Resistor | SMD | 470 | R46,R47,R52,R54,R55,R60,R62,R63,R68,R70,R71,R76,R78,R79,R84,R86,R87,R92,R94,R95,R100,R102,R103,R108,R133,R167,R172,R177,R182,R187,R192,R197,R202,R218 |  | 0.02 | 0.98 | 490 | 36750 | 735 | 32
16 | 11.24.05.351.5 | 1/4W 1% SMD Resistor | SMD | 5.1K | R48,R56,R64,R72,R80,R88,R96,R104,R114,R118,R122,R123,R124,R128,R138,R142 |  | 0.02 | 0.32 | 160 | 12000 | 240 | 33
8 | 11.24.05.356.0 | 1/4W 1% SMD Resistor | SMD | 5.6K | R50,R59,R66,R75,R82,R91,R98,R107 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 34
8 | 11.24.05.500.0 | 1/4W 1% SMD Resistor | SMD | 100K | R53,R61,R69,R77,R85,R93,R101,R109 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 35
48 | 11.24.05.300.6 | 1/4W 1% SMD Resistor | SMD | 1K | R9,R10,R14->R19,R49,R51,R57,R58,R65,R67,R73,R74,R81,R83,R89,R90,R97,R99,R105,R106,R117,R119,R127,R135,R141,R145,R149,R151,R152,R154->R157,R161,R162,R220->R224,R227->R229,R231 |  | 0.02 | 0.96 | 480 | 36000 | 720 | 36
1 |  | SMD Selection Jumper R0805 | SMD | 00 | ST1 |  | 0 | 0 | 10 | 750 | 0 | 37
6 |  | SMD Stand-Alone Pin for Probe Test Pin | SMD |  | ST2->ST7 |  | 0 | 0 | 60 | 4500 | 0 | 38
20 |  | Standalone Pin for Test Probe |  | Mounted | TP1->TP20 |  | 0 | 0 | 200 | 15000 | 0 | 39
2 | 47.62.59.257.0 | Vis 2,5X10 |  |  | montage connecteur |  | 0.01 | 0.02 | 20 | 1500 | 15 | 40
2 | 47.41.65.025.5 | Ecrou M2,5 |  |  | montage connecteur |  | 0.01 | 0.02 | 20 | 1500 | 15 | 41
711 | [7 empty] | 1221.6786 | 7110 | 533250 | 916258.935

## BLM Mezzanine EDA-00780-V2
EDA-00780-V2
BLM Mezzanine Liste de matériel / Material List
| Client/Customer: |  | C. Zamantzas |  |  | Through pins: 22
| DATE: |  | 2005-05-24 |  |  | SMD pins on TOP: 398
| Dessinateur/Drawer: |  | Jean-Marc Combe |  |  | SMD pins on BOTTOM: 227
| TS/DEM/BE |  | Board dimensions: 146x100mm |  |  | Total nb of pins: 647
Ref. | Qty | SCEM | Description | Value | Fournisseur/Supplier |  | Boitier/Outline
Matériel monté sur le PCB / Parts mounted on the PCB
C1->C2 C4 C6->C7 C9 C13->C14 C16 C18->C19 C21 C33->C34 C42->C43 | 16 |  | 50V SMD Ceramic Capacitor | 10nF |  |  | C0805
C3,C5 C8 C10->C12 C15,C17 C20 C22->C29 C31 C35->C41 C44->C57 | 39 |  | 25V 10% SMD Ceramic Capacitor | 100nF | FARNELL (VITRAMON) | 894-904 | C0805
C30,C32 | 2 |  | 35V SMD Tantalum Electrolytic Capacitor | 100uF | SIEMENS |  | Type B
IC1->IC4 | 4 |  | 1.6 To 1.5 GBPS Transceiver |  | TEXAS INSTRUMENTS | TLK1501IRCP | PQFP64_050
IC5 | 1 |  | 1Mbit Serial Flash Memory |  | ST | M25P10 | SOIC8S_127
J1->J2 | 2 | 09.55.40.064.7 | 1.0mm FH (IEEE 1386) Mezzanine SMD Connector 10mm stacking |  | AMP | 120527-1
J3->J6 | 4 |  | 1.25 Gbps InGaAs PIN/TIA Receiver |  | AFONICS | TXP0036
J7 | 1 |  | DA1 Series 10 Contacts PCB to Cable Connector |  | JAE | DA1R010H91
L1->L2 | 2 |  | RF Choke | 1uH | Siemens | B82412 | SelfB82412
QZ1 | 1 |  | Quartz 40MHz | 40MHz | C-MAC | CFPS72
R1,R9 R11,R18 R21 R27->R30 R39 | 10 |  | SMD Jumper | 00 |  |  | R0805
R2,R8 R10,R12 R19->R20 R31 R37->R38 R40 R46->R47 | 12 |  | 1/8W 5% SMD Resistor | 200 | BOURNS | CR 0805-FX | R0805
R22->R26 | 5 |  | 1/8W 5% SMD Resistor | 10K | BOURNS | CR 0805-FX | R0805
R3 R5->R7 R13 R15->R17 R32 R34->R36 R41 R43->R45 | 16 |  | 1/8W 5% SMD Resistor | 51 | BOURNS | CR 0805-FX | R0805
R4,R14 R33,R42 | 4 |  | 1/8W 5% SMD Resistor | 820 | BOURNS | CR 0805-FX | R0805
R48 | 1 |  | 1/8W 5% SMD Resistor | 100K | BOURNS | CR 0805-FX | R0805
RG1 | 1 |  | 3A Low-VoLtage Low-Dropout Regulator |  | MICREL | MIC39300-2.5BU | TO263