## BLM System
Sub-System | needed for installation | spare (10%) | total needed quantity | production loss | pieces per card | to be ordered | lost units while tests | Status | in stock | ordred | delivered | checked by | quantity difference | Unit Price | Total Price [CHF] | delivery schedule | comments | DAI |  | Price/Card
|  | 0.1 |  | 0.055 |  | 749.683
CFC | 646 | 64.6 | 710.6 | 39.083 |  | 750 | [9 empty] | F82/Mar90/May73/Jul68/Au80/O86Dec163
PCB and Assembly
Printed Circuit V6 | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | in progress | 0 | 0 | 0 |  | -750 | 54.8 | 41100 |  | https://edms.cern.ch/file/446068/6/EDA-00593-V6_mfg.pdf
Assembly PCB | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | DO 24132 | 0 | 0 | 0 |  | -750 | 55.38 | 41535 |  | https://edms.cern.ch/file/446069/6/EDA-00593-V6
Assembly PCB into case | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  |  | 0 | 0 | 0 |  | -1500 | 0 | 0
Case and mounting kit
APW 951-263903D (case) | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Ordered | 0 | 750 | 0 |  | -750 | 34.07 | 25552.5 |  | http://www.apw.com/raptor/pdf/pdf1-846.pdf
Card mount bracket | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1500 | 1500 | 1500 | Ew | 0 | 1.525 | 2287.5
Flat Alloy Bar | 62.016 | 6.2016 | 68m |  | 0.096 | 75 m |  | Complete | 75m | 75m | 75m | Ew | 0 | 0.907 | 68.025
Mechanical treatment alloy bar | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 750 | 750 | 750 | Ew | 0 | 3.426 | 2569.5 |  | https://edms.cern.ch/file/446070/2/EDA-00593-V2_misc1.pdf
Cyl. Screw M2.5*12mm | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1600 | 1600 | 1600 | Ew | 100 | 0.01 | 15
Pl. Washer M2.5 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1600 | 1600 | 1600 | Ew | 100 | 0.01 | 15
Bronze fan Washer M2.5 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1600 | 1600 | 1600 | Ew | 100 | 0.12 | 180
0
Optical connection material | [5 empty] | 0
E-2000 Adapter for Front panel | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1500 | 1500 | 1500 | Jo | 0 | 9.1 | 13650 |  | http://www.diamond-fo.com/media/products/datenblatt/E-2000_Simplex_d.pdf
Screw fixing clip E-2000 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1500 | 1500 | 1500 | Jo | 0 | 0.4 | 600
M2*6mm Pozidriv flat head screw | 2584 | 258.4 | 2842.4 | 156.332 | 4 | 3000 |  | Complete | 3000 | 3000 | 3000 | Ew | 0 | 0.0432 | 129.6
GOH | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Ordered | 0 | 1580 | 0 |  | -1500 | 257.12 | 385680
no standard material
100uF 10V 35V SMD | 5814 | 581.4 | 6395.4 | 351.747 | 9 | 6750 |  | Complete | 7000 | 7000 | 7000 | Ew | 250 | 0.27986 | 1889.0357 |  | http://www.kemet.com/kemet/web/homepage/kechome.nsf/vapubfilesname/F3102T495.pdf/$file/F3102T495.pdf
10uF SMD 1206 | 34238 | 3423.8 | 37661.8 | 2071.399 | 53 | 39750 |  | Ordered | 40000 | 40000 | 40000 | Ew | 250 | 0.091737 | 3646.5395 |  | http://www.murata.com/catalog/c02e11.pdf#page=14
100pF C0805 | 1938 | 193.8 | 2131.8 | 117.249 | 3 | 2250 |  | Complete | 4000 | 4000 | 4000 | Ew | 1750 | 2.4 | 5400
100nF SMD 0402 | 31008 | 3100.8 | 34108.8 | 1875.984 | 48 | 36000 |  | Complete | 40000 | 40000 | 40000 | Ew | 4000 | 0.006232 | 224.352 |  | http://www.farnell.com/datasheets/57604.pdf
100pF C1206 | 15504 | 1550.4 | 17054.4 | 937.992 | 24 | 18000 |  | Ordered | 20000 | 20000 | 20000 |  | 2000 | 3.4 | 61200
10pF C1206 | 16796 | 1679.6 | 18475.6 | 1016.158 | 26 | 19500 |  | Ordered | 20000 | 20000 | 20000 |  | 500 | 4.4 | 85800
100nF SMD 0805 | 82042 | 8204.2 | 90246.2 | 4963.541 | 127 | 95250 |  | Ordered | 96000 | 96000 | 96000 |  | 750 | 0.006232 | 593.598
470pF C1206 | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Ordered | 8000 | 8000 | 8000 |  | 2000 | 6.4 | 38400
4.7nF C1206 (2kV) | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Ordered | 0 | 8000 | 0 |  | -6000 | 0.293 | 1758
0.01uF C1206 | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete | 8000 | 8000 | 8000 | Ew | 2000 | 1.4 | 8400
BAV199 | 16796 | 1679.6 | 18475.6 | 1016.158 | 26 | 19500 |  | Complete | 21000 | 21000 | 21000 | Ew | 1500 | 0.043624 | 850.668 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/BAV199_4.pdf
BAV99LT1 | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete | 6000 | 6000 | 6000 | Ew | 0 | 0.011685 | 70.11 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/BAV99_4.pdf
A54SX72A2PQ208I | 646 | 64.6 | 710.6 | 39.083 | 1 | 768 |  | Complete | 768 | 768 | 768 |  | 0 | 75.64 | 58091.52 |  | http://www.actel.com/documents/SXA_DS.pdf
CERN CHIPIDEA ADC AD41240 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1550 | 1550 | 1550 | Ew | 50 | 18.75 | 28125 |  | http://proj-kchip.web.cern.ch/proj-Kchip/preshower/doc/AD41240%20Manual%20v0.2.pdf
LMV393M | 5814 | 581.4 | 6395.4 | 351.747 | 9 | 6750 |  | Complete | 6805 | 6805 | 6805 | Ew | 55 | 0.49493 | 3340.7788 |  | http://cache.national.com/ds/LM/LMV331.pdf
LM4140-2.5V | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 750 | 750 | 750 | Ew | 0 | 2.644 | 1983 |  | http://cache.national.com/ds/LM/LM4140.pdf
AD5346 | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 750 | 750 | 750 | Ew | 0 | 5.116 | 3837 |  | http://www.analog.com/UploadedFiles/Data_Sheets/4283875071479AD5346_7_8_0.pdf
THS4141CD | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete | 6050 | 6000 | 6050 | Ew | 50 | 4.27 | 25620 |  | http://focus.ti.com/lit/ds/symlink/ths4141.pdf
74HCT123D | 2584 | 258.4 | 2842.4 | 156.332 | 4 | 3000 |  | Complete | 3000 | 3000 | 3000 | Ew | 0 | 0.10906 | 327.18 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/74HC_HCT123_3.pdf
NE521DN | 2584 | 258.4 | 2842.4 | 156.332 | 4 | 3000 |  | Complete | 3000 | 3000 | 3000 | Ew | 0 | 2.8044 | 8413.2 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/NE521_2.pdf
TL072CD | 2584 | 258.4 | 2842.4 | 156.332 | 4 | 3000 |  | Ordered | 3025 | 3025 | 3025 |  | 25 | 0.0976 | 292.8 |  | http://focus.ti.com/lit/ds/symlink/tl072.pdf
CERN CHIPIDEA LVDS CRT910 | 3876 | 387.6 | 4263.6 | 234.498 | 6 | 4500 |  | Complete | 4650 | 4650 | 4650 | Ew | 150 | 5.5 | 24750
OPA627AU / OPA637AU | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete | 6000 | 6000 | 6000 | Ew | 0 | 19.67 | 118020 |  | http://focus.ti.com/lit/ds/symlink/opa627.pdf
AXN350038S (GOH connector) | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1500 | 1500 | 1500 | Ew | 0 | 5 | 7500 |  | http://www.naisweb.com/e/connecte/con_eng/pdf/con_eng_np3.pdf
1/4W 10% SMD Trimmer 11 Turns 1k | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete | 6000 | 6000 | 6000 | Ew | 0 | 1.5285 | 9171 |  | http://www.vishay.com/docs/51009/tsm4.pdf
1/4W 10% SMD Trimmer 11 Turns 5k | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete | 6000 | 6000 | 6000 | Ew | 0 | 1.5285 | 9171 |  | http://www.vishay.com/docs/51009/tsm4.pdf
X357, CFPS-72B (40MHz) | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 750 | 750 | 750 | Ew | 0 | 1.244 | 933 |  | http://www.cmac.com/mt/databook/oscillators/semtech/cfps-72.pdf
High ohmic resistor CHS 1206 10G 5 500 | 10336 | 1033.6 | 11369.6 | 625.328 | 16 | 12000 |  | Complete | 12000 | 10100 | 12000 | Ew | 0 | 2.08 | 24960 |  | http://www.willow.co.uk/CHS.pdf
EPCOS SMD-NTC resistor B57621C103K62 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1500 | 1500 | 1500 | Ew | 0 | 0.38867 | 583 |  | http://www.epcos.com/inf/50/db/ntc_02/00600061.pdf
150k 0.1% High Chip Resistors | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Ordered | 0 | 5000 | 0 |  | -1500 | 0.3426 | 513.9 | 27.4.06 | http://www.vishay.com/docs/20028/m101112.pdf
15k 0.1% High Chip Resistors | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Ordered | 0 | 5000 | 0 |  | -750 | 0.3426 | 256.95 | 16.2.06 | http://www.vishay.com/docs/20028/m101112.pdf
220k 0.1% High Chip Resistors | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Ordered | 0 | 5000 | 0 |  | -1500 | 0.4827 | 724.05 |  | http://www.vishay.com/docs/20028/m101112.pdf
300k 0.1% High Chip Resistors | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Ordered | 0 | 5000 | 0 |  | -750 | 0.4983 | 373.725 |  | http://www.vishay.com/docs/20028/m101112.pdf
120k 0.1% High Chip Resistors | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Ordered | 0 | 5000 | 0 |  | -750 | 0.3426 | 256.95 | latest | http://www.vishay.com/docs/20028/m101112.pdf
47k 0.1% High Chip Resistors | 1938 | 193.8 | 2131.8 | 117.249 | 3 | 2250 |  | Ordered | 0 | 5000 | 0 |  | -2250 | 0.3426 | 770.85 | 8-10 weeks | http://www.vishay.com/docs/20028/m101112.pdf
SST176 | 10336 | 1033.6 | 11369.6 | 625.328 | 16 | 12000 |  | Ordered | 3000 | 12000 | 3000 |  | -9000 | 0.20215 | 2425.8462 | week 12 | http://www.vishay.com/docs/70257/70257.pdf
BZX84-B2V7 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 3000 | 3000 | 3000 | Ew | 1500 | 1.0436 | 1565.436
standard material
100nF 50V C1206 | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Ordered | 4000 | 4000 | 4000 |  | 3250 | 0.02 | 15 |  | 10.03.04.500.2
33pF 50V C1206 | 5814 | 581.4 | 6395.4 | 351.747 | 9 | 6750 |  | Complete | 8000 | 8000 | 8000 | Ew | 1250 | 0.02 | 135 |  | 10.03.04.133.5
DIN 41612-TYPE C | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 750 | 750 | 750 | Ew | 0 | 1.7 | 1275 |  | 09.61.33.215.0
470 | 15504 | 1550.4 | 17054.4 | 937.992 | 24 | 18000 |  | Ordered | 18000 | 18000 | 18000 |  | 0 | 0.01 | 180 |  | 11.24.05.247.4
5.6K | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete | 10000 | 10000 | 10000 | Ew | 4000 | 0.01 | 60 |  | 11.24.05.356.0
51 | 7106 | 710.6 | 7816.6 | 429.913 | 11 | 8250 |  | Complete | 10000 | 10000 | 10000 | Ew | 1750 | 0.01 | 82.5 |  | 11.24.05.151.1
0 | 12274 | 1227.4 | 13501.4 | 742.577 | 19 | 14250 |  | Complete | 15000 | 15000 | 15000 | Ew | 750 | 0.01 | 142.5 |  | 11.24.05.000.5
1K | 12274 | 1227.4 | 13501.4 | 742.577 | 19 | 14250 |  | Complete | 15000 | 15000 | 15000 | Ew | 750 | 0.01 | 142.5 |  | 11.24.05.300.6
390 | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete | 10000 | 10000 | 10000 |  | 4000 | 0.01 | 60 |  | 11.24.05.239.4
470 Met. F. Resist 0.4W | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Ordered | 6000 | 6000 | 6000 |  | 0 | 0.04 | 240 |  | 11.22.10.347.8
2.2k Met. F. Resist 0.4W | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Ordered | 6000 | 6000 | 6000 |  | 0 | 0.04 | 240 |  | 11.22.10.422.4
1.5K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.315.9
1M | 2584 | 258.4 | 2842.4 | 156.332 | 4 | 3000 |  | Complete | 5000 | 5000 | 5000 | Ew | 2000 | 0.01 | 30 |  | 11.24.05.600.7
430 | 10336 | 1033.6 | 11369.6 | 625.328 | 16 | 12000 |  | Complete | 15000 | 15000 | 15000 |  | 3000 | 0.01 | 120 |  | 11.24.05.243.8
12K | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 5000 | 5000 | 5000 | Ew | 3500 | 0.01 | 15 |  | 11.24.05.412.9
5.1K | 12274 | 1227.4 | 13501.4 | 742.577 | 19 | 14250 |  | Complete | 15000 | 15000 | 15000 | Ew | 750 | 0.01 | 142.5 |  | 11.24.05.351.5
510k | 5814 | 581.4 | 6395.4 | 351.747 | 9 | 6750 |  | Complete | 15000 | 15000 | 15000 | Ew | 8250 | 0.01 | 67.5 |  | 11.24.05.551.9
100K | 12274 | 1227.4 | 13501.4 | 742.577 | 19 | 14250 |  | Ordered | 15000 | 15000 | 15000 |  | 750 | 0.0467 | 665.475 |  | Farnell 912712
10K | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 |  | Complete | 10000 | 10000 | 10000 | Ew | 4000 | 0.01 | 60 |  | 11.24.05.400.3
3k | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.330.0
130k | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.513.5
390k | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.539.5
22K | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 5000 | 5000 | 5000 | Ew | 3500 | 0.01 | 15 |  | 11.24.05.422.7
150k | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.515.3
470k | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.547.5
180k | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.518.0
4.7k | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.347.1
270k | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 4000 | 4000 | 4000 | Ew | 3250 | 0.01 | 7.5 |  | 11.24.05.527.9
240k | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 5000 | 5000 | 5000 | Ew | 3500 | 0.01 | 15 |  | 11.24.05.524.2
27k | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.427.2
160k | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.516.2
9.1K | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 5000 | 5000 | 5000 | Ew | 3500 | 0.01 | 15 |  | 11.24.05.391.7
51K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.451.2
200K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 5000 | 5000 | 5000 | Ew | 4250 | 0.01 | 7.5 |  | 11.24.05.520.6
3.3K | 10336 | 1033.6 | 11369.6 | 625.328 | 16 | 12000 |  | Complete | 15000 | 15000 | 15000 | Ew | 3000 | 0.01 | 120 |  | 11.24.05.333.7
0 Ohm (0805) | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 1000 | 1000 | 1000 | Ew | 250 | 0.01262 | 9.465 |  | Farnell 759788
Metallic Jumper for PCB | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 |  | Complete | 800 | 800 | 800 | Ew | 50 | 0 | 0 |  | 07.88.24.508.1
Solder terminal 2.3mm | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | Complete | 1500 | 1500 | 1500 | Ew | 0 | 0.18 | 270 |  | 07.88.24.350.5
|  |  | Components per Card |  | 717.096 | [6 empty] | Price per Card |  |  | 1410.4474
GOH | 1292 | 129.2 | 1421.2 | 113.696 |  | 1534.896 |  |  |  | 1580 |  |  | 45.104 |  |  |  | http://cms-tk-opto.web.cern.ch/cms-tk-opto/ecal/components/goh.html
no standard material
GOL (order) | 1292 | 129.2 | 1421.2 | 78.166 | 1 | 1525 |  | Completed | 1580 | 1580 | 1579 | Ew | 54 | 18.75 | 29625 |  | http://proj-gol.web.cern.ch/proj-gol/
LASER+E2000 APC | 1292 | 129.2 | 1421.2 | 78.166 | 1 | 1525 |  | Completed | 1580 | 1580 | 1580 | Cl | 55 | 134.5 | 212510 |  | http://cms-tk-opto.web.cern.ch/cms-tk-opto/tk/components/laserpill.html
CRT4T | 1292 | 129.2 | 1421.2 | 78.166 | 1 | 1525 |  | Completed | 1545 | 1580 | 1545 | Ew | 20 | 5.5 | 8690 | total mid feb 06
PCB and Assembly
GOH | 1292 | 129.2 | 1421.2 | 78.166 | 1 | 1525 |  | In progress | 0 | 1580 | 0 |  | -1525 | 98.37 | 155424.6 | J300/Mar400/May400/Julrest
[12 empty] | Price per Card |  |  | 257.12
TC | 331 | 33.1 | 364.1 | [13 empty] | EDA-00998
STRATIX EP1S40F780C7 | 331 | 33.1 | 364.1 |  | 1 | 364.1 |  | Completed |  | 360 |  |  | -364.1 | 483 | 212133.6 |  | http://altera.com/products/devices/stratix/stx-index.jsp
AS7C33512PFS32A-166TQC | 993 | 99.3 | 1092.3 |  | 3 | 1092.3 |  | Completed |  | 1122 |  |  | -1092.3 | 6.6 | 9034.344 |  | http://www.alsc.com/pdf/sram.pdf/fs/as7c331mpfs32a-36a_v2.3.pdf
PMC Connector (Socket: 71439-1164 (SMT 64WAY 11/12MM HIGH)) | 662 | 66.2 | 728.2 | 14.564 | 2 | 742.764 |  | Completed |  | 840 |  | Jose | -742.764 | 2.87 | 2410.8 |  | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/MX71439.pdf
Front Pannel / Handles(x2) / Fixation Bracket | 331 | 33.1 | 364.1 |  | 1 | 364.1 |  | Completed |  |  |  |  | -364.1
Front Pannel - Machining, Engraving & Assembly | 331 | 33.1 | 364.1 |  | 1 | 364.1 |  | Offer Requested |  |  |  |  | -364.1
0
TC mezzanine | 331 | 33.1 | 364.1 | [13 empty] | EDA-00780
no standard material
50V SMD Ceramic Capacitor 10nF C0805 | 5296 | 529.6 | 5825.6 | 116.512 | 16 | 5942.112 |  | Completed | 10000 | 8000 | 10000 |  | 4057.888 |  |  |  |  | 2115620
50V SMD Ceramic Capacitor 100nF C0805 | 12909 | 1290.9 | 14199.9 | 283.998 | 39 | 14483.898 |  | Completed | 16000 | 16000 | 16000 |  | 1516.102 |  |  |  |  | 2115620
100uF 10V 35V SMD | 662 | 66.2 | 728.2 | 14.564 | 2 | 742.764 |  | Completed | 1000 | 1000 | 1000 | Ch | 257.236 | 0.2 | 309 |  | SIEMENS, Type B | 2115775 |  | 0.618
TLK1501IRCP/R | 1324 | 132.4 | 1456.4 | 29.128 | 4 | 1485.528 |  | Completed | 1490 | 1490 | 1490 | Ew, Ch | 4.472 | 7 | 15664.32 | 2005-01-06 | http://focus.ti.com/docs/prod/folders/print/tlk1501.html | 2025559 | 2117030 | 42.0519
NV-Memory (ST M25P-AVMN6P) | 331 | 33.1 | 364.1 | 7.282 | 1 | 371.382 |  | Completed | 364 | 364 | 364 | Ew | -7.382 | 1.15 | 650 |  |  | 2025559 |  | 1.7857
PMC Connector (Header: 71436-2164 (SMT 64WAY 10MM HIGH)) | 662 | 66.2 | 728.2 | 14.564 | 2 | 742.764 |  | Completed | 760 | 760 | 760 | Ch | 17.236 | 2.99 | 2272.4 |  | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/MX71436.pdf | 1904928 |  | 5.98
Photodiodes (Neoptek NTPPT-3EPNH Pigtailed 1.25Gbps InGaAs PIN/TIA Receiver) | 1324 | 132.4 | 1456.4 | 29.128 | 4 | 1485.528 |  | Partly Completed | 900 | 1490 | 900 | Jo | -585.528 | 69.331 | 102993.1418 | Jan: 200, Mar: 700, Mai: rest | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/TXP0036.pdf |  |  | 276.4917
Connector Front-panel 26pin SCSI | 331 | 33.1 | 364.1 | 7.282 | 1 | 371.382 |  | Completed | 400 | 400 | 400 | Ch | 28.618 | 9.39 | 5852.61
JTAG Connector for PCB mounting | 662 | 66.2 | 728.2 | 14.564 | 2 | 742.764 |  |  | 0 | 800 | 0 |  | -742.764
RF Choke (B82412A1102K) | 662 | 66.2 | 728.2 | 14.564 | 2 | 742.764 |  | Completed | 800 | 800 | 800 | Ch | 57.236 | 0.9 | 677 |  |  | 2011788 |  | 1.6925
Reset Button (B3F-3100 OMRON) | 331 | 33.1 | 364.1 | 7.282 | 1 | 371.382 |  | Completed | 380 | 380 | 380 |  | 8.618 | 0.52 | 302.2 |  |  | 2117073 |  | 0.79526
Crystal Osc. (C-Mac 40.00 MHz IQXO-73B) | 331 | 33.1 | 364.1 | 7.282 | 1 | 371.382 |  | Completed | 400 | 400 | 400 | Ew | 28.618 | 0.8 | 498 |  | http://www.cmac.com/mt/databook/oscillators/smd/spxo/iqxo_70.html | 2028759 |  | 1.245
1/8W 5% SMD Resistor 0 | 3310 | 331 | 3641 | 72.82 | 10 | 3713.82 |  | Completed | 5000 | 5000 | 5000 |  | 1286.18 |  | 123 |  | 11.24.09.111.6 | 2117042 |  | 0.16869
1/8W 5% SMD Resistor 200 | 3972 | 397.2 | 4369.2 | 87.384 | 12 | 4456.584 |  | Completed | 5000 | 5000 | 5000 |  | 543.416 |  |  |  | R0805
1/8W 5% SMD Resistor 10K | 1655 | 165.5 | 1820.5 | 36.41 | 5 | 1856.91 |  | Completed | 5000 | 5000 | 5000 |  | 3143.09 |  |  |  | R0805
1/8W 5% SMD Resistor 51 | 5296 | 529.6 | 5825.6 | 116.512 | 16 | 5942.112 |  | Completed | 10000 | 10000 | 10000 |  | 4057.888 |  |  |  | R0805
1/8W 5% SMD Resistor 825 | 1324 | 132.4 | 1456.4 | 29.128 | 4 | 1485.528 |  | Completed | 5000 | 5000 | 5000 |  | 3514.472 |  |  |  | R0805
1/8W 5% SMD Resistor 100K | 331 | 33.1 | 364.1 | 7.282 | 1 | 371.382 |  | Completed | 5000 | 5000 | 5000 |  | 4628.618 |  |  |  | R0805
Voltage Regulator (MIC39301-2.5WU) | 331 | 33.1 | 364.1 | 7.282 | 1 | 371.382 |  | Completed | 450 | 450 | 450 | Ch | 78.618 | $ 2.59 | 1534 |  | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/mic39300.pdf | 2025637 |  | 3.4089
standard material
1/4W 10k smd 1206 | 331 | 33.1 | 364.1 | 7.282 | 1 | 371.382 |  | Completed | 5000 | 5000 | 5000 |  | 4628.618 |  | 50 |  | 11.24.05.400.3 | 2114830 |  | 0.01
Optical connection material
E-2000 Adapter Compact APC Front Panel | 662 | 66.2 | 728.2 |  | 2 | 730 |  | Completed | 730 | 730 | 730 | Jo | 0 | 20.6 | 15038 |  |  | 2048849 |  | 41.2
Fixing clip for FP special 2.5mm thickness | 1324 | 132.4 | 1456.4 |  | 4 | 1460 |  | Completed | 1500 | 1460 | 1500 | Jo | 40 | 0.45 | 657 |  |  | 2048849 |  | 1.8
Xtra parts
Male Connector Frondpanel (SCSI conector for prog. the memory) | 100 | 0 | 100 |  |  | 100 |  | Completed | 336 | 336 | 336 |  | 236 | 2.56 | 861 |  |  | 2096838 |  | 0
Spacers (entretoise) | 1324 | 132.4 | 1456.4 | 29.128 | 4 | 1485.528 |  | Ordered |  | 2000
|  |  | Components per Card |  | 135 | [6 empty] | Price per Card |  |  | 405.0581 |  |  |  |  | 377.2476
COM | 30
BLMCFT (portable tester) | 8 |  | 8 | [13 empty] | EDA-01329
Parallax Stratix 672 SmartPack | 8 | 0 | 8 |  | 1 | 7 |  | Completed | 7 | 7 | 7 |  | 0 | 653 | 5576.62 | 1 on the prototype
QuickUsb Module | 8 | 0 | 8 |  | 1 | 7 |  | Ordered | 0 | 7 | 0 |  | -7 | 211 | 1801.94 | 1 on the prototype
Photodiodes (Neoptek NTPPT-3EPNH Pigtailed 1.25Gbps InGaAs PIN/TIA Receiver) | 16 | 0 | 16 | 8 | 2 | 24 |  | Ordered | 0 | 24 | 0 |  | -24 | 69.331 | 1663.944
Relay V23026A1001B201 | 88 | 0 | 88 | 2 | 11 | 90 |  | Ordered | 0 | 120 | 0 |  | -90 | 2.5 | 225
Crystal Osc. (C-Mac 40.00 MHz IQXO-73B) | 8 | 0 | 8 | 1 | 1 | 9 |  | In stock | 14 | 0 | 14 |  | 5 |  |  |  | 9713565
TLK1501IRCP/R | 16 | 0 | 16 | 2 | 2 | 18 |  | Ordered | 0 | 18 | 0 |  | -18 | 12 | 216 |  | 8454876
AD5348 | 16 | 0 | 16 | 2 | 2 | 18 |  | Ordered | 2 | 16 | 0 |  | -18 | 15 | 270 |  | 8396906
MAX349 | 128 | 0 | 128 | 2 | 16 | 130 |  |  | 12 | 0 | 0 |  | -130 | 3.91 | 508.3
BSR17A | 88 | 0 | 88 | 2 | 11 | 90 |  |  | 0 | 0 | 0 |  | -90 | 4.5 | 405
BAT48 | 88 | 0 | 88 | 2 | 11 | 90 |  | In stock | 2500 | 0 | 2500 |  | 2410
OP291 | 16 | 0 | 16 | 2 | 2 | 18 |  | Ordered | 0 | 18 | 0 |  | -18 | 3 | 54 |  | 9994360
LM6134 | 48 | 0 | 48 | 2 | 6 | 50 |  | Ordered | 0 | 50 | 0 |  | -50 | 4.5 | 225 |  | 9490027
TMH0505 | 8 | 0 | 8 | 1 | 1 | 9 |  | Ordered | 4 | 5 | 4 |  | -5 | 14 | 126 |  | 1007554
LM4140-2.5V | 8 | 0 | 8 | 1 | 1 | 9 |  |  | 0 | 0 | 0 |  | -9 | 3 | 27
USB conn type B | 16 | 0 | 16 | 0 | 2 | 16 |  | Ordered | 0 | 16 | 0 |  | -16 | 1.5 | 24 |  | 1097897
74AC138SC | 8 | 0 | 8 | 1 | 1 | 9 |  | Ordered | 0 | 9 | 0 |  | -9 | 0.75 | 6.75 |  | 1103066
Reg 2.5V | 8 | 0 | 8 | 1 | 1 | 9 |  | In stock | 10 | 0 | 10 |  | 1
RF Chock | 8 | 0 | 8 | 1 | 2 | 9 |  | In stock | 10 | 0 | 10 |  | 1
EMCO High Voltage module | [7 empty] | In stock | 2 |  |  |  | 0
100uF | 8 | 0 | 8 | 0.16 | 1 | 8.16 |  |  | 0 | 0 | 0 |  | -8.16 | 0 | 0 |  | 10.71.01.471.5
10nF 2kV | 8 | 0 | 8 | 0.16 | 1 | 8.16 |  |  | 0 | 0 | 0 |  | -8.16 | 0 | 0 |  | 10.11.81.385.4
10uF POL | 40 | 0 | 40 | 0.8 | 5 | 40.8 |  |  | 0 | 0 | 0 |  | -40.8 | 0 | 0 |  | RS-262-4535
10uF 805 | 16 | 0 | 16 | 0.32 | 2 | 16.32 |  |  | 0 | 0 | 0 |  | -16.32 | 0 | 0 |  | Farnell-9402136
1uF 805 | 72 | 0 | 72 | 1.44 | 9 | 73.44 |  |  | 0 | 0 | 0 |  | -73.44 | 0 | 0 |  | Farnell-3352067
100nF 805 | 632 | 0 | 632 | 12.64 | 79 | 644.64 |  | Asked offer | 0 | 0 | 0 |  | -644.64 | 0 | 0 |  | Farnell-1086793
22nF C75x55 | 8 | 0 | 8 | 0.16 | 1 | 8.16 |  |  | 0 | 0 | 0 |  | -8.16 | 0 | 0 |  | RS-166-6443
10nF 805 | 104 | 0 | 104 | 2.08 | 13 | 106.08 |  | Asked offer | 0 | 0 | 0 |  | -106.08 | 0 | 0 |  | Farnell-1086795
1nF 805 | 64 | 0 | 64 | 1.28 | 8 | 65.28 |  | Asked offer | 0 | 0 | 0 |  | -65.28 | 0 | 0 |  | Farnell-9406344
10pF 805 | 24 | 0 | 24 | 0.48 | 3 | 24.48 |  | Asked offer | 0 | 0 | 0 |  | -24.48 | 0 | 0 |  | Farnell-9753559
0 R 805 1% | 56 | 0 | 56 | 1.12 | 7 | 57.12 |  | In stock | 500 | 500 | 500 |  | 442.88
51 R 805 1% | 80 | 0 | 80 | 1.6 | 10 | 81.6 |  | In stock | 500 | 500 | 500 |  | 418.4
200R 805 1% | 32 | 0 | 32 | 0.64 | 4 | 32.64 |  | In stock | 500 | 500 | 500 |  | 467.36
825R 805 1% | 16 | 0 | 16 | 0.32 | 2 | 16.32 |  | In stock | 500 | 500 | 500 |  | 483.68
10k 805 1% | 160 | 0 | 160 | 3.2 | 20 | 163.2 |  | In stock | 500 | 500 | 500 |  | 336.8
10R 805 1% | 128 | 0 | 128 | 2.56 | 16 | 130.56 |  | Asked offer | 0 | 0 | 0 |  | -130.56
330R 805 1% | 8 | 0 | 8 | 0.16 | 1 | 8.16 |  | Asked offer | 0 | 0 | 0 |  | -8.16
910R 805 1% | 64 | 0 | 64 | 1.28 | 8 | 65.28 |  | Asked offer | 0 | 0 | 0 |  | -65.28
1k 805 1% | 136 | 0 | 136 | 2.72 | 17 | 138.72 |  | Asked offer | 0 | 0 | 0 |  | -138.72
2k 805 1% | 16 | 0 | 16 | 0.32 | 2 | 16.32 |  | Asked offer | 0 | 0 | 0 |  | -16.32
9.1k 805 1% | 64 | 0 | 64 | 1.28 | 8 | 65.28 |  | Asked offer | 0 | 0 | 0 |  | -65.28
20k 805 1% | 8 | 0 | 8 | 0.16 | 1 | 8.16 |  | Asked offer | 0 | 0 | 0 |  | -8.16
240k 805 1% | 128 | 0 | 128 | 2.56 | 16 | 130.56 |  | Asked offer | 0 | 0 | 0 |  | -130.56
QuickUSB Connecteur | 8 | 0 | 8 | 0.16 | 1 | 8.16 |  |  | 16 | 16 | 16 |  | 7.84
Total |  |  | 570079.3 | 29509.551 |  | 599788.242 |  |  |  | 769040 |  |  |  | 2451.9277 | 1846275.1239
Note on A118: czam: Price increase (from BPM's DAB64x) FPGA: SFr. 432.32/card <---- (212,134 SFr / 360 pcs - 188,328 SFr / 1200 pcs) SRAM: SFr. 9.75/card <---- 3 * (9,034 SFr / 1122 pcs - 19,008 SFr / 3960 pcs) FPanel: E-2000: Total:
Note on A134: czam: will be changed with a similar one.
Note on A135: czam: new: FARNELL Part ID: 854025 Price: €9.39 FICHE FEMELLE SCSI 26 VOIES; Nombre de voies:26 ---------------------------------------------------------------- old: Code Commande : 965637 Fabricant HARTING Ref. Fabricant : 6011 026 5140 Description : SUB-D FEMELLE IEEE1284-C 26P http://www.farnell.com/datasheets/41215.pdf http://www.farnell.com/datasheets/21667.pdf
Note on A138: czam: BUTTON B3F-3100 OMRON SFr. 1.17 Best.-Nr.: 959704 Hersteller: OMRON Herstellerbez.: B3F-3100 Produktdetails PCB DUAL-IN-LINE-DRUCKTASTER; RoHS -konform:JA; Schaltfunktionstyp:SPNO; Spannung, Kontakt max. DC:24V; Temperatur, Betriebs- max.:70°C; Temperatur, Betriebs- min.:-25°C; Länge/Höhe, Außen-:7.4mm; Breite/Weite:7.3mm; Tiefe, Aussen:7.15mm; Haltbarkeit, elektrisch:10000000; Haltbarkeit, mechanisch:10000000; Spannungsfestigkeit, VDC:500V; Strom, Kontakt bei Kontaktspannung, DC, max.:50mA; Strom, Last, min.:1mA; Widerstand, Isolations-:100MR; Widerstand, Kontakt-:100mR
Note on A144: czam: Changed for 825 1% in state of 820 5%
Note on A155: czam: NOT nessacery for production
Note on A156: czam: not necessary for production FARNELL Part ID: 487703 Price: €5.18 FICHE SCSI-2 26 VOIES; Conforme RoHS:NON; Nombre de voies:26; Approuvé:EIA RS232, IPI, HIPPI, SCSI-2; Diamctre, câble max.:0.91mm; Diamctre, câble min.:0.74mm; Inflammabilité:UL94V-0; Maticre:Plastique noir; Maticre, con
Note on D228: czam: Total Number of components needed
Note on E106: czam: Production Loss = 8%
Note on E121: czam: production loss: 2%
Note on E131: czam: production loss: 2%
Note on E133: czam: production loss: 2%
Note on E134: czam: production loss: 2%
Note on E137: czam: production loss: 2%
Note on G228: czam: Total Number of components to be ordered
Note on I122: czam: Joint order with the BPM by Jose
Note on K109: effinger: original 1505 ordered new TID for 75 pcs launched at 31.10.05
Note on K110: dehning: first order 1460 second 120, out 22.09.05
Note on K120: czam: 17 Packages of 66 pcs
Note on K156: czam: minimum quantity
Note on K228: czam: Total Number of components to be ordered
Note on L110: dehning: first 1410 second 170
Note on O110: dehning: ST price
Note on O114: effinger: Total costs 127400$ for 1580 GOHs excange rate: 1.22
Note on O119: czam: ordered 24.05.05 Price given by EBV unit price $483 Total price $173,880
Note on O120: czam: ordered 31.03.05 unit price $6.60 Total price $7,405.20 MSC SUISSE SA, Avenue Nestle 14, 1820 MONTREUX (MSC-02, MA01)
Note on O121: czam: ordered 22.06.05 EME AG , Lohwisstrasse, 50, 8123 EBMATINGEN (EMEG50, MA01)
Note on O131: czam: Price for one piece. Offer has NOT been requested.
Note on O133: czam: ordered 22.06.05 EME AG , Lohwisstrasse, 50, 8123 EBMATINGEN (EMEG50, MA01)
Note on O134: dehning: aproximate price 53 br. Pounds
Note on O137: czam: price from FARNELL Zurich 6% deduction not calculated.
Note on O139: czam: ordered: 23.11.2005 SPOERLE ELECTRONIC DISTRIBUTION INTERNATIONAL, Case Postale, 1442 MONTAGNY (SPOE01, MA01)
Note on O146: czam: PRICE FROM ELECTRONITEL SA, C.P. 142, 1752 VILLARS-SUR-GLANE 1 (ELEC10, MA01)
Note on P119: dehning: dollar 1.22 (24.05.05)
Note on P131: czam: Unit : €7.00 Total €10,080.00 10,080 * 1.554 = 15664.32
Note on P132: czam: €418.60 * 1.554 = 650
Note on P134: czam: Final Price
Note on P137: czam: https://edh.cern.ch/Document/DAI/2011788 ordered: 03/11/2005 FARNELL ZH
Note on P161: czam: relative price (calculated including spare parts)
Note on Q114: effinger: e-mail from Alexander The Kapsch production rate is 400/week, our burning-in and testing rate is 228/week. If we will finish all formalities soon we can ask Kapsch to start your GOH production as soon as they will receive CRT4T. As all PCBs are ready, the boards assembly and testing will take one week, not more. Hence, the lasers mounting can start April. In this case all 1580 GOHs can be produced by April, latest first week of May, first slice delivered end-April, second mid- or end-May. The burning-in and testing will start in May and will take 1580/228=7weeks.
Note on U161: czam: Accurate price for components in one card

## CFC EDA-00593-V6
EDA-00593-V6
Current to Frquency Converter Liste de matériel / Material List
| Client/Customer: |  | Effinger E. |  |  | Through pins: | 130
| DATE: |  | 2006-03-03 |  |  | SMD pins on TOP: | 1977
| Dessinateur/Drawn by: |  | Benoit Civel |  |  | SMD pins on BOTTOM: | 574
| TS/DEM/BE |  | Board dimensions: 220x100mm |  |  | Total nb of pins: | 2681
Ref. | Qty | SCEM | Description | Value | Fournisseur/Supplier |  | Boitier/Outline
Matériel monté sur le PCB / Parts mounted on the PCB
BOX1 | 1 |  | BOX_PFL3_75X50 | BOX_PFL3_75X50 | PERANCEA LTD
C1->C4 C10,C15 C21->C23 | 9 |  | 35V SMD Tantalum Electrolytic Capacitor | 100uF | SIEMENS |  | Type B
C11->C12 C14,C19 C99 C119->C120 C125 C128->C129 C132->C133 C136->C137 C140,C147 C150,C153 C156,C158 C192,C194 C196,C198 C200,C204 C208,C212 C216,C220 C226 C228->C230 C233 C235->C237 C262->C267 C295,C298 C302->C303 C305,C308 C314,C317 C323 | 53 |  | 10V SMD Ceramic Capacitor | 10uF | MURATA | GRM31CR60J106KC01 | C1206
C13 | 1 | 10.03.04.500.2 | 50V SMD Ceramic Capacitor | 100nF |  |  | C1206
C160,C163 C168,C171 C176,C179 C184,C187 | 8 | 10.03.04.400.5 | 50V SMD Ceramic Capacitor | 10nF |  |  | C1206
C17,C293 C299 | 3 |  | 50V SMD Multilayer Chip Ceramic Capacitor | 100pF |  |  | C0805
C238->C261 C268->C291 | 48 |  | 16V SMD Ceramic Capacitor | 100nF | FARNELL | 301-9482 | C0402
C24->C31 C56,C58 C60 C63->C64 C66,C68 C70,C159 C166->C167 C174->C175 C182->C183 C190 | 24 | 10.03.04.200.1 | 50V SMD Ceramic Capacitor | 100pF |  |  | C1206
C32->C55 C301,C306 | 26 | 10.03.04.100.4 | 50V SMD Ceramic Capacitor | 10pF |  |  | C1206
C5->C9 C16,C18 C20 C88->C98 C100->C118 C121->C123 C126->C127 C130->C131 C134->C135 C138->C139 C141->C146 C148->C149 C151->C152 C154->C155 C157 C161->C162 C164->C165 C169->C170 C172->C173 C177->C178 C180->C181 C185->C186 C188->C189 C191,C193 C195,C197 C199 C201->C203 C205->C207 C209->C211 C213->C215 C217->C219 C221->C225 C227 C231->C232 C234,C292 C294 C296->C297 C300,C304 C307 C309->C313 C315->C316 C318->C322 C324 | 127 | 10.03.05.615.1 | 50V 10% SMD Ceramic Capacitor | 100nF | FARNELL(MULTICOMP) | 4227189(U0805R104KNT) | C0805
C57,C59 C61->C62 C65,C67 C69,C71 C124 | 9 | 10.03.04.133.5 | 50V SMD Ceramic Capacitor | 33pF |  |  | C1206
C72,C74 C76,C78 C80,C82 C84,C86 | 8 | 10.03.04.247.6 | 50V SMD Ceramic Capacitor | 470pF | VITRAMON |  | C1206
C73,C75 C77,C79 C81,C83 C85,C87 | 8 |  | 50V SMD Ceramic Capacitor | 4.7nF |  |  | C1206
D1,D3 D5,D7 D9,D11 D13,D15 D17->D34 | 26 |  | Low-leakage Double Diode | BAV199 | PHILIPS | BAV199 | SOT23
D2,D4 D6,D8 D10,D12 D14,D16 | 8 |  | Dual Series Rectifier Diode | BAV99LT1 | Motorola/ON | BAV99LT1 | SOT23
IC1 | 1 |  | SX-A FPGA | A54SX72A2PQ208I | ACTEL | A54SX72A2PQ208I | PQFP208_050
IC10->IC11 | 2 |  | A quad 12 bit-40 Ms/s 450 mW CMOS A/D Converter | AD41240 | CERN CHIPIDEA | AD41240 | BGA144M12_100
IC12->IC16 IC22,IC27 IC32,IC37 | 9 |  | Dual General Purpose, Low Voltage, TinyPack Comparator | LMV393M | NATIONAL SEMICONDUCTOR | LMV393M | SO8
IC19 | 1 |  | High Precision Low Noise Low Dropout Voltage | LM4140CCM-2.5 | NATIONAL SEMICONDUCTOR | LM4140CCM-2.5 | SO8
IC2 | 1 |  | 2.5V to 5.5V Parallel Interface Octal Voltage Output 8 Bit DACs | AD5346BRU | ANALOG DEVICES | AD5346BRU | SOIC38MA_050
IC21 IC25->IC26 IC30->IC31 IC35->IC36 IC40 | 8 |  | High Speed Fully Differential I/O Amplifiers | THS4141CD | TEXAS | THS4141CD | SOIC8S_127
IC23,IC28 IC33,IC38 | 4 |  | Dual Retriggerable Monostable Multivibrator | 74LS123D | TEXAS | 74LS123D | SOIC16
IC24,IC29 IC34,IC39 | 4 |  | High Speed Dual Differencial Comparator | NE521D | PHILIPS SEMICONDUCTORS | NE521D | SOT108-1
IC3 IC17->IC18 IC20 | 4 |  | Voltage-Feedback Operational Amplifier | TL072CD | MOTOROLA/TEXAS | TL072CD | SOIC8
IC4->IC9 | 6 |  | Eight Channels Differential Line Receiver | CRT910 | CERN CHIPIDEA | LVDS_RX | LPCC32_050
IC41->IC48 | 8 |  | Voltage feedback operational amplifier | OPA637AU | BURR-BROWN | OPA637AU | SOIC8S_S127
J1->J2 | 2 |  | Narrow Pitch (0.8mm) Connector P8 Series | AXN350038S | NAIS | AXN350038S
J3 | 1 | 09.61.33.215.0 | 96 Pins Right Angle PCB Connector |  | ERNI | DIN 41612-TYPE C
P1,P3 P5,P7 P9,P11 P13,P15 | 8 |  | 1/4W 10% SMD Miniature Trimmer 11 Turns Cermet Sealed | 1K | VISHAY SFERNICE | TSM4YL1K | TSM4YL
P2,P4 P6,P8 P10,P12 P14,P16 | 8 |  | 1/4W 10% SMD Miniature Trimmer 11 Turns Cermet Sealed | 5K | VISHAY SFERNICE | TSM4YL5K | TSM4YL
QZ1 | 1 |  | Quartz 40MHz | X357T(178-9978) | C-MAC | 40MHz IQXO-70 C
R1->R8 R180,R185 R190,R195 R200,R205 R210,R215 | 16 |  | 5% High Resistance Thick Film Chip Resistors | 10G | RIEDON | CHS1206-10G | S32X16
R11,R14 R17 R20->R22 R27,R30 R63,R90 R245->R246 R248,R257 R259->R262 | 18 |  | Specified On Test (S.O.T) SMD Resistor |  |  |  | R1206
R114->R115 R120 R122->R123 R128 R130->R131 R136 R138->R139 R144 R146->R147 R152 R154->R155 R160 R162->R163 R168 R170->R171 R176 | 24 | 11.24.05.247.4 | 1/4W 1% SMD Resistor | 470 | BOURNS | CR 1206-FX | R1206
R118,R127 R134,R143 R150,R159 R166,R175 | 8 | 11.24.05.356.0 | 1/4W 1% SMD Resistor | 5.6K | BOURNS | CR 1206-FX | R1206
R12->R13 R23->R26 R28->R29 R252->R253 R255 | 11 | 11.24.05.151.1 | 1/4W 1% SMD Resistor | 51 | BOURNS | CR 1206-FX | R1206
R15,R18 R62,R68 R81,R89 R97,R179 R184,R189 R194,R199 R204,R209 R214,R254 R256,R258 R264 | 19 | 11.24.05.000.5 | SMD Jumper | 00 | BOURNS | CR 1206-FX | R1206
R16,R19 R44,R48 R70,R76 R83,R88 R91,R96 R119,R126 R135,R142 R151,R158 R167,R174 R251 | 19 | 11.24.05.300.6 | 1/4W 1% SMD Resistor | 1K | BOURNS | CR 1206-FX | R1206
R178,R183 R188,R193 R198,R203 R208,R213 | 8 | 11.24.05.239.4 | 1/4W 1% SMD Resistor | 390 | BOURNS | CR 1206-FX | R1206
R181,R186 R191,R196 R201,R206 R211,R216 | 8 | 11.22.10.347.8 | 0.4W 1% High Stability Metal Film Resistor | 470 | PHILIPS | TYPE MRS 25 (2322 156...) | R04WHS
R182,R187 R192,R197 R202,R207 R212,R217 | 8 | 11.22.10.422.4 | 0.4W 1% High Stability Metal Film Resistor | 2.2K | PHILIPS | MRS 25 (2322 156...)
R218 | 1 | 11.24.05.315.9 | 1/4W 1% SMD Resistor | 1.5K | BOURNS | CR 1206-FX | R1206
R227->R228 R247,R250 | 4 | 11.24.05.600.7 | 1/4W 1% SMD Resistor | 1M | BOURNS | CR 1206-FX | R1206
R229->R244 | 16 | 11.24.05.243.8 | 1/4W 1% SMD Resistor | 430 | BOURNS | CR 1206-FX | R1206
R31,R249 | 2 | 11.24.05.412.9 | 1/4W 1% SMD Resistor | 12K | BOURNS | CR 1206-FX | R1206
R32,R39 R43 R52->R54 R58 R60->R61 R73,R77 R116,R124 R132,R140 R148,R156 R164,R172 | 19 | 11.24.05.351.5 | 1/4W 1% SMD Resistor | 5.1K | BOURNS | CR 1206-FX | R1206
R33 R219->R226 | 9 | 11.24.05.551.9 | 1/4W 1% SMD Resistor | 510K | BOURNS | CR 1206-FX | R1206
R34,R50 R85,R117 R121,R125 R129,R133 R137,R141 R145,R149 R153,R157 R161,R165 R169,R173 R177 | 19 | 11.24.05.500.0 | 1/4W 1% SMD Resistor | 100K | BOURNS | CR 1206-FX | R1206
R35->R36 R42,R57 R64->R66 R80 | 8 | 11.24.05.400.3 | 1/4W 1% SMD Resistor | 10K | BOURNS | CR 1206-FX | R1206
R37 | 1 | 11.24.05.330.0 | 1/4W 1% SMD Resistor | 3K | BOURNS | CR 1206-FX | R1206
R38,R69 | 2 |  | 10% SMD NTC Thermistors With Silver Palladium Termination | 10K NTC | EPCOS | B57621C0103K062 | R1206
R40,R86 | 2 |  | 0.1% High Resistance Thick Film Chip Resistors | 150k 0.1% | VISHAY | P1206E1503BB | R1206
R41 | 1 |  | 0.1% High Resistance Thick Film Chip Resistors | 15k 0.1% | VISHAY | P1206E1502BB | R1206
R45 | 1 | 11.24.05.513.5 | 1/4W 1% SMD Resistor | 130K | BOURNS | CR 1206-FX | R1206
R46 | 1 | 11.24.05.539.5 | 1/4W 1% SMD Resistor | 390K | BOURNS | CR 1206-FX | R1206
R47,R263 | 2 | 11.24.05.422.7 | 1/4W 1% SMD Resistor | 22K | BOURNS | TYPE CR 1206-FX | R1206
R49 | 1 | 11.24.05.515.3 | 1/4W 1% SMD Resistor | 150K | BOURNS | CR 1206-FX | R1206
R55 | 1 | 11.24.05.547.5 | 1/4W 1% SMD Resistor | 470K | BOURNS | CR 1206-FX | R1206
R56 | 1 | 11.24.05.518.0 | 1/4W 1% SMD Resistor | 180K | BOURNS | CR 1206-FX | R1206
R59,R87 | 2 |  | 0.1% High Resistance Thick Film Chip Resistors | 220k 0.1% | VISHAY | P1206E2203BB | R1206
R67 | 1 | 11.24.05.347.1 | 1/4W 1% SMD Resistor | 4.7K | BOURNS | CR 1206-FX | R1206
R71 | 1 | 11.24.05.527.9 | 1/4W 1% SMD Resistor | 270K | BOURNS | CR 1206-FX | R1206
R72,R74 | 2 | 11.24.05.524.2 | 1/4W 1% SMD Resistor | 240K | BOURNS | CR 1206-FX | R1206
R75 | 1 | 11.24.05.427.2 | 1/4W 1% SMD Resistor | 27K | BOURNS | CR 1206-FX | R1206
R78 | 1 |  | 0.1% High Resistance Thick Film Chip Resistors | 300k 0.1% | VISHAY | P1206E3003BB | R1206
R79 | 1 |  | 0.1% High Resistance Thick Film Chip Resistors | 120k 0.1% | VISHAY | P1206E1203BB | R1206
R82 R94->R95 | 3 |  | 0.1% High Resistance Thick Film Chip Resistors | 47k 0.1% | VISHAY | P1206E4702BB | R1206
R84 | 1 | 11.24.05.516.2 | 1/4W 1% SMD Resistor | 160K | BOURNS | CR 1206-FX | R1206
R9->R10 | 2 | 11.24.05.391.7 | 1/4W 1% SMD Resistor | 9.1K | BOURNS | CR 1206-FX | R1206
R92 | 1 | 11.24.05.451.2 | 1/4W 1% SMD Resistor | 51K | BOURNS | CR 1206-FX | R1206
R93 | 1 | 11.24.05.520.6 | 1/4W 1% SMD Resistor | 200K | BOURNS | CR 1206-FX | R1206
R98->R113 | 16 | 11.24.05.333.7 | 1/4W 1% SMD Resistor | 3.3K | BOURNS | CR 1206-FX | R1206
ST1 | 1 |  | SMD Selection Jumper | 00 | - | - | R0805
ST2->ST7 | 6 |  | SMD Stand-Alone Pin for Probe Test Pin |  |  |  | Not Mounted
ST8 | 1 | 07.88.24.508.1 | Metallic Jumper For PCB |  | COMATEL | 313000.5000.500
T1->T17 | 17 |  | P-Channel Switch | MMBFJ176 | FAIRCHILD | MMBFJ176 | SOT-23
TP3->TP20 | 18 |  | Stand-alone Pin For Probe Test Pin | Mounted
Z1->Z2 | 2 |  | General-Purpose Reference/Regulator Diode | 2V7 | PHILIPS | BZX84C2V7 | SOT23
NOT MOUNTED
PB1 | 1 |  | SMT Push Button |  | DIPTRONICS | DTSL-61R-B | SW4PSMD_DTSL6

## Mezz. EDA-00780-V3
EDA-00780-V3
MEZZANINE FOR DAB64X Liste de matériel / Material List
| Client/Customer: |  | C. Zamantzas |  |  | Through pins: | 72
| DATE: |  | 2005-12-20 |  |  | SMD pins on TOP: | 398
| Dessinateur/Drawer: |  | Jean-Marc Combe |  |  | SMD pins on BOTTOM: | 219
| TS/DEM/BE |  | Board dimensions: 146x110mm |  |  | Total nb of pins: | 689
Ref. | Qty | SCEM | Description | Value | Fournisseur/Supplier |  | Boitier/Outline
Matériel monté sur le PCB / Parts mounted on the PCB
C1->C2 C4 C6->C7 C9 C13->C14 C16 C18->C19 C21 C33->C34 C42->C43 | 16 | 10.03.05.614.2 | 50V SMD Ceramic Capacitor | 10nF | FARNELL(MULTICOMP) | 4227153(U0805R103KNT) | C0805
C3,C5 C8 C10->C12 C15,C17 C20 C22->C29 C31 C35->C41 C44->C57 | 39 | 10.03.05.615.1 | 50V 10% SMD Ceramic Capacitor | 100nF | FARNELL(MULTICOMP) | 4227189(U0805R104KNT) | C0805
C30,C32 | 2 |  | 35V SMD Tantalum Electrolytic Capacitor | 100uF | SIEMENS |  | Type B
IC1->IC4 | 4 |  | 1.6 To 1.5 GBPS Transceiver |  | TEXAS INSTRUMENTS | TLK1501IRCP | PQFP64_050
IC5 | 1 |  | 1Mbit Serial Flash Memory |  | ST | M25P10 | SOIC8S_127
J1->J2 | 2 | 09.55.40.064.7 | 1mm SMD Male Board to Board Connector 10mm Stack |  | AMP | 120527-1
J3->J6 | 4 |  | 1.25Gbps Pigtailed Coaxial PIN-TIA PD | (3.3V) | NEOPTEK | NTPPT-3EPNH
J7 | 1 |  | 26 Pins Connector Solder Pins Angled |  | HARTING | 60 11 026 51
J8->J9 | 2 |  | 2x5 Pins Vertical Female Connector |  | FCI | 76342-305
L1->L2 | 2 |  | RF Choke | 1uH | Siemens | B82412 | SelfB82412
PB1 | 1 |  | Unipolar Push Button |  | OMRON | B3F-3100
QZ1 | 1 |  | Quartz 40MHz | X357T(178-9978)
R1,R9 R11,R18 R21 R27->R30 R39 | 10 | 11.24.09.111.6 | 1/8W 5% SMD Jumper | 00 | PHYCOMP | 2322 730 91002 | R0805
R2,R8 R10,R12 R19->R20 R31 R37->R38 R40 R46->R47 | 12 |  | 1/8W 5% SMD Resistor | 200 | BOURNS | CR 0805-FX | R0805
R22->R26 | 5 |  | 1/8W 5% SMD Resistor | 10K | BOURNS | CR 0805-FX | R0805
R3 R5->R7 R13 R15->R17 R32 R34->R36 R41 R43->R45 | 16 |  | 1/8W 5% SMD Resistor | 51 | BOURNS | CR 0805-FX | R0805
R4,R14 R33,R42 | 4 |  | 1/8W 5% SMD Resistor | 820 | BOURNS | CR 0805-FX | R0805
R48 | 1 |  | 1/8W 5% SMD Resistor | 100K | BOURNS | CR 0805-FX | R0805
R49 | 1 | 11.24.05.400.3 | 1/4W 1% SMD Resistor | 10K | BOURNS | CR 1206-FX | R1206
RG1 | 1 |  | 3A Low-VoLtage Low-Dropout Regulator |  | MICREL | MIC39300-2.5BU | TO263