## BLM System
Sub-System | needed for installation | spare (10%) | total needed quantity | production loss | pieces per card | to be ordered | lost units while tests | Status | in stock | in stock / or ordred | delivery date | checked by | quantity difference | Unit Price | Total Price [CHF] | delivery schedule | comments
|  | 0.1 |  | 0.055 |  | 749.683
CFC | 646 | 64.6 | 710.6 | 39.083 |  | 750 | [9 empty] | F82/Mar90/May73/Jul68/Au80/O86Dec163
Printed Circuit | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [10 empty] | https://edms.cern.ch/item/EDA-00593/0
APW 951-263903D (case) | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 35.5816 | 26686.2 |  | http://www.apw.com/raptor/pdf/pdf1-846.pdf
AXN350038S (GOH connector) | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 | [7 empty] | 5 | 7500 |  | http://www.naisweb.com/e/connecte/con_eng/pdf/con_eng_np3.pdf
CERN CHIPIDEA LVDS_RX | 3876 | 387.6 | 4263.6 | 234.498 | 6 | 4500 |  | TID launched | [5 empty] | 5.5 | 24750
CERN CHIPIDEA AD41240_V2 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 |  | TID launched | [5 empty] | 18.75 | 28125 |  | http://proj-kchip.web.cern.ch/proj-Kchip/preshower/doc/AD41240%20Manual%20v0.2.pdf
A54SX72A2PQ208I | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 75.64 | 56730 |  | http://www.actel.com/documents/SXA_DS.pdf
OPA627AU | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 19.67 | 118020 |  | http://focus.ti.com/lit/ds/symlink/opa627.pdf
NE521DN | 2584 | 258.4 | 2842.4 | 156.332 | 4 | 3000 | [7 empty] | 1.75 | 5250 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/NE521_2.pdf
74HCT123D | 2584 | 258.4 | 2842.4 | 156.332 | 4 | 3000 | [7 empty] | 0.38 | 1140 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/74HC_HCT123_3.pdf
THS4141CD | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 7.51 | 45060 |  | http://focus.ti.com/lit/ds/symlink/ths4141.pdf
AD5346 | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 7.14 | 5355 |  | http://www.analog.com/UploadedFiles/Data_Sheets/4283875071479AD5346_7_8_0.pdf
TL072CD | 1938 | 193.8 | 2131.8 | 117.249 | 3 | 2250 | [7 empty] | 0.77 | 1732.5 |  | http://focus.ti.com/lit/ds/symlink/tl072.pdf
LMV393M | 5814 | 581.4 | 6395.4 | 351.747 | 9 | 6750 | [7 empty] | 1.11 | 7492.5 |  | http://cache.national.com/ds/LM/LMV331.pdf
LM4041-2.5V | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 3.81 | 2857.5 |  | http://cache.national.com/ds/LM/LM4140.pdf
X357, CFPS-72B (40MHz) | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 2.6 | 1950 |  | http://www.cmac.com/mt/databook/oscillators/semtech/cfps-72.pdf
SST176 | 10336 | 1033.6 | 11369.6 | 625.328 | 16 | 12000 | [7 empty] | 0.32 | 3840 |  | http://www.vishay.com/docs/70257/70257.pdf
BAV99LT1 | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 0.03 | 180 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/BAV99_4.pdf
BAV199 | 16150 | 1615 | 17765 | 977.075 | 25 | 18750 | [7 empty] | 0.06 | 1125 |  | http://www.semiconductors.philips.com/acrobat_download/datasheets/BAV199_4.pdf
EPCOS SMD-NTC resistor B57621C103K62 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 | [7 empty] | 0.474 | 711 |  | http://www.epcos.com/inf/50/db/ntc_02/00600061.pdf
High ohmic resistor CHS 1206 10G 5 500 | 10336 | 1033.6 | 11369.6 | 625.328 | 16 | 12000 |  |  | 1900 |  |  |  |  | 2.08 | 24960 |  | http://www.willow.co.uk/CHS.pdf
1/4W 10% SMD Trimmer 11 Turns 1k | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 2.91 | 17460 |  | http://www.vishay.com/docs/51009/tsm4.pdf
1/4W 10% SMD Trimmer 11 Turns 5k | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 2.91 | 17460 |  | http://www.vishay.com/docs/51009/tsm4.pdf
100uF 10V SMD | 5814 | 581.4 | 6395.4 | 351.747 | 9 | 6750 | [7 empty] | 3.21 | 21667.5 |  | http://www.kemet.com/kemet/web/homepage/kechome.nsf/vapubfilesname/F3102T495.pdf/$file/F3102T495.pdf
10uF SMD 1206 | 31654 | 3165.4 | 34819.4 | 1915.067 | 49 | 36750 | [7 empty] | 0.56 | 20580 |  | http://www.murata.com/catalog/c02e11.pdf#page=14
100nF SMD 0402 | 31008 | 3100.8 | 34108.8 | 1875.984 | 48 | 36000 | [7 empty] | 0.02 | 720 |  | http://www.farnell.com/datasheets/57604.pdf
100nF SMD 0805 | 78166 | 7816.6 | 85982.6 | 4729.043 | 121 | 90750 | [7 empty] | 0.02 | 1815
10pF SMD 0805 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 | [7 empty] | 0.02 | 30
standard material
100nF | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 10.03.04.500.2
10nF | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 0.02 | 120 |  | 10.03.04.400.5
10pF | 16796 | 1679.6 | 18475.6 | 1016.158 | 26 | 19500 | [7 empty] | 0.02 | 390 |  | 10.03.04.100.4
33pF | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 0.02 | 120 |  | 10.03.04.133.5
100pF | 15504 | 1550.4 | 17054.4 | 937.992 | 24 | 18000 | [7 empty] | 0.03 | 540 |  | 10.03.04.200.1
470pF | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 0.02 | 120 |  | 10.03.04.247.6
4.7nF | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 0.02 | 120 |  | 10.03.04.347.3
DIN 41612-TYPE C | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 1.7 | 1275 |  | 09.61.33.215.0
100 | 3876 | 387.6 | 4263.6 | 234.498 | 6 | 4500 | [7 empty] | 0.02 | 90 |  | 11.24.05.200.9
10K | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 0.02 | 120 |  | 11.24.05.400.3
9.1K | 1938 | 193.8 | 2131.8 | 117.249 | 3 | 2250 | [7 empty] | 0.02 | 45 |  | 11.24.05.391.7
3.3K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.333.7
1.6K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.316.8
51 | 16150 | 1615 | 17765 | 977.075 | 25 | 18750 | [7 empty] | 0.02 | 375 |  | 11.24.05.151.1
6.8K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.368.6
39K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.439.8
6.2K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.362.2
11K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.411.0
2.7K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.327.5
2.4K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.324.8
00 | 3230 | 323 | 3553 | 195.415 | 5 | 3750 | [7 empty] | 0.02 | 75 |  | 11.24.05.000.5
3.6K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.336.4
22K | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 | [7 empty] | 0.02 | 30 |  | 11.24.05.422.7
240 | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 | [7 empty] | 0.02 | 30 |  | 11.24.05.224.1
1.2K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.312.2
2K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.320.2
390 | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 0.02 | 120 |  | 11.24.05.239.4
2.2K | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 0.02 | 120 |  | 11.24.05.322.0
1.5K | 646 | 64.6 | 710.6 | 39.083 | 1 | 750 | [7 empty] | 0.02 | 15 |  | 11.24.05.315.9
12K | 1292 | 129.2 | 1421.2 | 78.166 | 2 | 1500 | [7 empty] | 0.02 | 30 |  | 11.24.05.412.9
470 | 31654 | 3165.4 | 34819.4 | 1915.067 | 49 | 36750 | [7 empty] | 0.02 | 735 |  | 11.24.05.247.4
5.1K | 10336 | 1033.6 | 11369.6 | 625.328 | 16 | 12000 | [7 empty] | 0.02 | 240 |  | 11.24.05.351.5
5.6K | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 0.02 | 120 |  | 11.24.05.356.0
100K | 5168 | 516.8 | 5684.8 | 312.664 | 8 | 6000 | [7 empty] | 0.02 | 120 |  | 11.24.05.500.0
1K | 31008 | 3100.8 | 34108.8 | 1875.984 | 48 | 36000 | [7 empty] | 0.02 | 720 |  | 11.24.05.300.6
GOH | 1292 | 129.2 | 1421.2 | 113.696 |  | 1534.896 |  |  |  | 1525 |  |  | -9.896 |  |  |  | http://cms-tk-opto.web.cern.ch/cms-tk-opto/ecal/components/goh.html
GOL (order) | 1292 | 129.2 | 1421.2 |  |  | 1525 |  | Completed |  | 1580 |  |  | 55 |  |  |  | http://proj-gol.web.cern.ch/proj-gol/
LASER+E2000 APC | 1292 | 129.2 | 1421.2 |  |  | 1525 |  |  |  | 1580 |  |  | 55 | 134.5 | 212510 |  | http://cms-tk-opto.web.cern.ch/cms-tk-opto/tk/components/laserpill.html
GOH | 1292 | 129.2 | 1421.2 |  |  | 1525 |  |  |  | 1580 | [5 empty] | J300/Mar400/May400/Julrest
CRT4T | 1292 | 129.2 | 1421.2 |  |  | 1525 |  | TID launched |  | 1580
TC | 331 | 33.1 | 364.1 | [13 empty] | EDA-00998
STRATIX EP1S40F780C7 | 331 | 33.1 | 364.1 |  |  | 358 |  | Completed |  | 360 |  |  | 2 | 483 | 212133.6 |  | http://altera.com/products/devices/stratix/stx-index.jsp
AS7C33512PFS32A-166TQC | 993 | 99.3 | 1092.3 |  |  | 1073 |  | Completed |  | 1122 |  |  | 49 | 6.6 | 9034.344 |  | http://www.alsc.com/pdf/sram.pdf/fs/as7c331mpfs32a-36a_v2.3.pdf
PMC Connector (Socket: 71439-1164 (SMT 64WAY 11/12MM HIGH)) | 662 | 66.2 | 728.2 | 14.564 |  | 742.764 |  | Completed |  | 840 |  |  | 97.236 | 2.87 | 2410.8 |  | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/MX71439.pdf
Front Pannel | 331 | 33.1 | 364.1
E-2000 Mating Adapter + Sleeve | 1324 | 132.4 | 1456.4
TC mezzanine | 331 | 33.1 | 364.1 | [13 empty] | EDA-00780
TLK1501 | 1324 | 132.4 | 1456.4 | 29.128 |  | 1485.528 | [7 empty] | 8.4 | 15223.6909 |  | http://focus.ti.com/docs/prod/folders/print/tlk1501.html
Photodiodes (Afonics TXP0036 Pigtailed 1.25Gbps InGaAs PIN/TIA Receiver) | 1324 | 132.4 | 1456.4 | 29.128 |  | 1485.528 | [7 empty] | 116 | 172321.248 |  | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/TXP0036.pdf
Crystal Osc. (C-Mac 40.00 MHz IQXO-71B) | 331 | 33.1 | 364.1 | [13 empty] | http://www.cmac.com/mt/databook/oscillators/smd/spxo/iqxo_70.html
PMC Connector (Header: 71436-2164 (SMT 64WAY 10MM HIGH)) | 662 | 66.2 | 728.2 | 14.564 |  | 742.764 |  | Completed |  | 760 |  |  | 17.236 | 2.99 | 2272.4 |  | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/MX71436.pdf
Voltage Regulator (MIC39300-2.5BU) | 331 | 33.1 | 364.1 |  |  | 364.1 | [7 empty] | 9.5 | 3458.95 |  | http://ab-div-bdi-bl-blm.web.cern.ch/ab-div-bdi-bl-blm/BLMTC_Design/pdf_files/Datasheets/mic39300.pdf
NV-Memory (ST M25P10-A) | 331 | 33.1 | 364.1 |  |  | 364.1 | [10 empty] | http://focus.ti.com/docs/prod/folders/print/tlk1501.html
Receptacle (JAE - DA1 Series) | 331 | 33.1 | 364.1 |  |  | 364.1 | [10 empty] | http://www.jae.com/productpdf/ioc/ptc/da1.pdf
RF Choke (B82412A1102K) | 662 | 66.2 | 728.2 | 14.564 |  | 742.764 | [7 empty] | 0.95 | 705.6258
Plug Connector (JAE - DA1 Series) | 10 | 0 | 10 |  |  | 10 | [10 empty] | http://www.jae.com/productpdf/ioc/ptc/da1.pdf
JTAG Connector (plug & recept.) | 662 | 66.2 | 728.2 |  |  | 728.2
COM | 30
Ion ch. (CNGS 80 included) | 3562 | 237 | 3799
Al electrodes |  |  | 231739
feed throughs |  |  | 7598
Ceramics |  |  | 7598
cover assembly |  |  | 7598
tube (long)
tube (short)
SEM | 274 | 41 | 315
Ti electrodes |  |  | 315
|  |  | 738676.5 |  |  | 508060.848
Total |  |  | 6974 | 25971.396 |  | 2284.896 |  |  |  | 10927 |  |  |  | 965.0256 | 1079117.8587
Note on A85: czam: will be changed with a similar one.
Note on A93: czam: Still under Consiferation
Note on C100: dehning: Total IC 3562 Spare IC arcs IC 2160 65 3% Spare IC SS IC 1402 140 10% BL mobile 32
Note on C114: dehning: Spare SEM 274 41 15%
Note on D101: dehning: 61 per chamber
Note on D123: czam: Total Number of components needed
Note on E70: czam: Production Loss = 8%
Note on E79: czam: production loss: 2%
Note on E84: czam: production loss: 2%
Note on E85: czam: production loss: 2%
Note on E87: czam: production loss: 2%
Note on E91: czam: production loss: 2%
Note on G123: czam: Total Number of components to be ordered
Note on K71: effinger: original 1505 ordered new TID for 75 pcs launched at 31.10.05
Note on K72: dehning: first order 1460 second 120, out 22.09.05
Note on K78: czam: 17 Packages of 66 pcs
Note on O72: dehning: ST price
Note on O77: czam: ordered 24.05.05 Price given by EBV unit price $483 Total price $173,880
Note on O78: czam: ordered 31.03.05 unit price $6.60 Total price $7,405.20 MSC SUISSE SA, Avenue Nestle 14, 1820 MONTREUX (MSC-02, MA01)
Note on O79: czam: ordered 22.06.05 EME AG , Lohwisstrasse, 50, 8123 EBMATINGEN (EMEG50, MA01)
Note on O84: czam: Price for one piece. Offer has NOT been requested.
Note on O85: dehning: aproximate price 53 br. Pounds
Note on O87: czam: ordered 22.06.05 EME AG , Lohwisstrasse, 50, 8123 EBMATINGEN (EMEG50, MA01)
Note on O88: czam: price from FARNELL Zurich
Note on O91: czam: price from FARNELL Zurich
Note on P77: dehning: dollar 1.22 (24.05.05)

## TC mezz.
EDA-00780-V1
Mezzanine For DAB64X
Nom du client: |  | C. Zamantzas
DATE: |  | 2004-09-20
Dessinateur: |  | Jean-Marc Combe
Board dimensions: 144x100mm
Materiel monté sur le circuit
QTY | SCEM/NAME | Supplier | Description | Value | Outline | Volt./ w. | Tol. | Parts
Standard Magasin (SCEM)
2 | 09.55.40.064.7 | AMP | 1.0mm FH (IEEE 1386) Mezzanine SMD Connector 10mm stacking | AMP 120527-1 |  |  |  | J1-J2
Non Standard Magasin
3 | 07.88.24-VKDEG |  | Address Selection Jumper (mounted on SCEM 09.55.10.708.9) | JUMPER |  |  |  | ST1-ST3
1 | 08.11.B82412-A1100 | Siemens | RF Choke | 1uH | SelfB82412 |  |  | L1
2 | 08.57.MIC39301-2.5BU | MICREL | Low-VoLtage Low-Dropout Regulator | MIC39300-2.5BU | TO263 | 3A |  | RG1-RG2
1 | 09.55.RJ45.95122 | MOLEX | Right Angle Standard Profile External Shield PCB Jack | RJ45 |  |  |  | J7
39 | 10.03.05.100NF (FARNELL 894-904) | Vitramon | SMD Ceramic Capacitor | 100nF | C0805 | 25V | 10% | C3,C5,C8,C10-C11,C14,C16,C19,C21,C23,C25-C38,C40,C44-C57
14 | 10.03.05.10NF | Vitramon | SMD Ceramic Capacitor | 10nF | C0805 | 50V |  | C1-C2,C4,C6-C7,C9,C12-C13,C15,C17-C18,C20,C42-C43
4 | 10.82.01.100UF | SIEMENS | SMD Tantalum Electrolytic Capacitor | 100uF | Type B | 35V |  | C22,C24,C39,C41
2 | 11.25.04.100K | Bourns | SMD Resistor | 100K | R0805 | 1/8W | 5% | R37-R38
4 | 11.25.04.100R | Bourns | SMD Resistor | 100 | R0805 | 1/8W | 5% | R5,R14,R23,R32
8 | 11.25.04.200R | BOURNS | SMD Resistor | 200 | R0805 | 1/8W | 5% | R1,R8,R10,R17,R19,R26,R28,R35
20 | 11.25.04.51R | Bourns | SMD Resistor | 51 | R0805 | 1/8W | 5% | R2,R4,R6-R7,R9,R11,R13,R15-R16,R18,R20,R22,R24-R25,R27,R29,R31,R33-R34,R36
4 | 11.25.04.820R | BOURNS | SMD Resistor | 820 | R0805 | 1/8W | 5% | R3,R12,R21,R30
1 | M25P10 | ST | 1Mbit Serial Flash Memory | M25P10 | SOIC8S_127 |  |  | IC5
4 | TLK1501IRCP | TEXAS INSTRUMENTS | 1.6 To 1.5 GBPS Transceiver | TLK1501IRCP | PQFP64_050 |  |  | IC1-IC4
4 | TXP0036-AFONICS | AFONICS | 1.25 Gbps InGaAs PIN/TIA Receiver | TXP0036 |  |  |  | J3-J6
Through pins: 38
SMD pins on TOP: 370
SMD pins on BOTTOM: 224
Total nb of pins: 632

## CFC EDA-00593-V3
C.F.C EDA-00593-V3
Nom du client: GF.Ferioli / E.Effinger
Date: 4/05/2005 | [8 empty] | 1.58
Materiel non standart
QTY | SCEM / Art. No. |  |  | Valeur | Remarques | Prix (EURO) | Prix (CH) PC | Prix par unité | QTY for 10 | QYT 750 | total price
1 | N.S | Cablage |  |  |  | 1.58 | 100 | 100 | 10 | 750 | 75000
1 | N:S | Circuit imprimé |  |  |  |  | 80 | 80 | 10 | 750 | 60000
2 | N.S | GOH |  |  |  |  | 200 | 400 | 20 | 1500 | 300000
1 | Radiospares 121-2118 | EMI-RFI Box 75*50*25mm |  | PFL3 | Box1 | 9.13 | 14.4254 | 14.4254 | 10 | 750 | 10819.05 |  | n.c.
1 | APW 951-263903D | Case |  |  | price for more than 500pcs | 22.52 | 35.5816 | 35.5816 | 10 | 750 | 26686.2
1 | DIPTRONICS | SMT Push Button | SW4PSMD_DTSL6 | DTSL-61R-B | PB1 |  |  |  | 10 | 750 | 0
9 | Radiospares 262-4759 | 10V SMD Tantalum Electrolytic Capacitor | SMD | 100uF 10V | C1->C4,C10,C44,C87->C89 | 2.032 | 3.2106 | 28.895 | 90 | 6750 | 21671.28
48 | FARNELL 301-9482 | 16V SMD Ceramic Capacitor; 2238 787 19849 PHYCOMP | SMD 0402 | 100nF | C220->C243,C250->C273 |  | 0.069 | 3.312 | 480 | 36000 | 2484
49 | Radiospares 367-3279 | 10V SMD Ceramic Capacitor | SMD 1206 | 10uF | C45,C47,C49,C53,C119,C122->C123,C126->C127,C130->C131,C134,C139,C142,C145,C148,C182,C185,C188,C191,C194,C197,C207,C209->C210,C213,C215->C216,C218->C219,C244->C249,C275,C277,C279,C281,C284,C286,C290->C291,C293,C299,C302,C308,C311 |  | 0.564 | 27.636 | 490 | 36750 | 20727
121 |  | 25V 10% SMD Ceramic Capacitor | SMD 0805 | 100nF | C5->C9,C46,C48,C50,C52,C54,C90->C118,C120->C121,C124->C125,C128->C129,C132->C133,C135->C138,C140->C141,C143->C144,C146->C147,C162->C165,C167->C170,C172->C175,C177->C181,C183->C184,C186->C187,C189->C190,C192->C193,C195->C196,C198->C206,C208,C211->C212,C214,C217,C274,C276,C278,C280,C282->C283,C285,C288,C292,C295->C298,C300->C301,C303->C307,C309->C310,C312 |  |  | 0 | 1210 | 90750 | 0
2 |  | 50V SMD Multilayer Chip Ceramic Capacitor | SMD 0805 | 100pF | C51,C287 |  | 0 | 0 | 20 | 1500 | 0
2 | NAIS A.C.G. AXN350038S | SM50 Contact Narrow-pitch NAIS AXN350038S |  | AXN350038S | J1->J2 |  | 5 | 10 | 20 | 1500 | 7500
8 |  | Dual Series Rectifier Diode | SOT23 | BAV99LT1 | D2,D4 D6,D8 D10,D12 D14,D16 | 0.02 | 0.0316 | 0.2528 | 80 | 6000 | 189.6
25 | Spoerle No. 110542 | Low-leakage Double Diode | SOT23 | BAV199W | D1,D3 D5,D7 D9,D11 D13,D15 D17->D33 | 0.039 | 0.06162 | 1.5405 | 250 | 18750 | 1155.375
8 | Radiospares 318-1297 | Dual General Purpose, Low Voltage, TinyPack Comparator | SO08 | LMV393M | IC12->IC15 IC20,IC25 IC30,IC35 | 0.7 | 1.106 | 8.848 | 80 | 6000 | 6636
1 | A54SX72A2PQ208I | SX-A FPGA | PQ208 | 54SX72A | IC1 | 62$ | 75.64 | 75.64 | 10 | 750 | 56730
6 | CERN CHIPIDEA LVDS_RX | LVDS driver | LPCC32_050 | LVDS_RX | IC4->IC9 |  | 10 | 60 | 60 | 4500 | 45000
1 | Spoerle AD5346BRU | 2.5V to 5.5V Parallel Interface Octal Voltage Output 8 Bit DACs | TSSOP-38 | AD5346 | IC2 | 7.41 | 11.7078 | 11.7078 | 10 | 750 | 8780.85
2 | CERN CHIPIDEA AD41240_V2 | A quad 12 bit-40 Ms/s 450 mW CMOS A/D Converter | BGA144M12_100 | AD41240_V2 | IC10->IC11 | 8.85 | 18.75 | 37.5 | 20 | 1500 | 28125
3 | Farnell 401134 | Voltage-Feedback Operational Amplifier | SOIC8 | TL072CD | IC3 IC16->IC17 | 0.49 | 0.7742 | 2.3226 | 30 | 2250 | 1741.95
8 | Spoerle No. 442433 | Precision Voltage feedback operational amplifier | SO08 | OPA627AU | IC38->IC45 | 12.45 | 19.671 | 157.368 | 80 | 6000 | 118026
4 | Chipbrocker NE521D | High Speed Dual Differencial Comparator | SO14 | NE521DN | IC22,IC27,IC32,IC37 | 1.11 | 1.7538 | 7.0152 | 40 | 3000 | 5261.4
4 | Radiospares 436-7644 | Dual Retriggerable Monostable Multivibrator | SO14 | 74HCT123D | IC21,IC26,IC31,IC36 | 0.24 | 0.3792 | 1.5168 | 40 | 3000 | 1137.6
8 | Far. 8453276 or Spoerle ??? | High Speed Fully Differential I/O Amplifiers | SOIC8S_127 | THS4141CD | IC18->IC19,IC23->IC24,IC28->IC29,IC33->IC34 | 4.75 | 7.505 | 60.04 | 80 | 6000 | 45030
1 | Radiospares 471-4337 | Voltage source | so08 | LM4041-2.5V |  | 2.41 | 3.8078 | 3.8078 | 10 | 750 | 2855.85
8 | Farnell 3065297 | 1/4W 10% SMD Miniature Trimmer 11 Turns Cermet Sealed | SMD | 1K | P1,P3, P5, P7, P9, P11, P13, P15 | 1.84 | 2.9072 | 23.2576 | 80 | 6000 | 17443.2
8 | Farnell 3065297 | 1/4W 10% SMD Miniature Trimmer 11 Turns Cermet Sealed | SMD | 5K | P1,P3, P5, P7, P9, P11, P13, P15 | 1.84 | 2.9072 | 23.2576 | 80 | 6000 | 17443.2 |  | will be added in V4
1 | Spoerle 040929 | Quarz 40MHz | SMD | X357, CFPS-72B | QZ1 |  | 0.08 | 0.08 | 10 | 750 | 60
2 | Radiospares 191-2342 | EPCOS SMD-NTC resistor B57621C103K62 | SMD | 10k | R113, R134 | 0.474 | 0.74892 | 1.4978 | 20 | 1500 | 1123.38
16 | Dynatime SA | High ohmic resistor CHS 1206 10G 5 500 | SMD | 10G | R1->R8 |  | 2.08 | 33.28 | 160 | 12000 | 24960 |  | 8 pcs more will be added in V4
16 | Spoerle 132075 | P-Channel JFET | SOT23 | SST176 | IC46->IC59 T13->T14 | 0.2 | 0.316 | 5.056 | 160 | 12000 | 3792
Materiel standart
1 | 10.03.04.500.2 | 50V SMD Ceramic Capacitor | SMD | 100nF | C11 |  | 0.02 | 0.02 | 10 | 750 | 15 | 1
8 | 10.03.04.400.5 | 50V SMD Ceramic Capacitor | SMD | 10nF | C150->C151,C153->C154,C156->C157,C159->C160 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 2
26 | 10.03.04.100.4 | 50V SMD Ceramic Capacitor | SMD | 10pF | C20->C43,C289,C294 |  | 0.02 | 0.52 | 260 | 19500 | 390 | 3
8 | 10.03.04.133.5 | 50V SMD Ceramic Capacitor | SMD | 33pF | C56,C60,C64,C67,C72,C76,C80,C84 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 4
24 | 10.03.04.200.1 | 50V SMD Ceramic Capacitor | SMD | 100pF | C12->C19,C55,C59,C63,C68,C71,C75,C79,C83,C149,C152,C155,C158,C161,C166,C171,C176 |  | 0.03 | 0.72 | 240 | 18000 | 540 | 5
8 | 10.03.04.247.6 | 50V SMD Ceramic Capacitor | SMD | 470pF | C57,C61,C65,C69,C73,C77,C81,C85 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 6
8 | 10.03.04.347.3 | 50V SMD Ceramic Capacitor | SMD | 4.7nF | C58,C62,C66,C70,C74,C78,C82,C86 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 7
1 | 09.61.33.215.0 | 96 Pins Right Angle PCB Connector |  | DIN 41612-TYPE C | J3 |  | 1.7 | 1.7 | 10 | 750 | 1275 | 8
6 | 11.24.05.200.9 | 1/4W 1% SMD Resistor | SMD | 100 | R11,R20,R25,R28,R230,R234 |  | 0.02 | 0.12 | 60 | 4500 | 90 | 9
8 | 11.24.05.400.3 | 1/4W 1% SMD Resistor | SMD | 10K | R110->R111,R121,R126,R130->R131,R136,R139 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 10
3 | 11.24.05.391.7 | 1/4W 1% SMD Resistor | SMD | 9.1K | R112,R132,R137 |  | 0.02 | 0.06 | 30 | 2250 | 45 | 11
18 |  | Specified On Test (S.O.T) SMD Resistor | SMD | oo | R164->R165,R169->R170,R174->R175,R179->R180,R184->R185,R189->R190,R194->R195,R199->R200 |  | 0 | 0 | 180 | 13500 | 0 | 12
1 | 11.24.05.333.7 | 1/4W 1% SMD Resistor | SMD | 3.3K | R115 |  | 0.02 | 0.02 | 10 | 750 | 15 | 13
1 | 11.24.05.316.8 | 1/4W 1% SMD Resistor | SMD | 1.6K | R116 |  | 0.02 | 0.02 | 10 | 750 | 15 | 14
25 | 11.24.05.151.1 | 1/4W 1% SMD Resistor | SMD | 51 | R12->R13,R21->R24,R26->R27,R30->R45,R158 |  | 0.02 | 0.5 | 250 | 18750 | 375 | 15
1 | 11.24.05.368.6 | 1/4W 1% SMD Resistor | SMD | 6.8K | R120 |  | 0.02 | 0.02 | 10 | 750 | 15 | 16
1 | 11.24.05.439.8 | 1/4W 1% SMD Resistor | SMD | 39K | R125 |  | 0.02 | 0.02 | 10 | 750 | 15 | 17
1 | 11.24.05.362.2 | 1/4W 1% SMD Resistor | SMD | 6.2K | R129 |  | 0.02 | 0.02 | 10 | 750 | 15 | 18
1 | 11.24.05.411.0 | 1/4W 1% SMD Resistor | SMD | 11K | R140 |  | 0.02 | 0.02 | 10 | 750 | 15 | 19
1 | 11.24.05.327.5 | 1/4W 1% SMD Resistor | SMD | 2.7K | R143 |  | 0.02 | 0.02 | 10 | 750 | 15 | 20
1 | 11.24.05.324.8 | 1/4W 1% SMD Resistor | SMD | 2.4K | R144 |  | 0.02 | 0.02 | 10 | 750 | 15 | 21
5 | 11.24.05.000.5 | SMD Jumper | SMD | 00 | R146,R225->R226,R233,R236 |  | 0.02 | 0.1 | 50 | 3750 | 75 | 22
1 | 11.24.05.336.4 | 1/4W 1% SMD Resistor | SMD | 3.6K | R147 |  | 0.02 | 0.02 | 10 | 750 | 15 | 23
2 | 11.24.05.422.7 | 1/4W 1% SMD Resistor | SMD | 22K | R148,R232 |  | 0.02 | 0.04 | 20 | 1500 | 30 | 24
2 | 11.24.05.224.1 | 1/4W 1% SMD Resistor | SMD | 240 | R150,R153 |  | 0.02 | 0.04 | 20 | 1500 | 30 | 25
1 | 11.24.05.312.2 | 1/4W 1% SMD Resistor | SMD | 1.2K | R159 |  | 0.02 | 0.02 | 10 | 750 | 15 | 26
1 | 11.24.05.320.2 | 1/4W 1% SMD Resistor | SMD | 2K | R160 |  | 0.02 | 0.02 | 10 | 750 | 15 | 27
8 | 11.24.05.239.4 | 1/4W 1% SMD Resistor | SMD | 390 | R163,R168,R173,R178,R183,R188,R193,R198 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 28
8 | 11.24.05.322.0 | 1/4W 1% SMD Resistor | SMD | 2.2K | R166,R171,R176,R181,R186,R191,R196,R201 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 29
1 | 11.24.05.315.9 | 1/4W 1% SMD Resistor | SMD | 1.5K | R235 |  | 0.02 | 0.02 | 10 | 750 | 15 | 30
2 | 11.24.05.412.9 | 1/4W 1% SMD Resistor | SMD | 12K | R29,R219 |  | 0.02 | 0.04 | 20 | 1500 | 30 | 31
49 | 11.24.05.247.4 | 1/4W 1% SMD Resistor | SMD | 470 | R46,R47,R52,R54,R55,R60,R62,R63,R68,R70,R71,R76,R78,R79,R84,R86,R87,R92,R94,R95,R100,R102,R103,R108,R133,R167,R172,R177,R182,R187,R192,R197,R202,R218 |  | 0.02 | 0.98 | 490 | 36750 | 735 | 32
16 | 11.24.05.351.5 | 1/4W 1% SMD Resistor | SMD | 5.1K | R48,R56,R64,R72,R80,R88,R96,R104,R114,R118,R122,R123,R124,R128,R138,R142 |  | 0.02 | 0.32 | 160 | 12000 | 240 | 33
8 | 11.24.05.356.0 | 1/4W 1% SMD Resistor | SMD | 5.6K | R50,R59,R66,R75,R82,R91,R98,R107 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 34
8 | 11.24.05.500.0 | 1/4W 1% SMD Resistor | SMD | 100K | R53,R61,R69,R77,R85,R93,R101,R109 |  | 0.02 | 0.16 | 80 | 6000 | 120 | 35
48 | 11.24.05.300.6 | 1/4W 1% SMD Resistor | SMD | 1K | R9,R10,R14->R19,R49,R51,R57,R58,R65,R67,R73,R74,R81,R83,R89,R90,R97,R99,R105,R106,R117,R119,R127,R135,R141,R145,R149,R151,R152,R154->R157,R161,R162,R220->R224,R227->R229,R231 |  | 0.02 | 0.96 | 480 | 36000 | 720 | 36
1 |  | SMD Selection Jumper R0805 | SMD | 00 | ST1 |  | 0 | 0 | 10 | 750 | 0 | 37
6 |  | SMD Stand-Alone Pin for Probe Test Pin | SMD |  | ST2->ST7 |  | 0 | 0 | 60 | 4500 | 0 | 38
20 |  | Standalone Pin for Test Probe |  | Mounted | TP1->TP20 |  | 0 | 0 | 200 | 15000 | 0 | 39
2 | 47.62.59.257.0 | Vis 2,5X10 |  |  | montage connecteur |  | 0.01 | 0.02 | 20 | 1500 | 15 | 40
2 | 47.41.65.025.5 | Ecrou M2,5 |  |  | montage connecteur |  | 0.01 | 0.02 | 20 | 1500 | 15 | 41
711 | [7 empty] | 1221.6786 | 7110 | 533250 | 916258.935