## General
2004-02-16 |  |  |  | Planning Beam Loss monitors
|  | 2004 |  |  |  | 2005 |  |  |  | 2006 |  |  |  | 2007
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
7--8
Front end electronics, Power supply developpement | bar: Q1 to 2004 Q3; 2006 Q2
Front end electronics, Power supply production | bar: 2004 Q4 to 2005 Q4; 2006 Q2; 2007 Q3
Front end electronics, Power supply tests | bar: 2005 Q2 to 2006 Q2; 2007 Q3
[10 empty] | S |  |  |  |  | C
Digital elctronics developpement | bar: Q1 to 2004 Q4; 2006 Q2
Digital elctronics pruduction | bar: 2004 Q1 to 2006 Q2
Digital elctronics tests | bar: 2005 Q2 to 2006 Q3
[10 empty] | B |  |  |  |  | B
Ionisation chamber, SEM developpement | bar: Q1 to 2004 Q3; 2006 Q2; 2007 Q3
Ionisation chamber, SEM production | bar: 2004 Q4 to 2006 Q2; 2007 Q3
Ionisation chamber, SEM test | bar: 2005 Q2 to 2006 Q3
Installation of fibres | bar: Q1 to 2005 Q4; 2006 Q2
Installation of cupper cables (BJBAP, BJBHT, NG18, CBH50) | bar: Q1 to 2005 Q4; 2006 Q2
Check of cupper cable (NG18, CBH50) | bar: Q1 to 2005 Q4; 2006 Q2
Production, test CBH50, CB50 cables (short cables) | bar: 2004 Q1 to 2005 Q4; 2006 Q2
Installation of chambers | bar: 2005 Q3 to 2006 Q1
Installation of short cables | bar: 2005 Q3 to 2006 Q1
Installation of crates in the tunnel | bar: 2005 Q3 to 2006 Q1
Post-installation check of cabling | bar: 2005 Q3 to 2006 Q1
Installation of crates in the surface | bar: 2005 Q4 to 2006 Q1
Test of each channel from surface | bar: 2005 Q4 to 2006 Q1
Developpement | bar: Q1 to 2004 Q3
Production, Tests | bar: 2004 Q4 to 2006 Q3
Installation | bar: 2005 Q3 to 2006 Q1

## Tunnel Inst
23/3/2004 | [5 empty] | Beam Loss LHC installation planning
SECTOR |  |  |  | 7- 8 |  |  | 8 -1 |  |  |  | 4 - 5 |  |  | 3- 4 |  |  | 5- 6 |  |  | 6- 7 |  |  | 2- 3 |  |  | 1- 2
2004 | Apr
May
Jun
Jul
Aug
Sep
| Oct | [28 empty] | 1 | Check location
| Nov | [29 empty] | 1 week / sector 70 quad, 2 persons
| Dec | [27 empty] | BL section |  | 8 weeks / LHC 16 man weeks
2005 | Jan
| Feb | [28 empty] | 2 | Supports installation
| Mar | [28 empty] | 3 | Chambers installation
| Apr | [28 empty] | 4 | Mini rack installation ( BPM BLM) under quad
| May | [29 empty] | ( electrical car in the tunnel)
| Jun | [29 empty] | ( transport of materials from lab to SR to Tunnel)
| Jul | [29 empty] | 1/2 day/ 2 quadrupole 16 chambers 2 persons
| Aug |  | 1 |  | 1 | 1 |  | 1 | [22 empty] | 70 quad 420 chambres 17.5 days 4 weeks
| Sep |  | 4 | 4 | 2 | 4 | 4 | 2 | [20 empty] | External |  | 35 weeks/LHC 70 man weeks
Oct
Nov
| Dec | [28 empty] | 5 | Cupper cables installation
2006 | Jan | [8 empty] | 1 |  | 1 | [17 empty] | 6 | Fiber patch pannel installation
| Feb | [8 empty] | 4 | 4 | 2 | [17 empty] | 7 | Micro fip installation
| Mar | [11 empty] | 1 |  | 1 | [14 empty] | 8 | Cupper cables connection on the chambers
| Apr | [11 empty] | 4 | 4 | 2 | [15 empty] | 1/2 day/ 2 quadrupole 24 cables 2 persons
| May | [29 empty] | 70 quad 1680 cables 17.5 days 4 weeks
| Jun | [27 empty] | External |  | 35 weeks/LHC 70 man weeks
| Jul |  |  |  |  | BEAM
| Aug | [14 empty] | 1 |  | 1 | [11 empty] | 9 | Chassis installation (under quadrupole) with BPM
| Sep | [14 empty] | 4 | 4 | 2 | 1 |  | 1 | [8 empty] | 10 | High Voltage cables test (CBH50)
| Oct | [14 empty] | 1 | 1 | 1 | 4 | 4 | 2 | 1 |  | 1 | [5 empty] | 11 | Analog cables test (CB50) (with picometer and current source)
| Nov | [14 empty] | (Dump) |  |  | 1 | 1 | 1 | 4 | 4 | 2 | [5 empty] | 12 | Cables connection on the chassis
| Dec | [17 empty] | (Collim.) |  |  | 1 | 1 | 1 | [5 empty] | 13 | CFC installation and test
2007 | Jan | [20 empty] | (Collim.) |  |  | 1 |  | 1 |  |  | 14 | Optical fibres installation
| Feb | [23 empty] | 4 | 4 | 2 |  |  | 15 | Test from surface
| Mar | [29 empty] | 1 day 8 quad 8CFC, 8 Alim, 18 otical cords, 3- 4 persons
| Apr | Final test | [6 empty] | Final test | [6 empty] | Final test | [5 empty] | Final test | [8 empty] | 70 quad 9 days 2 weeks/ sector 3- 4 persons
| May | [27 empty] | BL section |  | 19 weeks/LHC 57 or 72 man weeks
Jun
Jul
| Aug |  | BEAM |  |  | BEAM |  |  |  | BEAM |  |  | BEAM |  |  | BEAM |  |  | BEAM |  |  | BEAM |  |  | BEAM |  |  |  |  | 16 | Surface installation
| Sep | [29 empty] | 1 week / point 2 persons
| Oct | [27 empty] | BL section |  | 8 weeks / LHC 16 man weeks
Nov
Dec
Total
Weeks | EXT |  | 8 |  |  | 8 |  |  |  | 8 |  |  | 8 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 8 |  |  | 70
Weeks | BL |  | 4 |  |  | 4 |  |  |  | 4 |  |  | 4 |  |  | 5 |  |  | 5 |  |  | 5 |  |  | 4 |  |  | 35
Generals Interconnections Works
Works | EXT |  |  | Works 2 - 4 | [6 empty] | Works 5 - 8 | [10 empty] | 140 man weeks
Works | BL |  |  | Works 1 | [6 empty] | Works 9 - 15 | [5 empty] | Works 16 |  |  |  |  | 89 or 104 man weeks

## BLM&BPM Installation
22/3/2004 |  |  | LHC installation planning (Beam Loss and BPM)
SECTOR |  | 7 - 8 |  |  |  |  | 8 - 1 |  |  |  |  | 4 - 5 |  |  |  |  | 3 - 4 |  |  |  |  | 5 - 6 |  |  |  |  | 6 - 7 |  |  |  |  | 2 - 3 |  |  |  |  | 1 - 2 | [5 empty] | Work Performed by | Installation Step | Description
2004 | Apr | [41 empty] | BL Section | 1 | Check and number location
| May | [41 empty] | 2 Persons |  | 1 week per sector (70 quads)
Jun
| Jul | [41 empty] | External (BDI-BL) | 2 | Support installation
| Aug | [41 empty] | 2 Persons | 3 | Chamber installation
| Sep | [42 empty] | 4 | Mini-rack installation
| Oct | [43 empty] | 4 quads per day Þ 16 chambers
| Nov | [43 empty] | 70 quads Þ 420 chambres Þ 17.5 days (4 weeks)
Dec
2005 | Jan | [41 empty] | TS-EL | 5 | BLM Cable installation
| Feb | [41 empty] | J-C. Guillaume | 6 | BLM cable connection to the chambers
| Mar | [41 empty] | 2 Persons |  | 4 quads per day Þ 24 cables
| Apr | [43 empty] | 70 quads Þ 1680 cables Þ 17.5 days (4 weeks)
May
| Jun | [41 empty] | TS-EL | 7 | Installation of fibre-optic patch panel
| Jul | [41 empty] | L. de Jonge | 8 | Fibre-optic termination and test
| Aug |  | 1 | 1 | 4 |  |  | 1 | 1 | 4 | [32 empty] | 2 Persons |  | X quads per day Þ X patch panels & X terminations
| Sep |  | 4 | 2 | 2 | 2 |  | 4 | 2 | 2 | 2 | [33 empty] | 70 quads Þ 70 patch-panels & XX terminations Þ XX days (X weeks)
Oct
| Nov | [41 empty] | External (BDI-EM) | 9 | Install chassis under quadrupole
| Dec | [41 empty] | 2 Persons | 10 | Connect BPM cables
2006 | Jan | [11 empty] | 1 | 1 | 4 | [28 empty] | 11 | Connect fibre-optic cables
| Feb | [11 empty] | 4 | 2 | 2 | 2 | [28 empty] | 8 quads per day Þ 8 chassis, 64 coax cables, 64 optical patch cords
| Mar | [16 empty] | 1 | 1 | 4 | [24 empty] | 70 quads Þ 9 days (2 weeks)
| Apr | [16 empty] | 4 | 2 | 2 | 2
| May | [41 empty] | EM Section | 12 | Test of chassis using local WorldFIP link
| Jun | [41 empty] | 2/3 Persons | 13 | Check of fibre-optic connection to the surface
| Jul | [6 empty] | BEAM | [35 empty] | 14 | Test of chassis using full WorldFIP link
| Aug | [21 empty] | 1 | 1 | 5 | [19 empty] | 8 quads per day
| Sep | [21 empty] | 5 | 2 | 2 | 3 |  | 1 | 1 | 5 | [14 empty] | 70 quads Þ 9 days (2 weeks)
| Oct | [26 empty] | 5 | 2 | 2 | 3
| Nov | [31 empty] | 1 | 1 | 5 | [7 empty] | BL Section | 15 | High Voltage cables test (CBH50)
| Dec | [31 empty] | 5 | 2 | 2 | 3 | [6 empty] | 2/3 Persons | 16 | Analog cables test (CB50) (with picometer and current source)
2007 | Jan | [36 empty] | 1 | 1 | 4 |  |  |  | 17 | Cables connection on the chassis
| Feb | [36 empty] | 4 | 2 | 2 | 2 |  |  | 18 | CFC installation and test
| Mar | [42 empty] | 19 | Optical fibres installation
| Apr | Final test | [9 empty] | Final test | [10 empty] | Final test | [9 empty] | Final test | [10 empty] | 20 | Test from surface
| May | [43 empty] | 8 quads per day Þ 8 CFC, 8 Alim, 18 optical patch cords
| Jun | [43 empty] | 70 quads Þ 9 days (2 weeks)
| Jul | [41 empty] | EM Section | 21 | Surface installation
| Aug |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | BEAM |  |  |  |  | 2 Persons
| Sep | [41 empty] | BL Section
| Oct | [41 empty] | 2 Persons |  | 1 week per Point
Nov
Dec
Total
Weeks | EXT-BDI |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 7 |  |  |  |  | 7 |  |  |  |  | 6 |  |  |  | 51
Weeks | EXT-TS/EL |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 5 |  |  |  |  | 5 |  |  |  |  | 4 |  |  |  | 35
Weeks | BL |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 5 |  |  |  |  | 5 |  |  |  |  | 4 |  |  |  | 35
Weeks | EM |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  | 24
General Interconnections Works
Work | EXT-BDI |  |  | Steps 2 - 4 | [9 empty] | Steps 9 - 11 | [21 empty] | 204 |  |  |  | Man Weeks
Work | EXT-TS/EL |  |  | Steps 5 - 8 | [31 empty] | 140 |  |  |  | Man Weeks
Work | BL |  |  | Step 1 | [9 empty] | Step 15 - 20 | [9 empty] | Step 21 | [11 empty] | 210 |  |  |  | Man Weeks
Work | EM | [12 empty] | Step 12-14 | [9 empty] | Step 21 | [11 empty] | 96 |  |  |  | Man Weeks

## Planning simplifié
Secteurs
|  |  | 56 | 67 |  | 78 | 81 | 12 | 23 | 34 | 45
2004 | 2004-02-01 | 2004-02-02
2004-02-09
2004-02-16
2004-02-23
| 2004-03-01 | 2004-03-01
2004-03-08
2004-03-15
2004-03-22
2004-03-29
| 2004-04-01 | 2004-04-05
2004-04-12
2004-04-19
2004-04-26
| 2004-05-01 | 2004-05-03
2004-05-10
2004-05-17
2004-05-24
2004-05-31
| 2004-06-01 | 2004-06-07
2004-06-14
2004-06-21
2004-06-28
| 2004-07-01 | 2004-07-05
2004-07-12
2004-07-19
2004-07-26
| 2004-08-01 | 2004-08-02
2004-08-09
2004-08-16
2004-08-23
2004-08-30
| 2004-09-01 | 2004-09-06
2004-09-13
2004-09-20
2004-09-27
| 2004-10-01 | 2004-10-04
2004-10-11
2004-10-18
2004-10-25
| 2004-11-01 | 2004-11-01
2004-11-08
2004-11-15
2004-11-22
2004-11-29
| 2004-12-01 | 2004-12-06
2004-12-13
2005 | 2005-01-01 | 2005-01-03
2005-01-10
2005-01-17
2005-01-24
2005-01-31
| 2005-02-01 | 2005-02-07
2005-02-14
2005-02-21
2005-02-28
| 2005-03-01 | 2005-03-07
2005-03-14
2005-03-21
2005-03-28
| 2005-04-01 | 2005-04-04
2005-04-11
2005-04-18
2005-04-25
| 2005-05-01 | 2005-05-02
2005-05-09
2005-05-16
2005-05-23
2005-05-30
| 2005-06-01 | 2005-06-06
2005-06-13
2005-06-20
2005-06-27
| 2005-07-01 | 2005-07-04
2005-07-11
2005-07-18
2005-07-25
| 2005-08-01 | 2005-08-01
2005-08-08
2005-08-15
2005-08-22
2005-08-29
| 2005-09-01 | 2005-09-05
2005-09-12
2005-09-19
2005-09-26
| 2005-10-01 | 2005-10-03
2005-10-10
2005-10-17
2005-10-24
2005-10-31
| 2005-11-01 | 2005-11-07
2005-11-14
2005-11-21
2005-11-28
| 2005-12-01 | 2005-12-05
2005-12-12
2005-12-19
2006 | 2006-01-01 | 2006-01-09
2006-01-16
2006-01-23
2006-01-30
| 2006-02-01 | 2006-02-06
2006-02-13
2006-02-20
2006-02-27
| 2006-03-01 | 2006-03-06
2006-03-13
2006-03-20
2006-03-27
| 2006-04-01 | 2006-04-03
2006-04-10
2006-04-17
2006-04-24
| 2006-05-01 | 2006-05-01
2006-05-08
2006-05-15
2006-05-22
2006-05-29
| 2006-06-01 | 2006-06-05
2006-06-12
2006-06-19
2006-06-26
| 2006-07-01 | 2006-07-03
2006-07-10
2006-07-17
2006-07-24
2006-07-31
| 2006-08-01 | 2006-08-07
2006-08-14
2006-08-21
2006-08-28
| 2006-09-01 | 2006-09-04
2006-09-11
2006-09-18
2006-09-25
| 2006-10-01 | 2006-10-02
2006-10-09
2006-10-16
2006-10-23
2006-10-30
| 2006-11-01 | 2006-11-06
2006-11-13
2006-11-20
2006-11-27
| 2006-12-01 | 2006-12-04
2006-12-11
2006-12-18
2007 | 2007-01-01 | 2007-01-08
2007-01-15
2007-01-22
2007-01-29
| 2007-02-01 | 2007-02-05
2007-02-12
2007-02-19
2007-02-26
| 2007-03-01 | 2007-03-05
2007-03-12
2007-03-19
2007-03-26
| 2007-04-01 | 2007-04-02
2007-04-09
2007-04-16
2007-04-23
2007-04-30
| 2007-05-01 | 2007-05-07
2007-05-14
2007-05-21
2007-05-28
| 2007-06-01 | 2007-06-04
2007-06-11
2007-06-18
2007-06-25
| 2007-07-01 | 2007-07-02
2007-07-09
2007-07-16
2007-07-23
2007-07-30
| 2007-08-01 | 2007-08-06
2007-08-13
2007-08-20
2007-08-27
| 2007-09-01 | 2007-09-03
2007-09-10
2007-09-17
2007-09-24
| 2007-10-01 | 2007-10-01
2007-10-08
2007-10-15
2007-10-22
2007-10-29
| 2007-11-01 | 2007-11-05
2007-11-12
2007-11-19
2007-11-26
| 2007-12-01 | 2007-12-03
2007-12-10
2007-12-17
General Services
QRL installation
QRL associated works
QRL cold tests and commisioning
Interconnections works
Arc and DS magnets inst.
LSS installation
Transport
El-qa at warm, cooldown, El-qa at cold
Powering tests
BLM installation